## TDB2
TMNA TDB2 MIGRATION EXECUTION RUNBOOK - Draft (V12 → V13)
JCLLIB : DB2SYS.V13.REMIG.JCL
Pre-migration Phase
S.No | Job Name | Description | OWNER | STATUS | Notes/Comments
1 | CHECK DATA | Run Check data utility | IBM
2 | DSNTESQ | Run the queries & DSNTIJPE | IBM
3 | DSNTIJIC | Take image copy of Directory and Catalog catalogs of V12 | IBM
4 | DISPLAY | Display all the Threads / Running Utils & Restricted objects. | IBM
5 | Bring down all the external connections, Stop all connected subsystems(CICS, IMS, MQ) , other connected regions to TDB2 |  | TMNA
6 | STOPDB2 | /= STOP DB2 | IBM / TMNA
7 | DSN1COPY | Run this utility with CHECK option on catalog tablespaces | IBM
8 | LLA & Linklist | Add the Db2 link dataset in LLA & Linklist : DB2TN.DB2V12.SDSNLINK ( verify the status and if possible can we create V13 dataset separetely) | TMNA |  | Check if this has been performed during V13 upgrade
V13 Re-Migration Phase
9 | DB2DUMP | Take a dump of DB2 Catalog, Directory, Logs and BSDS | IBM
10 | CREBKUP1 | Take a backup of RUNLIB.LOAD, DBRMLIB.DATA & SRCLIB.DATA | IBM
11 | CREBKUP2 | Take backup of existing runtime library - SDSNLOAD, SDSNLOD2, SDSRRESL | IBM
12 | COPYREPL | Compress and Copy replace, compress of SDSNLOAD, SDSNLOD2, SDSRRESL | IBM
13 | DSNTIJUZ | Run the DSNTIJUZ zPARM job | IBM
14 | DSNTIJUA | Assemble & Linkedit Application Default module DSNHDECP | IBM
15 | DSNTIJUM | Assemble DSNHMCID DATA-ONLY LOAD MODULE | IBM
16 | COPYEXIT | Copy modules from existing SDSNEXIT to SDSNEXIT, SDSNLOAD | IBM
17 | DB2 early code Refresh | Early code refresh /-ssid REFRESH DB2,EARLY | IBM
18 | START DB2 in maint mode | /= START DB2 ACCESS(MAINT) | IBM
19 | DSNTIJTC | Catalog Maintenance job | IBM
20 | Check the Space in DB2 related Storage group volume
21 | V13JIC | V13 Image copy | IBM
22 | DSNTIJTM | Prepare dynamic SQL program | IBM
23 | DSNTIJSG | Bind SPUFI/DCLGEN and user-maintained DB Step DSNTIJP = 8 is acceptable | IBM
24 | DSNTIJCL | CLI Binds | IBM
25 | DSNTIJRT | Set up DB2-supplied routines - In Install-Preview mode | IBM
26 | DSNTIJRT | Set up DB2-supplied routines - In Install mode | IBM
27 | Update the PARMLIB for UTILITY SUITE and activate dynamically |  | TMNA |  | Check if this has been performed during V13 upgrade
28 | DSNTEJ0 | IVP Jobs | IBM
29 | DSNTEJ1 | IVP Jobs | IBM
30 | DSNTEJ1L | IVP Jobs | IBM
31 | DSNTEJ2A | IVP Jobs | IBM
32 | STOPDB2 | /= STOP DB2 | IBM
33 | STARTDB2 | /= START DB2 | IBM
34 |  | Start all connected subsystems(CICS, IMS, MQ), other connected regions to TDB2 | TMNA
35 | EXPLAIN TABLES | DSNTIJXA job | IBM
36 | DISPLAY | Display all the Threads / Running Utils & Restricted objects. | IBM
37 |  | Post Implementation verification - DB2 SPUFI, Utilities, Tools, etc | IBM
Testing Phase
38 |  | Inform respective Application teams for Sanity Testing | TMNA
39 |  | Application Testing, IBM Team on Stand-by | TMNA/IBM
40 |  | GO/NO-GO decision – all stakeholders confirm | TMNA
Backout Phase( Only if Required)
BACKOUT- PLAN
S.No | Job Name | Description | OWNER | STATUS | Notes/Comments
1 | Stop extenal connections, applications to TDB2 |  | TMNA
2 | Stop DB2 | /=STOP DB2 | IBM
3 | BKOUT1 | Rename Current runtime to .V13BKP | IBM
4 | BKOUT2 | Rename .V12FL510.BKP to runtime dataset | IBM
5 | Start Db2 in maint mode | /= START DB2 ACCESS(MAINT) | IBM
6 | JCLLIB: DB2SYS.V12.BKOUT.JCL
7 | DSNTIJIC | Image copy job | IBM
8 | DSNTIJTM | Prepare dynamic SQL program | IBM
9 | DSNTIJSG | Bind SPUFI/DCLGEN and user-maintained DB Step DSNTIJP = 8 is acceptable | IBM
10 | DSNTIJCL | CLI Binds | IBM
11 | DSNTIJRT | Set up DB2-supplied routines - In Install-Preview mode | IBM
12 | DSNTIJRT | Set up DB2-supplied routines - In Install mode | IBM
13 | DSNTEJ0 | IVP Jobs | IBM
14 | DSNTEJ1 | IVP Jobs | IBM
15 | DSNTEJ1L | IVP Jobs | IBM
16 | DSNTEJ2A | IVP Jobs | IBM
17 | STOP DB2 | /= STOP DB2 | IBM
18 | START DB2 | /= START DB2 | IBM
19 |  | Start all connected subsystems(CICS, IMS, MQ), other connected regions to TDB2 | TMNA
20 | DISPLAY | Display all the Threads / Running Utils & Restricted objects. | IBM
21 |  | Post Implementation verification - DB2 SPUFI, Utilities, Tools, etc | IBM
22 |  | Inform respective Application teams for Sanity Testing | TMNA
23 |  | Application Testing, IBM Team will be on Stand-by | TMNA/IBM