## Overview
Db2 for z/OS Post-Change Validation Checklist
Standard validation to confirm Db2 and its dependent services are ready for business processing after an IPL, maintenance or configuration change.
Item | Description
Purpose | Confirm that Db2, Java/WLM stored procedure environments, applications and tools work end to end before a change is closed.
When to use | After any IPL, Db2 or z/OS maintenance, Java upgrade, WLM change or configuration change affecting Db2.
Scope | Db2 subsystem health, SQL and data, logging and recovery, DDF connectivity, WLM and Java stored procedures, batch and CICS, QMF, Admin Tool, HPU, utilities and monitoring.
Key principle | A successful Db2 startup alone does not confirm that applications, Java routines or tools are working. Dependent services must be validated.
Closure rule | A change is closed only when all Required checks (and applicable checks) are met and dependency documentation is updated.
Validation Areas
Validation Area | No. of Checks | Required | What It Confirms
Subsystem Foundations | 6 | 6 | Db2 is up, correctly configured and error-free.
Database and SQL | 8 | 8 | Data, packages and security work correctly.
Logging and Recovery | 3 | 2 | Logs and backups support recovery.
Distributed Connectivity | 4 | 4 | Remote and encrypted connections work.
WLM and Stored Procedures | 8 | 7 | Java/WLM environments and stored procedures run correctly.
Application Processing | 4 | 3 | Batch, CICS and critical business paths complete.
QMF | 4 | 4 | Query and reporting tool works.
Db2 Administration Tool | 3 | 3 | Admin tool works against the correct subsystem.
High Performance Unload | 3 | 3 | Unload tool works and output reconciles.
Utilities | 4 | 1 | Db2 utilities run correctly.
Monitoring and Resilience | 4 | 2 | Monitoring, performance and restart resilience.
Release and Closure | 1 | 1 | End-to-end verification and formal closure.
Total | 52 | 44
Check Types
Type | Meaning
Required | Performed after every IPL or system/runtime change.
If applicable | Performed only where the component is configured (e.g. data sharing, IMS).
Scheduled | Deeper or intrusive tests performed in an approved maintenance window.
Responsibilities
Role | Responsibility
Db2 Support | Subsystem, SQL, stored procedure, tool, log and utility checks.
z/OS Support | Libraries, WLM, Java runtime, file system mounts and startup configuration.
Application / CICS Support | Batch jobs, transactions, APIs and business output.
Security / Network Support | Access, certificates, TLS and connectivity.
Change Owner | Reviews results and approves change closure.

## Validation Checklist
ID | Validation Area | Validation Check | Objective | Acceptance Criteria | Owner | Check Type
V01 | Subsystem Foundations | Subsystem identity and routing | Commands and SQL reach the intended subsystem and location. | Every route resolves to the approved subsystem and location. | Db2 Support | Required
V02 | Subsystem Foundations | Db2 release and maintenance level | Code, catalog and function levels and maintenance match the approved target. | Levels match target; prerequisites and HOLD actions satisfied. | Db2 Support | Required
V03 | Subsystem Foundations | Address spaces and startup | MSTR, DBM1, IRLM and DIST started cleanly and remain healthy. | All components active; startup completed with no unresolved errors. | Db2 Support | Required
V04 | Subsystem Foundations | Procedure libraries and subsystem definitions | Active and restart library references and APF settings are correct. | Effective and restart configuration reference approved libraries. | Db2 / z/OS Support | Required
V05 | Subsystem Foundations | System parameters and attachments | Live DSNZPARM values and attachment settings match the baseline. | Effective values match baseline; attachments target the correct subsystem. | Db2 Support | Required
V06 | Subsystem Foundations | Message and dump review | Logs reviewed for new severe errors, abends or dumps. | No new unexplained errors or dumps; known items dispositioned. | Db2 Support | Required
V07 | Database and SQL | Catalog and directory access | Db2 catalog and directory are readable and unrestricted. | Catalog query succeeds; no restrictive states. | Db2 Support | Required
V08 | Database and SQL | Application object availability | Critical databases, table spaces and indexes are available. | Required objects available; no unapproved pending states. | Db2 Support | Required
V09 | Database and SQL | Buffer pools and work files | Buffer pools and work files are operating within limits. | Pools and work files usable; performance within baseline. | Db2 Support | Required
V10 | Database and SQL | Packages, plans and APPLCOMPAT | Critical packages and plans are valid with correct compatibility. | Packages valid and operative; APPLCOMPAT appropriate. | Db2 Support | Required
V11 | Database and SQL | Basic SQL and business reads | Basic SQL and representative business reads return correct data. | SQL succeeds; values match reference data. | Db2 Support | Required
V12 | Database and SQL | Commit, rollback and data integrity | Transactional behaviour verified using dedicated test data. | Rollback and commit behave correctly; test data cleaned up. | Db2 Support | Required
V13 | Database and SQL | Authorities and execution identities | Normal service IDs can perform required operations. | Required operations succeed with normal IDs; unauthorised access denied. | Db2 / Security Support | Required
V14 | Database and SQL | Locks, threads and in-doubt work | No unexplained blocking or in-doubt transactions. | Thread activity consistent with workload; no in-doubt work. | Db2 Support | Required
V15 | Logging and Recovery | Active logs and offload | Logging and archive offload are progressing normally. | Logs progress and offload runs without failures. | Db2 Support | Required
V16 | Logging and Recovery | Backup and recovery inventory | Image copies and archive logs support the recovery requirement. | Recovery inventory complete; latest backups successful. | Db2 Support | Required
V17 | Logging and Recovery | Recovery rehearsal | Recovery of an isolated test object meets RTO/RPO. | Data recovered correctly within agreed objectives. | Db2 Support | Scheduled
V18 | Distributed Connectivity | DDF listener and location | DDF endpoints, ports and location are correctly configured. | DDF active; endpoints match approved inventory. | Db2 Support | Required
V19 | Distributed Connectivity | Remote JDBC / ODBC execution | Remote clients execute business SQL and calls successfully. | Client reaches correct server; SQL and CALL succeed. | Db2 / Application Support | Required
V20 | Distributed Connectivity | TLS certificates and encryption | Encrypted connections work with valid, trusted certificates. | Certificates valid; connection uses encrypted path. | Db2 / Security Support | Required
V21 | Distributed Connectivity | Remote locations and DDF WLM | Outbound dependencies work and DDF work is correctly classified. | Remote requests complete; correct WLM classification. | Db2 Support | Required
V22 | WLM and Stored Procedures | WLM policy and application environments | Correct WLM policy is active; required environments are available. | Policy active; all required environments available. | Db2 / z/OS Support | Required
V23 | WLM and Stored Procedures | WLM procedures and LE runtime | WLM address spaces use the correct subsystem and libraries. | Runtime initialises without allocation, LE or attach failures. | Db2 / z/OS Support | Required
V24 | WLM and Stored Procedures | Java path and persistent startup references | Java (JVM) path in WLM/JAVAENV parameters points to the current installed release. | JVM path resolves on all systems; no reference to a retired Java release. | Db2 / z/OS Support | Required
V25 | WLM and Stored Procedures | Java libraries, JARs and class paths | Required JARs and class paths are accessible to the routines. | Routine call completes without class or linkage errors. | Db2 / z/OS Support | Required
V26 | WLM and Stored Procedures | Stored procedure catalog mapping | Routine definitions map to the correct WLM environments. | Catalog mappings match approved routines and environments. | Db2 Support | Required
V27 | WLM and Stored Procedures | Stored procedure functional calls | Critical stored procedures return expected results. | Calls return expected output; no abends or queueing. | Db2 Support | Required
V28 | WLM and Stored Procedures | External functions and triggers | UDFs and trigger dependencies behave as expected. | Functions return expected values; triggers behave correctly. | Db2 Support | If applicable
V29 | WLM and Stored Procedures | Demand start and repeat calls | WLM environments start on demand and stay serviceable. | First and repeated calls succeed throughout observation. | Db2 / z/OS Support | Required
V30 | Application Processing | Critical batch SQL jobs | Critical batch jobs complete with correct output. | All steps meet expected RC; output reconciles. | Db2 / Application Support | Required
V31 | Application Processing | Critical application regression paths | Previously affected business paths are re-tested end to end. | Paths complete with correct output and no runtime errors. | Db2 / Application Support | Required
V32 | Application Processing | CICS-Db2 attachment and transactions | CICS transactions run against the correct Db2 subsystem. | Transactions complete; no attachment errors. | Db2 / Application Support | Required
V33 | Application Processing | IMS, RRS, CAF and other attachments | Alternate attachments complete their units of work. | Units of work complete; no recovery uncertainty. | Db2 / Application Support | If applicable
V34 | QMF | QMF startup and subsystem selection | QMF starts at the correct release and connects to the right subsystem. | QMF initialises and connects correctly. | Db2 Support | Required
V35 | QMF | QMF query and report execution | Queries and reports run with correct results. | Correct rows, formatting and totals. | Db2 Support | Required
V36 | QMF | QMF saved objects and repository | Saved objects can be saved, reopened and executed. | Objects work; permissions behave as designed. | Db2 Support | Required
V37 | QMF | QMF procedures, batch and export | Batch and export paths produce expected output. | All applicable routes produce expected output. | Db2 Support | Required
V38 | Db2 Administration Tool | Admin Tool startup and routing | Tool starts and connects to the correct subsystem. | Tool initialises with correct access. | Db2 Support | Required
V39 | Db2 Administration Tool | Catalog browsing, SQL and DDL | Catalog navigation and DDL generation are correct. | Output reflects correct subsystem and objects. | Db2 Support | Required
V40 | Db2 Administration Tool | Work statement lists and utilities | Generated work and utility integration function correctly. | Generated work completes with correct output. | Db2 Support | Required
V41 | High Performance Unload | HPU installation and customisation | HPU configuration matches the approved release. | Configuration supports required Db2 features. | Db2 Support | Required
V42 | High Performance Unload | HPU bounded unload | A small test unload completes and reconciles. | Expected RC; output matches reference data. | Db2 Support | Required
V43 | High Performance Unload | HPU special data paths | Required unload modes preserve data and format. | All required modes produce correct output. | Db2 Support | Required
V44 | Utilities | Utility engine and existing state | No stuck or unexplained utilities; probe completes. | Existing utilities explained; probe completes cleanly. | Db2 Support | Required
V45 | Utilities | COPY / backup | Image copy completes and is registered. | COPY successful; records present. | Db2 Support | Scheduled
V46 | Utilities | UNLOAD and LOAD | Extract and load preserve test data. | Records preserved; target in expected state. | Db2 Support | Scheduled
V47 | Utilities | REORG, RUNSTATS and CHECK | Maintenance utilities complete correctly. | Utilities complete; warnings dispositioned. | Db2 Support | Scheduled
V48 | Monitoring and Resilience | Monitoring, traces and alerts | Monitoring tools show live data for the subsystem. | Live data and alerts available. | Db2 / Monitoring Support | Required
V49 | Monitoring and Resilience | Performance and capacity | Response and resource use compared with baseline. | Within agreed thresholds; no sustained saturation. | Db2 Support | Required
V50 | Monitoring and Resilience | Data sharing and coupling facility | Data sharing members and CF structures are healthy. | Members and structures available; no retained locks. | Db2 Support | If applicable
V51 | Monitoring and Resilience | Restart, failover and persistence | Configuration survives restart and failover. | Recovery within objectives; all probes pass after restart. | Db2 / z/OS Support | Scheduled
V52 | Release and Closure | End-to-end processing and sign-off | Full business path verified and change formally closed. | All applicable checks evidenced; business outcomes correct. | Db2 / Application Support | Required