## List of Testers
2 Role Swap PRODDSS/Colo to PRODDSS/Temple
Saturday 02/22/2025 - Starting at 8:30 am
Kyle Cushman (JDE/RODS)
Michael Mclntire. and Scott Davis
Bala Mallampati (Cognos-Reports)
Uma Sundaresan/Madison Hanson
(load balance - netscaler - multiple)
Syndee Stiles
Tammy Fields (479-936-1266)
Jason Deal - DNS | Workday?
Alteryx Server - Roland M. added Feb 2025
Goldengate
Cognos
Bill/WMSHUB and BI

## iSeries
DATE: | 2025-02-22 |  |  | iSeries System Outage Agenda
Start | End |  | Steps | Activity | Sys | Sys | Sys | Sys | Notes
|  |  |  | ISERIES-907 -- CM-24663 | INFO | INFO | INFO | INFO
Friday
| done | Mary | 1 | Do a do ETS50050 *disable mimix audits | PE
| done | Mary | 2 | Hold Re* 'Saturday Jobs RE020SAT, RE030SAT, RE040SAT | PE
Saturday
8:30 |  | Ops | 1 | Start Teams Meeting
|  | Mary | 2 | Signon to CONSOLE as myself to PRODDSS/Carrollton |  | DSS/C |  |  | 10.7.1.130
|  | Mary | 3 | Logon to Teams Meeting
8:24 |  | Mary | 4 | https://olamvssprod.mclaneco.com
|  | Mary | 5 | Select Template Needed Change DNS: PRODDSS to point from 10.7.1.163 to 10.7.1.230 |  | DSS/C |  |  | ipconfig /flushdns
|  | Mary | 6 | ping after DNS chgs: RODS.APPN.SNA.IBM.COM ; PRODDSS.APPN.SNA.IBM.COM |  | DSS/C
|  | Mary | 7 | End Robot Schedule: rbo>1>3>2 |  | DSS/C
|  | Mary | 8 | ENDs Replication between PRODe/ to PRODDSS/ha
|  | Mary | 9 |  | PE
8:31 |  | Mary | 10 | MIMIX/ENDMMX and Press Enter | PE |  |  |  | if > 10 minutes
|  | Mary | 11 | MIMIX/WRKDG to monitor (proda) MIMIXIASP/WRKDG to monitor (proddssha) | PE | DSS/C |  |  | make sure all datagroups are down, end manually if needed
|  | Mary | 12 | MIMIX/WRKSYS *INACTIVE all | PE |  |  |  | Subsystem Active and ports are active
|  | Mary | 13 | After ending mimix, ports should only be *active under all 4 nodes sbs | PE | DSS/T | DSS/C | PA
|  | Mary | 14 | End mimix sbs on proddss/prod it should be showing two ports: ENDSBS SBS(MIMIXSBS) OPTION(*IMMED) |  | DSS/T
|  | Mary | 15 | End mimix sbs on proddss/ha it should be showing 1 port: ENDSBS SBS(MIMIXSBS) OPTION(*IMMED) |  |  | DSS/C
|  | Mary | 16 | Kill sbs's on proddss/prod and proddss/ha to kill ports | PE | DSS/T | DSS/C | PA | 2 ports/source….1 port/target active
|  | Mary | 17 | ENDTCPIFC INTNETADR('10.7.1.169') |  | DSS/C |  |  | Deactivate 10.7.1.169 -
|  | Mary | 18 | Verified it's ended> NETSTAT OPTION(*IFC) |  | DSS/C
|  | Mary | 19 | Before and After Images |  | DSS/C
|  | Mary | 20 | STRTCPIFC INTNETADR('10.7.1.169') |  |  | DSS/T |  | Activate 10.7.1.169 -
|  | Mary | 21 | Verified it's ended> NETSTAT OPTION(*IFC) |  |  | DSS/T
|  | Mary | 22 | Before and After Images |  |  | DSS/T
|  | Mary | 23 | Start Role Swap from Proddss/HA to Proddss/Prod
|  | Mary | 24 | Logoff and back on to CONSOLE as QSECOFR PRODDSS/Carrollton |  | DSS/C |  |  | 10.7.1.130
|  | Mary | 25 | WRKCLU |  | DSS/C
|  | Mary | 26 | Run QZRDPWRHA/CHKDUPLIBS IASP(DSSIASP) |  | DSS/C |  |  | ADDLIBLE QZRDPWRHA and QZRDHASM
|  |  | 27 | QSYS/WRKASPJOB *end all jobs |  | DSS/C
|  | Mary | 28 | Take Option 9 - Verify DSSDEVCRG Resource Group is Active and Primary Node is Correct |  | DSS/C
|  | Mary | 29 |  |  | DSS/C
|  | Mary | 30 | Option 6 |  | DSS/C
|  | Mary | 31 | Option 6 |  | DSS/C
|  | Mary | 32 | Option 6 |  | DSS/C
|  | Mary | 33 | Take Option 10 - Verify ASP Copy> Take Option 25 on DSSHA, make sure Asp Copy is Corret |  | DSS/C
|  | Mary | 34 |  |  | DSS/C
|  | Mary | 35 |  |  | DSS/C
|  | Mary | 36 | qbatch has to be active….start sbs qbatch in library qsys on all 4 nodes |  | DA/C | DSS/C
|  | Mary | 37 | Take Option 9 > Take Option 3=Change primary>dssdevcrg |  | DSS/C
|  | Mary | 38 |  |  | DSS/C
8:46 | 8:50 |  | 39 |  |  | DSS/C
|  | Mary | 40 | qbatch |  | DSS/C |  |  | Varyoff should take 2:37 on source/Job ends once it has vary off the iasp
|  | Mary | 41 | Start another session to PRODDSS/Carrollton to monitor: ASP State will go to VARYOFF |  | DSS/C
|  | Mary | 42 | Signon to CONSOLE as QSECOFR on PRODDSS/Temple to Monitor: ASP State will go to AVAILABLE |  |  | DSS/T |  | 10.7.1.180
|  | Mary | 43 |  |  |  | DSS/T |  | Takes 1:37 to varyon iasp on dss car/Once role swap starts job runs in qbatch on target system
|  | Mary | 44 | Verify Direction of Replication has been switch |  |  | DSS/T
|  | Mary | 45 | [5 empty] | 10.7.1.182 or 10.7.1.132
|  | Mary | 46 | Verify Cluster on all 4 nodes are active | PE | DSS/C | DSS/T | PA
|  | Mary | 47 | Verify 3rd party software on PRODDSS/Temple |  |  | DSS/T
|  | Mary | 48 | Apply Turnover Key |  |  | DSS/T |  | logon as me
|  | Mary | 49 | 'IFS KEY: /home/unicom/licenses/TN4/* |  |  | DSS/T |  | DOES NOT REPLICATE FOR PRODDSS
| SKIP | Mary | 50 | IBM I Access Client Solutions to rename |  |  | DSS/T
| SKIP | Mary | 51 | > RENAME License to LicenseCOLO2025 |  |  | DSS/T |  | proddssha
| SKIP | Mary | 52 | > RENAME LicenseTemple2025 to License |  |  | DSS/T |  | before role swap back to temple
| SKIP | Mary | 53 |  |  |  | DSS/T |  | LPAR 3 -
|  | Mary | 54 |  |  |  |  | DSS/C | before role swap
|  | Mary | 55 | SOFTTURNE/TWRKLIC |  |  | DSS/T |  | had to ftp M4SYS library from upgrade/*sysbas
|  | Mary | 56 | STRSBS QGPL/TSERVER if not started> STRSBS SBSD(QGPL/TSERVER) |  |  | DSS/T
|  | Mary | 57 | Option 11>Option 1>2=change PRODDSS>Change Serial number to *LOCAL and Press Enter |  |  | DSS/T |  | SN# 7858201
|  |  | 58 |  |  |  | DSS/T
|  |  | 59 |  |  |  | DSS/T
|  | Mary | 60 | Robot Schedule |  |  | DSS/T |  | login as mlengbr2
8:55 |  | Mary | 61 | Bring down RBTSLEEPER Subsystem by running RSLSHUTDWN |  |  | DSS/T |  | rbtsyslib/rslshutdwn
|  | SKIP | 62 | (RSLCHGSYSN BEFORE(PRODDSS) AFTER(PRODDSS) PRODUCT(ROBOT)) |  |  | DSS/T |  | same system name
8:59 |  | Mary | 63 | RSLSETOID PRC(RBT) |  |  | DSS/T
|  | Mary | 64 | STRSBS SBSD(RBTSYSLIB/RBTSLEEPER) |  |  | DSS/T
|  | Mary | 65 | Verify that all subsystem are Active see Tab |  |  | DSS/T
|  | Mary | 66 | Verify all tcp servers and host servers are active that should be |  |  | DSS/T
| done | Mary | 67 | Host Table Changes for PRODDSSHA |  | DSS/C |  |  | F15 Postion To
|  | Mary | 68 | RMVTCPHTE INTNETADR('10.7.1.230')
|  | Mary | 69 | RMVTCPHTE INTNETADR('10.7.1.163')
|  | Mary | 70 | ADDTCPHTE INTNETADR('10.7.1.230') HOSTNAME((PRODDSS) (PRODDSS.APPN.SNA.IBM.COM) (RODS) (MSDSS) (MXVPRDSS))
|  | Mary | 71 | ADDTCPHTE INTNETADR('10.7.1.163') HOSTNAME((BRMSDSS))
I need for MIMIX | done | Mary | 72 | Host Table Changes for PRODDSS |  |  | DSS/T |  | F15 Postion To
|  | Mary | 73 | RMVTCPHTE INTNETADR('10.7.1.230')
|  | Mary | 74 | RMVTCPHTE INTNETADR('10.7.1.163')
|  | Mary | 75 | ADDTCPHTE INTNETADR('10.7.1.230') HOSTNAME((PRODDSS) (PRODDSS.APPN.SNA.IBM.COM) (RODS) (MSDSS) (MXVPRDSS))
|  | Mary | 76 | ADDTCPHTE INTNETADR('10.7.1.163') HOSTNAME((BRMSDSS))
|  | Mary | 77 | Host Table Changes for PRODE | PE |  |  |  | F15 Postion To
|  | Mary | 78 | RMVTCPHTE INTNETADR('10.7.1.230')
|  | Mary | 79 | RMVTCPHTE INTNETADR('10.7.1.163')
|  | Mary | 80 | ADDTCPHTE INTNETADR('10.7.1.230') HOSTNAME((PRODDSS) (PRODDSS.APPN.SNA.IBM.COM) (RODS) (MSDSS) (MXVPDSS))
|  | Mary | 81 | ADDTCPHTE INTNETADR('10.7.1.163') HOSTNAME((BRMSDSS))
|  | Mary | 82 | Host Table Changes for PRODA |  | PA |  |  | F15 Postion To
|  | Mary | 83 | RMVTCPHTE INTNETADR('10.7.1.230')
|  | Mary | 84 | RMVTCPHTE INTNETADR('10.7.1.163')
|  | Mary | 85 | ADDTCPHTE INTNETADR('10.7.1.230') HOSTNAME((PRODDSS) (PRODDSS.APPN.SNA.IBM.COM) (RODS) (MSDSS) (MXVPDSS))
|  | Mary | 86 | ADDTCPHTE INTNETADR('10.7.1.163') HOSTNAME((BRMSDSS))
|  | Mary | 87 | Host Table Changes for DEVA |  | DEVA/T |  |  | F15 Postion To
|  | Mary | 88 | RMVTCPHTE INTNETADR('10.7.1.230')
|  | Mary | 89 | RMVTCPHTE INTNETADR('10.7.1.163')
|  | Mary | 90 | ADDTCPHTE INTNETADR('10.7.1.230') HOSTNAME((PRODDSS) (PRODDSS.APPN.SNA.IBM.COM) (RODSVRT))
|  | Mary | 91 | ADDTCPHTE INTNETADR('10.7.1.163') HOSTNAME((BRMSDSS))
|  | Mary | 87 | Host Table Changes for DEVA/HA |  |  |  | DEVA/C | F15 Postion To
|  | Mary | 88 | RMVTCPHTE INTNETADR('10.7.1.230')
|  | Mary | 89 | RMVTCPHTE INTNETADR('10.7.1.163')
|  | Mary | 90 | ADDTCPHTE INTNETADR('10.7.1.230') HOSTNAME((PRODDSS) (PRODDSS.APPN.SNA.IBM.COM) (RODSVRT))
|  | Mary | 91 | ADDTCPHTE INTNETADR('10.7.1.163') HOSTNAME((BRMSDSS))
|  | Mary | 92 | Turn Over To Teams for Testing
|  | OPS | 93 | See Tab 1 for List of Testers
|  | JDE | 94 | Compare counts prior to starting MIMIX
|  | Mary | 95 | Run ETS50204 RUNQRY ZMARY/ROLECNTSPE to display counts |  |  | DSS/T
|  | Mary | 96 | START MIMIX REPLICATION BETWEEN PRODE/PROD TO PRODDSS/HA |  |  | DSS/T
|  | MIMIX | 97 | STRSQL verify relational database if PRODDSS | PE |  | DSS/T |  | before on proda to proddssc
|  | MIMIX | 98 | WRKRD* delete MX_MIMIXIASP_IABA 10.7.1.169 | PE |  |  |  | dssiasp/prode&proddss;proddss/proda&proddssha
|  | MIMIX | 99 | ADDRDBDIRE RDB(DSSIASP MX_MIMIXIASP_IABA) RMTLOCNAME('10.7.1.169' *IP) **floating ip | PE |  |  |  | RDB* from DSSIASP to PRODDSS/name of the IASP in wrkrb*/*LOOPBACK is the Relational Database
|  | Mary | 100 | Verify MIMIX SBS is started on PRODA and PRODE | PE |  |  | PE
|  | Mary | 101 | Start MIMIX SBS on Proddss/Car>> STRSBS MIMIXQGPL/MIMIXSBS |  | DSS/C |  |  | Should only have 1 port active AND 10.7.1.169 S/B *inactive
|  | Mary | 102 | Start MIMIX SBS on Proddss/Prod/Temple>> STRSBS MIMIXQGPL/MIMIXSBS |  |  | DSS/T |  | Make sure both ports are active
| SEE MIMIX TAB | Mary | 103 | LOGON: MLENGBR2 > MIMIXIASP/MIMIX >MIMIXIASP/STRSVR HOST('10.7.1.169') PORT(50500) |  |  | DSS/T |  | RUN IF PORT WILL NOT START
|  | Mary | 104 | MIMIX/WRKSYS Option 9 | PE |  |  |  | starts communication
|  | Mary | 105 | MIMIX/STRMMX to start replication | PE
|  | Mary | 106 |  | PE
|  | JDE | 107 | Check File counts once MIMIX has been Started to make sure they are changing |  |  | DSS/T
|  | Mary | 108 | Run ETS50205 RUNQRY ZMARY/ROLECNTSPA to display before counts |  |  | DSS/T
|  | Mary | 109 | MISC
|  | Mary | 110 | Make Sure Robot Schedule has Been Started |  |  | DSS/T |  | Check robot/console AND robot alert
|  | Mary | 111 | Run miss jobs/start robot jobs that need to be started |  |  | DSS/T
|  | Mary | 112 | Robot Schedule: display missed jobs time frame: 0827 to ???? date: 02/22/2025 |  |  | DSS/T
|  | Mary | 113 | Do a 'DO' on ETS50020 Terminated jobs |  |  | DSS/T
|  | Mary | 114 | Release 'Saturday Jobs RE020SAT, RE030SAT, RE040SAT' and DO if needed | PE
|  | Mary | 115 | Release ETS50051 *enable mimix audits | PE
|  | Mary | 116 | Verify that performance is running |  |  | DSS/T
|  | Mary | 117 | Do a 'DO' on ETS50001 Disable APPADMIN & SYSMGMT |  |  | DSS/T
|  | Mary | 118 | DO' on Robot job ETS40080 to Reset Robot Host Node for GUI monitor |  |  | DSS/T |  | ROBOT NETWORK GUI AFTER ROLE SWAP
|  | Mary | 119 | ROBOT GUI - NETWORK
|  | Mary | 120 | RBTNETNODE/RBNENDNODE |  |  | DSS/T
|  | Mary | 121 | RSLWL |  |  | DSS/T |  | IFS
|  | Mary | 122 | ROBOT NETWORK>nodeConfig.xml >>>search on Primary Shift/F4 |  |  | DSS/T
|  | Mary | 123 | RBTNETNODE/RBNCFGNODE HOSTIP('10.7.1.239') AHOSTIP(*NONE) |  |  | DSS/T
|  | Mary | 124 | RBTNETNODE/RBNSTRNODE |  |  | DSS/T
|  | Mary | 125 | IF MULTIPLE NODES IN GREY: GO TO PRODE | PE
|  | Mary | 126 | RBTNETLIB/RBNDLTNODE F4 and input DEVA (delete twice if needed) | PE
|  | Mary |  | WRKCFGSTS CFGTYPE(*CTL) CFGD(*CMN)

## Keys
| LPAR 2 | 7858711 | 42A | EPGM |  |  |  | Spreadsheet
| Abstract | sysbas | perm |  | A | Turnover | perm | ready/rename | QMGTOOLS | no keys
| Esend | sysbas | perm |  |  | MIMIX | perm
B | Robot CONSOLE | sysbas | perm | proddss-T&C from T
| Robot Alert | sysbas | perm | proddss-T&C from T
| Robot Schedule | IASP | perm | proddss-T&C from T
| Robot Network | sysbas | perm | proddss-T&C from T
| Taatools | sysbas | 90 days
| DBU11 | sysbas | perm
1
ABSTRACT | ADDLIBLE ABSTRACT
APPERM
EMM0817E869+HCL6M49UXMG0UAWMEKZDM7WQT8BGL48V3427C+4TWV4K*J*1TI+PPWMTZM6MBM1
2
ESEND | ADDLIBLE ESEND
ESPERM
6NIF26F1B3PPIZKRFVN4WF0QFJ+FD5*MFWEZ9XNT9QKPAQBR6HQ078Q83ISGB1VEE*TK*FGYCFG
3
DBU | ADDLIBLE DBU11
DBUSEC
7858201 DBU 11.0 13431F C7181B 0F2001 5103_________enter (partition 3)
4
TAATOOLS | ADDLIBLE TAATOOL
CHGTAAKEY
CHGTAAKEY KEY(547399CEB851D098B4F2FA5289B362E96AF00F747255293B5124D7265286
)
This key can only be used on this system.
Serial number - 7858201
Model - P20
Feature code - *NA
Release - V7R3M0
Expiration date - *UNLIMITED
Use it when installing the tools or with the CHGTAAKEY command.
The key information should be entered as:
Key value 54 73 99 CE B8 51 D0 98 B4 F2 FA 52 89 B3 62 E9 6A F0 0F 74
-- -- -- -- -- -- -- -- -- -- -- -- -- -- -- -- -- -- -- --
Position 1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16 17 18 19 20
Key value 72 55 29 3B 51 24 D7 26 52 86
-- -- -- -- -- -- -- -- -- --
Position 21 22 23 24 25 26 27 28 29 30
If you have the April 15, 2017 refresh (R66) or later you can use
this value for the KEY parameter on the CHGTAAKEY command.
547399CEB851D098B4F2FA5289B362E96AF00F747255293B5124D7265286

## SBS
PRODDSS/PROD |  |  | PRODDSS/HA
| Subsystem |  |  | Subsystem
| MIMIXSBS | MIMIXQGPL |  | MIMIXSBS
| QBATCH | QSYS |  | QBATCH
| QCMN | QSYS |  | QCMN | QSTRUPPGM
| QCTL | QSYS |  | QCTL | Startup program
| QHTTPSVR | QSYS |  | QHTTPSVR
| QINTER | QSYS |  | QINTER
| QSERVER | QSYS |  | QSERVER | . : STRPWRHA71
| QSNADS | QSYS |  | QSNADS | . : PRDPWRHA | this call qgpl/startup
| QSPL | QSYS |  | QSPL
| QSYSWRK | QSYS |  | QSYSWRK | qgpl/startup | OBJ/AMSCONFIG
did not come up when role swap to ha | QUSRWRK | QSYS |  | Q1ABRMNET
| Q1ABRMNET | QBRM |  | RBTSLEEPER
| RBTSLEEPER | RBTSYSLIB
did not come up when role swap to ha | TSERVER | QGPL | ******this was the only sbs that did not come up
all sbs up on the way back

## mimix
LOGON: MLENGBR2 > MIMIXIASP/MIMIX >MIMIXIASP/STRSVR HOST('10.7.1.169') PORT(50500) | DSS/T | RUN IF PORT WILL NOT START

## HostTables
PRODDSS/T
PRODDSS/C