## List of Testers
We will Role Swap from Proda/Carrollton to Prode/Temple. This role swap will start 4 am.
MISD Verification Teams
· Kyle Cushman (JDE/RODS) - JDE RODS Support
Michael/Grace/Trent
· Ken Dunham - FS Web Team
| Customer Facing: POLLING: SOURCE LINK and IVR |  |  | VSENDJDE FTP does not need to come down | will not be affected
| Olamide Adedotun |  |  | members with ORDER to srlordr
services, connections, getting data
· Andy Seely/QA
Brent Nitcher
· Chris Dixon - FS EDI Support
| (FTP feeds B2B sends orders to JDE) (srlordr file) |  |  | no longer will gocome down | will not be affected
| Michael Gracia |  |  | members with EDI to srlordr
· Lee Hendrix - Architecture Support
| Dustin Jones - Frank P. |  |  | Saturday morning at 7am these jobs will load to AJF (active job file) – list of jobs like ROBOT
At 03:30 Sunday morning the STOP will run automatically – time driven
When you get ready to START, have operations CONFIRM (like a DO on ROBOT) the Start script😊
Scheduling - Melissa Padgett
Verify Load Balance Weights
· Sivakami Natarajan (EBS - Oracle) - EBS Financials |  |  |  | Will only need to verify once on proda
| Subhash Vaishnav |  |  | Sales Orders feed to order/SO-Detail/Stats and Price History Files.
oracle directory
FTP's
End User Verification Teams – After 8:00 am
Brian Hayden – Oracle/JDE Goldengate - CDH
Michael Gray – will call Evan/Yessenia if he sees any problems
1-972-821-3398
Patricia Gray – Oracle/JDE Goldengate - CDH
Evan Flickinger/Yessenia Dominguez
| Work: 254-239-6615 | Work: 254-931-6529
Cell: 405-303-0928 Cell: 254-931-7649
Syndee Stiles – Oracle/JDE Goldengate – PDH/IDH
Tammy Fields
479-936-1266
David Leach
Trista Reitz – NO NEED TO WE GOOD
972.542.3662
Michael Taub – Oracle/JDE Goldengate – NDH/Planner
Kinley Harnish
Work: 972-364-2993

## iSeries
DATE: | 2025-03-23 |  |  | 4 | PE | PA | DSS | DEVA
Start | End |  | Steps | Activity | Sys | Sys | Sys | Sys | Notes
PC-10242 |  |  |  | CM- ISERIES-1037 | INFO | INFO | INFO | INFO
Friday
| DONE |  |  | Release ETS50203; ETS50206
| DONE |  |  | Release - #16 below - Schedule Robot Job to Run at 3:55 am> ETS95040
Sunday
0:01 | ETS50206 |  | 1 | Put Robot Job; AM0400; AM0415SUN;AM0430; AM0445; AM0500; AM0530; AM0600; AM0610; AM0615; AM0700; AM0715; AM0745; AM0800; AM0815; AM0900; AM0915; AM0930 on HOLD | PA
0:01 | ETS50206 |  | 2 | Do a 'DO' on ETS50050 | PA |  |  |  | *disable mimix audits
0:01 | ETS50206 |  | 3 | Do a 'DO' on ETS50021 ENABLED Profile SYSMGMT | PA
|  | Mary | 4 | Spot Check OUTQs and JOBQs | PA
3:30 |  | Ops | 5 | Start Teams Meeting
|  |  | 6 | Bring Down Apps Prior to Role Swap
SKIP |  |  | 7 | VSENDJDE FTP does not need to come down |  |  |  |  | Ken Dunham
3:30 | Francis/Marion |  | 8 | AUTOMATED will receive email |  |  |  |  | Keith Langley
|  | Mary | 9 | Signon to CONSOLE as SYSMGMT to PRODA/Carrollton Then go to Opt. 10 on screen. | PA |  |  |  | 10.7.1.130
3:49 | Norman |  | 10 | Change Polling box DALHQ125 server from 10.7.1.239 PRODa to 10.7.1.234 PRODe |  |  |  |  | proda/polling input orders and out going invoices
| Brent Riveria | Mary | 11 | https://olamvssprod.mclaneco.com
3:42 |  | Mary | 12 | Make DNS changes to have DBSERVER, GENESIS and SPYVIEW to point to PRODE 10.7.1.234 | PA
|  | Mary | 13 | Test ping after DNS chgs: DBSERVER, GENESIS and SPYVIEW 10.7.1.234 | PA
| ETS50203 | DONE | 14 |  | PA
| no jobs | Mary | 15 | allow all oracle jobs to COMPLETE: Release jobq QGPL/QBATCH runs and generates jobs in QGPL/ORACLEGL and release JOBQ QGPL/ORACLE | PA
| ETS95040 | Mary | 16 | Schedule Robot Job to Run at 3:55 am> ETS95040 | PA
4:00 |  | Mary | 17 | End level 3 on PRODE/Prod/Temple (Opt 3) (Wail until IPL_PRCS completes) WRKACTJOB SBS(QCTL) | PA
|  | Mary | 18 | Goldengate - STOP Manager (manually) | PA
|  | Mary | 19 | ENDSBS SBS(GOLDENGATE) OPTION(*IMMED) | PA
|  | Mary | 20 | ENDs Replication between PRODA/PROD to PRODDSS/HA |  |  |  |  | mimix support: 1-630-282-8300
4:05 |  | Mary | 21 | MIMIX/ENDMMX and Press Enter. | PA |  |  |  | if > 10 minutes
|  | Mary | 22 | MIMIX/WRKDG to monitor | PA |  |  |  | make sure all datagroups are down, end manually if needed
|  | Mary | 23 | MIMIX/WRKSYS *INACTIVE all | PA |  |  |  | subsystem just port active
|  | Mary | 24 |  | PA
|  | Mary | 25 |  | PA
|  | Mary | 26 | MIMIX/ENDMMX and Press Enter >kills all jobs except sbs and ports | PA |  |  |  | 2 ports on prode/prod and 1 port on proda/ha
|  | Mary | 27 | MIMIX/WRKDG to monitor | PA |  | DSS/T |  | make sure all datagroups are down, end manually if needed
|  | Mary | 28 | MIMIX/WRKSYS *INACTIVE all | PA |  |  |  | Subsystem Active and ports are active
|  | Mary | 29 | After ending mimix, ports should only be *active under all 4 nodes sbs | PE | DSS/T | DSS/C | PA
|  | Mary | 30 | End mimix sbs on prode/prod it should be showing two ports: ENDSBS SBS(MIMIXSBS) OPTION(*IMMED) | PA |  |  |  | only kill prode/proda
|  | Mary | 31 | End mimix sbs on proda/ha it should be showing 1 port: ENDSBS SBS(MIMIXSBS) OPTION(*IMMED) |  |  |  | PE | only kill proda/proda
|  | Mary | 32 | Kill sbs's on prode/prod and proda/ha to kill ports | PA |  |  | PE | 2 ports/source….1 port/target active
|  | Mary | 33 | ENDTCPIFC INTNETADR('10.7.1.168') | PA |  |  |  | Deactivate 10.7.1.168 -
|  | Mary | 34 | Verified it's ended> NETSTAT OPTION(*IFC) | PA
|  | Mary | 35 |  | PA
|  | Mary | 36 | STRTCPIFC INTNETADR('10.7.1.168') |  |  |  | PE | Activate 10.7.1.168 -
|  | Mary | 37 | Verified it's ended> NETSTAT OPTION(*IFC) |  |  |  | PE
|  | Mary | 38 |  |  |  |  | PE
|  | Mary | 39 | strsbs qbatch/amsconfig hold jobs in jobq qbatch/ | PA
|  | Mary | 40 | Start Role Swap from ProdA to ProdE
|  | Mary | 41 | Logoff and back on to CONSOLE as QSECOFR PRODA/COLO | PA |  |  |  | 10.7.1.180
|  | Mary | 42 | WRKCLU | PA
|  | Mary | 43 | Run QZRDPWRHA/CHKDUPLIBS IASP(PRODEIASP) | PA |  |  |  | QZRDHASM, QZRDPWRHA
|  | Mary | 44 | QSYS/WRKASPJOB | PA |  |  |  | Verify that all SUBSYSTEMS HAVE ENDED IN LEVEL 3
|  | Mary | 45 | Take Option 9 - Verify PEDEVCRG Resource Group is Active | PA
|  | Mary | 46 | Option 6 | PA
|  | Mary | 47 | Option 6 | PA
|  | Mary | 48 | Option 6 | PA
|  | Mary | 49 | Option 6 | PA
|  | Mary | 50 | Take Option 10 - Verify ASP Copy> Take Option 25 on PRODA | PA
|  | Mary | 51 |  | PA
|  | Mary | 52 |  | PA
|  | Mary | 53 | qbatch has to be active….start sbs qbatch in library amsconfig on all 4 nodes : STRSBS AMSCONFIG/QBATCH | PE | DA/C | DSS/C | PA/C | keep jobq release qbatch
4:11 | 4:17 | Mary | 54 | Take Option 9 > Take Option 3=Change primary (PEDEVCRG) | PA
|  | Mary | 55 |  | PA |  |  |  | 1:30 to varyoff
|  | Mary | 56 | qbatch | PA |  |  |  | Job ends once it has vary off the iasp
|  | Mary | 57 | Start another session to PRODA/Carrollton to monitor: ASP State will go to VARYOFF | PA |  |  |  | QSECOFR/varyon 1:00 then a dlyjob 60
|  | Mary | 58 | Signon to CONSOLE as QSECOFR on PRODE/Temple to Monitor: ASP State will go to AVAILABLE |  |  |  | PE | 10.7.1.180
|  | Mary | 59 |  |  |  |  | PE
|  | Mary | 60 | Verify Direction of Replication has been switch |  |  |  | PE
|  | Mary | 61 |  |  |  |  | PE | 10.7.1.132
|  | Mary | 62 | Verify Cluster that all 4 nodes are active | PA |  |  | PE
| SKIP | Mary | 63 | Shut down Goldengate (manually shut down mgr - levels will shut everything else) ck sbs | PA
|  |  | 64 | 3rd party software on ProdE/Temple
|  | Mary | 65 | Logon as Self to verify menu |  |  |  | PE
|  | Mary | 66 | Login as SYSMGMT |  |  |  | PE
|  | Mary | 67 | Sync System Time |  |  |  | PE
|  | Mary | 68 | WRKSYSVAL QINACTITV change from 45 to *NONE |  |  |  | PE
A |  | Mary | 69 | Verify Spyview otherwise, apply |  |  |  | PE
4:19 |  | SYSMGMT | 70 | STRSPY>F21 |  |  |  | PE
|  | SYSMGMT | 71 | CLRPFM FILE(SPYVIEW/MFKYLIC) |  |  |  | PE | SN# 7858201
|  | SYSMGMT | 72 | CLRPFM FILE(SPYVIEW/MFKYMST) |  |  |  | PE
|  | SYSMGMT | 73 | F12>Option 7> 5EFFD3876609CB894D8E73DF68C5B5B6 |  |  |  | PE | LPAR NUMBER: 001
|  | SYSMGMT | 74 | Select Products and apply Users and Demo Date |  |  |  | PE | (DOCVIEW- 7 on PE; 1 on PA
|  | SYSMGMT | 75 | START SPYVIEW PRINT DISTRIBUTION |  |  |  | PE
|  | SYSMGMT | 76 | CALL PRDETSSRC/STRDSTLIST (185) |  |  |  | PE | SYSMGMT
|  | SYSMGMT | 77 | STRMON if needed |  |  |  | PE
ADDED | ADDED | SYSMGMT | 78 | Set *PUBLIC = *USE authority for service program QPMLPMGT
B |  | Mary | 78 | KEY - Apply Turnover Key |  |  |  | PE | need to apply
|  | Mary | 79 | 'IFS KEY: /home/unicom/licenses/* TN4 |  |  |  | PE | SN# 7858201
| WAS GOOD | Mary | 80 | RENAME License to LicenseCOLO2025 then RENAME LicenseTemple2025 to License |  |  |  | PE | LPAR 001
|  | Mary | 81 | SOFTTURNE/TWRKLIC |  |  |  | PE | LPAR 001
| *sysbas | Mary | 82 | STRSBS SBSD(AMSCONFIG/TURNOVER) if not started |  |  |  | PE
|  | Mary | 83 | Turnover Menu: Take Option 11>Option 1> |  |  |  | PE
|  | Mary | 84 | 2=change > PRODE System description = change serial number 7858201 Serial number = *LOCAL and Press Enter |  |  |  | PE | Highlight Remote System
|  | Mary | 85 |  |  |  |  | PE | before RS
|  | Mary | 86 |  |  |  |  | PE | after RS
|  | Mary | 87 | Take Option 1 from Turnover Main Menu |  |  | DEVA/T
|  | Mary | 88 |  |  |  | DEVA/T
|  | Mary | 89 | level 30 |  |  | DEVA/T |  | 1=highlight 4=unhighlight
|  | Mary | 90 | level 30 |  |  | DEVA/T |  | highlight system
|  | Mary | 91 | check 11>1 deva highlight ck serial no |  |  | DEVA/T
C |  | Mary | 92 | KEY - Verify DSI Key |  |  |  | PE | Logon to Verify
|  | Mary | 93 | DLTOBJ OBJ(DCL511DTA/DSIPROTECT) OBJTYPE(*DTAARA) |  |  |  | PE | svc_dclink/key by sn#
| 4:25 | Mary | 94 | CRTDTAARA DTAARA(DCL511DTA/DSIPROTECT) TYPE(*CHAR) LEN(24) VALUE(X'C1E935EDACCF9B5D14DBE418D19A7E5CC4DDD2CC383A813A') |  |  |  | PE | NO SPACES!!!!key not needed for DSI to run. It's use for SVC_DCLINK interface 13
D |  | Mary | 95 | KEY - INIT and APPLY JDE KEYS |  |  |  | PE
|  | Mary | 96 | https://licensecodes.oracle.com/cgi-bin/keygen.pl https://www.oracle.com/support/license-codes/jd-edwards-world.html |  |  |  | PE | SAME KEY AS BEFORE BY SERIAL NO
|  | SYSMGMT | 97 | Logon as SYSMGMT |  |  |  | PE
|  | Mary | 98 | CHGDTAARA DTAARA(JDFOBJA73/QJDF (496 17)) VALUE(‘060139RPGHDB00701’) |  |  |  | PE | SAME KEY AS BEFORE/BY SN# will be same for DEVA/Prod
|  | Mary | 99 | Software Protection Code RPGHDB System 00 Install Key L123M12345NO27 |  |  |  | PE
|  | Mary | 100 | DSPDTAARA JDFOBJA73/QJDF for Verification |  |  |  | PE | DD - #CYR///50
|  | Mary | 101 |  |  |  |  | PE | Screen Shot of PRODE KEY B/4 ROLE SWAP SAMPLE
|  | Mary | 102 |  | PA |  |  |  | Screen Shot of PRODA KEY AFT ROLE SWAP SAMPLE
|  | Mary | 103 | Logon as QSECOFR |  |  |  | PE
|  | Mary | 104 | SETASPGRP ASPGRP(PRODEIASP) |  |  |  | PE
|  | Mary | 105 | Have to KEY Each on at a Time!!! |  |  |  | PE
|  | Mary | 106 | WRKOBJLCK OBJ(QGPL/JDE_IDX_1) OBJTYPE(*USRIDX) |  |  |  | PE
|  | Mary | 107 | WRKOBJLCK OBJ(QGPL/JDE_IDX_2) OBJTYPE(*USRIDX) |  |  |  | PE
|  | Mary | 108 | WRKOBJLCK OBJ(QGPL/JDE_IDX_3) OBJTYPE(*USRIDX) |  |  |  | PE
|  | Mary | 109 | WRKOBJLCK OBJ(QGPL/JDE_IDX_4) OBJTYPE(*USRIDX) |  |  |  | PE
|  | Mary | 110 | WRKOBJ OBJ(QGPL/JDE*) OBJTYPE(*USRIDX) |  |  |  | PE
|  | Mary | 111 | DELETE 1-4 ONLY! |  |  |  | PE
|  | Mary | 112 | SBMJOB CMD(CALL PGM(JDFOBJA73/J98802JQ)) JOBQ(AMSCONFIG/QCTL1) INLLIBL(QTEMP JDFOBJA73 PRDCOMA73 PRDDATA73 SECUREA73 QGPL) LOG(0 99 *SECLVL) |  |  |  | PE | CALL QCMD AND PASTE and PAST NEXT
|  | Mary | 113 | WRKOBJ OBJ(QGPL/JDE*) OBJTYPE(*USRIDX) |  |  |  | PE | Rebuilds 1-4
|  | Mary | 114 | Signoff and Log Back in as DXRECOV/yellow1 |  |  |  | PE
4:28 |  | Mary | 115 | G90>OPTION 5>F2>CALL J99LSF#> I > 00 > Press Enter> C > 00 > Apply new Install Key Matrix and Press Enter |  |  |  | PE
|  | Mary | 116 | System 00 Install Key L123M12345NO7 |  |  |  | PE | Screen Shot Prior to Role Swap
|  | Mary | 117 | Go CSEC Menu> Take Option 2 > Alpha Name.. A>Press Enter>> Option 3 for Verification>I > PAGE DOWN |  |  |  | PE
|  | Mary | 118 | G94>14>F6 to Verify Software Secuirty Code |  |  |  | PE
E |  | SYSMGMT | 119 | Robot Schedule Changes due to Different System names (completion history) |  |  |  | PE | SYSMGMT
4:36 |  | SYSMGMT | 120 | RBTSYSLIB/RSLSHUTDWN |  |  |  | PE | Bring down RBTSLEEPER Subsystem by running:
|  | SYSMGMT | 121 | RSLCHGSYSN BEFORE(PRODA) AFTER(PRODE) PRODUCT(ROBOT) |  |  |  | PE
|  | SYSMGMT | 122 | RSLSETOID PRC(RBT) |  |  |  | PE
|  | SYSMGMT | 123 | STRSBS SBSD(RBTSYSLIB/RBTSLEEPER) |  |  |  | PE
F | skip | Mary | 124 | Verify Formsprint - 15 days get screenshot to send to vendor for perm key |  |  |  | PE | KEYS IS IN ICSPROG/SYSBAS
| skip | Mary | 125 | Double Check Formsprint #3 (otherwise, do F16>3>Verify 3 CALL ICSPROG/FMSTCTLA |  |  |  | PE | CALL ICSPROG/LICENSE
|  | Mary | 126 | Verify that all subsystem are Active see Tab |  |  |  | PE
|  | Mary | 127 | Verify all tcp servers and host servers are active that should be |  |  |  | PE
|  |  | 128 | Host Table Changes
|  | SKIP | 129 | Host Tables Entries for PRODE and PRODA do not need to change due to different system names | PE |  |  | PA
|  | SKIP | 130 | Host Tables Entries for Proddsss and ProddssHA do not need to change due to different system names | DSS |  |  | DSSHA
|  | SKIP | 131 | Host Tables Entries for DEVA and DEVAHA do not need to change due to different system names | DEVA |  |  | DEVAHA
|  | Mary | 132 | Start Level 3 - and End Qinter |  |  |  | PE
|  | Mary | 133 | Run Robot job SOP93000 (release job in sbs QCTL) note: do not need to wait for job completion: |  |  |  | PE
|  | Mary | 134 | Run Robot Job: PR_90000 note: do not need to wait for job completion |  |  |  | PE
4:42 |  | Mary | 135 | RLSSBSJQ SBS(AMSCONFIG/DCSBS) |  |  |  | PE
|  | Mary | 136 | RLSSBSJQ SBS(AMSCONFIG/QBATCH) |  |  |  | PE
|  | Mary | 137 | RLSSBSJQ SBS(AMSCONFIG/ORDERPOST) |  |  |  | PE
4:43 |  | Mary | 138 | Start level 3 on PRODE/Temple (Opt 13) (Wail until IPL_PRCS completes) WRKACTJOB SBS(QCTL) |  |  |  | PE
|  | Mary | 139 | kill Qinters* CALL PRDETSOBJ/ENDQINTERS |  |  |  | PE | MLENGBR2
|  | Mary | 140 | STRHOSTSVR *ALL |  |  |  | PE
|  | Mary | 141 | STRTCPSVR *ALL |  |  |  | PE
|  | Mary | 142 | BOUNCE QSNADS |  |  |  | PE
G |  | Mary | 143 | Fastfax - Using the same Environment # and DNS |  |  |  | PE
|  | Mary | 144 | ENDTCPSVR *NETSVR | PA |  |  |  | SYSMGMT
|  | Mary | 144 | SUBSYSTEM NEEDS TO BE DOWN: FASTFAXLC/FASTFAXL |  |  |  | PE
|  | Mary | 145 | IBMi Net Server & ODBC should be ACTIVE |  |  |  | PE
|  | Mary | 146 | CHGCURLIB FASTFAXL |  |  |  | PE
|  | Mary | 147 | DSPDTAARA FASTFAXL/DTAPTF |  |  |  | PE
|  | Mary | 148 | [5 empty] | 5.0.0.003=GEN1 5.5.1.005=GEN2
4:51 |  | Mary | 149 | STRSQL |  |  |  | PE | LPAR1
|  | Mary | 150 | INSERT INTO FASTFAXL/FFXLDV (FDVPID, FDVPNB, FDVTP1, FDVTP2, FDVSEQ, FDVFNM, FDVFVL, FDVFF1, FDVFF2, FDVFF3) VALUES(0, 0, 900000001, 900000098, 1, 'I1_8201.QSP', '011ed777f8f2f0f1d0c4d8d337579715f39f0737579715131f0737509414', '', '', '') |  |  |  | PE | IBMi 7859201 partition 1
|  | Mary | 151 | UPDATE FASTFAXL/FFXLDE SET FLEASN=’WINPRODE1’ where FLEEID = 4 |  |  |  | PE | TO UPDATE THE NETSERVER NAME - Subsystem will NOT stay up if Wrong
|  | Mary | 152 | FFXTOOLS option 87 |  |  |  | PE | NetServer Name on iSeries Can you go into or FFXTOOLS option 87 & verify the NetServer name Also make sure it’s all uppercase no lower case characters & no spaces or type-o’s
|  | Mary | 153 | At a command line verify your security code by typing: FASTFAXL/FFXSECURE |  |  |  | PE
|  | Mary | 154 | STRFFX If the security code is valid you can start FastFax by typing |  |  |  | PE
|  | Mary | 155 | FastFax should go Active once the Subsystem is started to verify type WRKFAXJOB On the Outbound Message screen press F9=Status |  |  |  | PE | FastFax should go Active once the Subsystem is started to verify type WRKFAXJOB On the Outbound Message screen press F9=Status
|  | Mary | 156 | CHECK MSF OTHERWISE BOUNCE IT SBS: QSYSWRK STRMSF MSGOPT(*RESUME) NBRMSFJOB(6) |  |  |  | PA | IF NEEDED
|  | Mary | 157 | Verify PCMiler is Active SBS: QUSRWRK QZHQSSRV PCMILER | PE |  |  |  | tools ? Task scheduler
|  | Mary | 158 | Turn Over to Teams for Testing
4:57 |  | OPS | 159 | See Email Sent to Ops
|  | OPS | 160 | JDE Team
|  | Brent | 161 | Users
|  |  | 162 | Restart Apps
SKIP |  |  | 163 | VSENDJDE FTP did not come down
| Customer Facing | OPS | 164 | Polling: Source Link and IVR |  |  |  |  | Ken Dunham
| FTP B2B | OPS | 165 | FTP B2B and JDE ( sends orders from b2b to jde) |  |  |  |  | Chris Dixon
| Request Ops to CONFIRM | Mary | 166 | Verify Load Balance Weights |  |  |  |  | Lee Hendrix
| FTP ORACLE | OPS | 167 | Verfication of FTP from JDE to Oracle |  |  |  |  | Sivakami Natarajan
| STRL3 | Mary | 168 | Verify QNTC File shares are all connected otherwise run ETS90000 |  |  |  | PA | MKDIR DIR('/QNTC/WTDSTDSIAPP01') MKDIR DIR('/QNTC/vfiler-onbase01') MKDIR DIR('/QNTC/VSERVER-DATA01')
done |  | MLENGBR2 | 169 | FORMSPRT: Virtual Queue: START MANUALLY: INVOICEPDF, INVOICERPRT, FAX |  |  |  | PE
5:53 | DSI!!! | Mary | 196 | DO A 'DO' ON JOB : OPS90100 |  |  |  | PE
|  | Mary | 197 | WRKACTJOB SBS(DCL511SBS) and make sure job status are not in TIMW |  |  |  | PE
|  | Mary | 198 | note: see 2nd worksheet for DSI locations LABELED: DSI DCs |  |  |  | PE
6:02 |  | Mary | 170 | START Qinters* CALL PRDETSOBJ/STRQINTERS |  |  |  | PE
|  | JDE | 171 | Compare counts prior to starting MIMIX
|  | Mary | 172 | Run ETS50204 RUNQRY ZMARY/ROLECNTS to display counts |  |  | DSS/T
H |  | Mary | 173 | START MIMIX REPLICATION BETWEEN PRODE TO PRODDSS/T
| NOTES | Mary | 174 | LAKEVIEW/WRKPRD
| NOTES | Mary | 175 |  | PE
| NOTES | Mary | 176 |  |  |  |  | PA
|  | Mary | 177 | CALL MIMIXQGPL/MCLANEIAPA (PRODE and PRODA *sysbas) to added Asure MIMIX - MIMIXIASP to PA |  |  |  | PA | COPY ON DEVA
| NOTES | Mary | 178 | LAKEVIEW/UPDINSPRD
| NOTES | Mary | 179 | IF 2nd port does not start: MIMIXIASP/STRSVR HOST('10.7.1.168') PORT(50500)
| NOTES | Mary | 180 | MIMIXIASP/MIMIX>>>> MIMIX/WRKSYS>>>>>MIMIX/STRMMX
DSSIASP | SKIP NOT SWAPPING | Mary | 181 | STRSQL verify relational database if PRODDSS do NEXT TWO STEPS |  |  | DSS/T
DSSIASP | SKIP NOT SWAPPING | Mary | 182 | WRKRD* delete MX_MIMIXIASP_IABA 10.7.1.169 | PE
DSSIASP | SKIP NOT SWAPPING | Mary | 183 | ADDRDBDIRE RDB(DSSIASP MX_MIMIXIASP_IABA) RMTLOCNAME('10.7.1.169' *IP) | PE |  |  |  | dssiasp/prode&proddss;proddss/proda&proddssha
|  | Mary | 184 | STARTs Replication between PRODE to PRODDSS
|  | Mary | 185 | STRSBS MIMIXQGPL/MIMIXSBS start subsystem | PE | DSS/T | DSS/C | PA | make sure 2 ports are active proda and 1 on prode
|  | Mary | 186 | MIMIX/WRKSYS Option 9 |  |  |  | PE
6:08 |  | Mary | 187 | MIMIX/STRMMX - to start datagroups/replication |  |  |  | PE
|  | Mary | 188 |  |  |  |  | PE
|  | JDE | 189 | Check File counts once MIMIX has been Started to make sure they are changing |  |  | DSS/T
|  | Mary | 190 | Run ETS50205 RUNQRY ZMARY/ROLECNTSPA to display before counts |  |  | DSS/T
|  |  | 191 | MISC
|  | Mary | 192 | IF job time is < (less than) 'Current Time' AM0400; AM0415SUN; AM0430; AM0445; AM0500; AM0530; AM0600; AM0610; AM0700; AM0800; AM0900; then do the following: R=Release and 'DO' on jobs ONE At A Time; (If you have any questions, CALL SYSTEM i ON-CALL PERSON.**) |  |  |  | PE
|  | Mary | 193 | IF job time is > (greater than) 'Current Time' AM0400; AM0430; AM0445; AM0500; AM0530; AM0600; AM0610; AM0700; AM0800; AM0900; than do the following: R=Release ONE At A Time; (If you have any questions, CALL iSERIES ON-CALL PERSON.**) |  |  |  | PE
|  | Mary | 194 | If job GL_19020, GL_35000, AR_10000, FED15220 or VTS38001 Ended Abnormal due to outage ONLY, Robot Job Has A 'T' Status **** Do a 'DO' to run job |  |  |  | PE
|  | Mary | 195 | PR_11601 job runs at 8:00 am, PR_11605 job runs at 7:00 am, PR_11610 job runs at 6:00 am, and PR_11699 runs at 5:05 am. Should be on the list of missed jobs. Do a 'DO' when system comes back up. |  |  |  | PE
|  | Mary | 199 | Verify that all subsystem are Active |  |  |  | PE
|  | Mary | 200 | Verify all tcp servers are active that should be |  |  |  | PE
|  | Mary | 201 | Robot Schedule: display missed jobs time frame: 0400 to 0800 date: 03/23/25 |  |  |  | PE
|  | Mary | 202 | Run ETS50020 for 'T'erminated Jobs |  |  |  | PE
|  | Mary | 203 | Start iSeries Robot GUI Monitors after iSeries has given the ok. |  |  |  | PE
|  | Mary | 204 | Do a 'DO' on ETS51000 to start stats to Splunk |  |  |  | PE
|  | Mary | 205 | Do a 'DO' on ETS50001 Disable APPADMIN & SYSMGMT |  |  |  | PE
|  | Mary | 206 | WRKJOBSCDE RLS VTLD0395 |  |  |  | PE
|  | Mary | 207 | WRKJOBSCDE HOLD VTLD0395 |  |  |  | PE
|  | Mary | 208 | DO' on Robot job ETS40080 to Reset Robot Host Node for GUI monitor |  | DSS/T | DEVA/T | PE
|  | Mary | 209 | SETUP ROBOT NETWORK GUI / bounce on all systems |  | DSS/T | DEVA/T | PE
|  | Mary | 210 | MISC BACKUPS |  |  |  | PE
DONE |  | Mary | 211 | Modify MEDPCY ETSCLNJRNV from: HTAPED090 to VTAPED090/deactivate/line60 and activate/line50 |  |  |  | PE
DONE |  | Mary | 212 | Modify MEDPCY FIN14600 from: HTAPED090 to VTAPED090 |  |  |  | PE
DONE |  | Mary | 213 | HOLD ETS50203 AND ETS50206 |  |  |  | PE
DONE | 6:24 | Mary | 214 | WRKSYSVAL QINACTITV change from *NONE to 45 |  |  |  | PE
| SKIP | Mary | 215 | CPA
|  | Mary | 216 | CPA: it exist on the sysbase side |  |  |  | PE
|  | Mary | 217 | CPA/OPTION 1> OPTION 7 - CPADAILY - 9:00 am; CPAWEEKLY-Monday 9:00 am |  |  |  | PE
|  | Mary | 218 | Verify |  |  |  | PE
|  | Mary | 219 |  |  |  |  | PE
|  | Mary | 220 | to: |  |  |  | PA
|  | Mary | 221 |  |  |  |  | PE
|  |  | 179 | ROBOT GUI - NETWORK
|  | Mary | 180 | RBTNETNODE/RBNENDNODE | PE
|  | Mary | 181 | RSLWL | PE |  |  |  | IFS
|  | Mary | 182 | ROBOT NETWORK>nodeConfig.xml >>>search on PrimaryHost Shift/F4 | PE
|  | Mary | 183 | RBTNETNODE/RBNCFGNODE HOSTIP('10.7.1.239') AHOSTIP(*NONE) | PE
|  | Mary | 184 | RBTNETNODE/RBNSTRNODE | PE
|  | Mary | 185 | IF MULTIPLE NODES IN GREY: GO TO PRODE | PE
|  | Mary | 186 | RBTNETLIB/RBNDLTNODE F4 and input DEVA | PE
|  | Mary | 187 | Follow the Above then go to GUI and setup new host> proda | PE
|  |  | 170 | GOLDENGATE VERIFICATION
SKIP | STRL3 | Mary | 171 | GOLDENGATE>OOGUSER>ETS95000 to start mgr
SKIP | STRL3 | Mary | 172 | strsbs goldengate
SKIP | SKIP | Mary | 173 | ADDLNK OBJ('/DAHAIASP/GoldenGate') NEWLNK('/GoldenGate') LNKTYPE(*SYMBOLIC)
SKIP | STRL3 | Mary | 174 | Do a 'DO' on Robot job ETS95000
SKIP | STRL3 | Mary | 175 | Logon with OOGUSER
SKIP | STRL3 | Mary | 176 | leon side 'distribution service' - OGG job
SKIP | STRL3 | Mary | 177 | START REPLICAT's
SKIP | STRL3 | Mary | 178 | START PUMP/EXTRACT
| SKIP | Mary | 188 | CK: PRDETSDTA/CURSYS *DTAARA | PE |  | PE/T
| SKIP | Mary | 189 | run ETSCURSYS (runs on sat's) if needed | PE |  | PE/T
ISSUES
NETSVR would not stay active for ff
|  |  |  | Monday |  |  |  |  | ROBOT JOBS/SCRIPTS/DATAAREA HAVE TO CHANGE FROM DIST004 TO DIST004P2
|  | Grace/Mary | 1 | Name Description Time M T W TH F
SOP11400 RS-Upd RBTROB SFTP JOB 08:00 14:30 C C C C C
|  |  | 2 | Test Turnover form
Review Globals
|  |  | 3 | DIST004 RSCS SFTP Connection from JDE - PRODE
DIST004P2 RSCS SFTP Connection from JDE - PRODA
| could view on both lpars |  |  | /tmp/RSCS
not equal
|  | PRODE |  | home/DIST004
|  | PRODA |  | home/DIST004P2
PRODE
PRODA
| KEYS |  |  | /home/dist004/.ssh/known_hosts
Logon with DIST004/mcl1320$p
| Test Connection |  |  | Logon with DISTOO4P2/mcl1320$P2
call qp2term
sftp dist004p2@rscs.hostedftp.ocm
cd /Dist004p2/GPSEcomm
ls
info extract cext
fix
alter extract cext, SEQNO 996369538 journal PRDJRNLIB/JDEJD7JRN JRNRCV PRDJRNLIB/JD7JDE7821
alter extract iext, SEQNO 996369538 journal PRDJRNLIB/JDEJD7JRN JRNRCV PRDJRNLIB/JD7JDE7821
alter extract next, SEQNO 996369538 journal PRDJRNLIB/JDEJD7JRN JRNRCV PRDJRNLIB/JD7JDE7821
alter extract pext, SEQNO 996369538 journal PRDJRNLIB/JDEJD7JRN JRNRCV PRDJRNLIB/JD7JDE7821
> info extract next
EXTRACT NEXT Last Started 2025-03-16 06:12 Status ABENDED
Checkpoint Lag 00:00:00 (updated 00:55:34 ago)
VAM Read Checkpoint 2025-03-16 03:47:41.372576
Journal Receiver Timestamp (UTC) Sequence Number
PRDJRNLIB/JDEJD7JRN ¦ PRDJRNLIB/JD7JDE7821¦Mar 16 2025 08:47:41.372576¦00000000000996369537
ERROR
PRDJRNLIB/JDEJD7JRN ¦ PRDJRNLIB/JD7JDE7821¦Mar 16 2025 08:47:41.372576¦00000000000996369537.
Positioning sequence ID is out of order, old sequence ID is 00000000000996369537, new sequence ID is 00000000000000050059.
WRKCFGSTS CFGTYPE(*CTL) CFGD(*CMN)
2025-03-23
Journal Receiver Timestamp (UTC) Sequenc
JRNLIB/JDEJD7JRN ¦ PRDJRNLIB/JD7JDE7899¦Mar 23 2025 08:47:37.854912¦000000000000
ce Number
62271050
sequence ID is out of order, old sequence ID is 00000000000062271050, new sequennce ID is 00000000000000018119.
alter extract cext, SEQNO 62271051 journal PRDJRNLIB/JDEJD7JRN JRNRCV PRDJRNLIB/JD7JDE7899
alter extract iext, SEQNO 62271051 journal PRDJRNLIB/JDEJD7JRN JRNRCV PRDJRNLIB/JD7JDE7899
alter extract next, SEQNO 62271051 journal PRDJRNLIB/JDEJD7JRN JRNRCV PRDJRNLIB/JD7JDE7899
alter extract pext, SEQNO 62271051 journal PRDJRNLIB/JDEJD7JRN JRNRCV PRDJRNLIB/JD7JDE7899
5:09

## Apply Keys
| LPAR 1 | 7858711 | 42A | EPGM |  |  |  | Spreadsheet
1 | Abstract | sysbas | not on pe |  | A | Spyview |  | ready | Vertex | no keys
2 | Esend | sysbas | not on pe |  | B | Turnover | perm | ready/rename | PcMiler | no keys
E | Robot CONSOLE | sysbas | perm |  | C | DSI | 90 days | ready | QMGTOOLS | no keys
E | Robot Alert | sysbas | perm |  | D | JDE |  | ready | RDI | no keys
E | Robot Schedule | IASP | perm |  | G | Fastfax | perm |  | MQ FTE | no keys
E | Robot Network | sysbas | perm |  | H | MIMIX | sysbas | perm
4 | Taatools | sysbas | 90 days
3 | DBU11 | sysbas | perm
F | FormsPrint | sysbas | 90 days sent email to vendor/Lou
3
DBU | ADDLIBLE DBU11
DBUSEC
7858201 DBU 11.0 C68A79 344711 C39C01 5101_________enter (partition 1)
4
TAATOOLS | ADDLIBLE TAATOOL
CHGTAAKEY
CHGTAAKEY KEY(547399CEB851D098B4F2FA5289B362E96AF00F747255293B5124D7265286)
This key can only be used on this system.
Serial number - 7858201
Model - P20
Feature code - *NA
Release - V7R3M0
Expiration date - *UNLIMITED
Use it when installing the tools or with the CHGTAAKEY command.
The key information should be entered as:
Key value 54 73 99 CE B8 51 D0 98 B4 F2 FA 52 89 B3 62 E9 6A F0 0F 74
-- -- -- -- -- -- -- -- -- -- -- -- -- -- -- -- -- -- -- --
Position 1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16 17 18 19 20
Key value 72 55 29 3B 51 24 D7 26 52 86
-- -- -- -- -- -- -- -- -- --
Position 21 22 23 24 25 26 27 28 29 30
If you have the April 15, 2017 refresh (R66) or later you can use
this value for the KEY parameter on the CHGTAAKEY command.
547399CEB851D098B4F2FA5289B362E96AF00F747255293B5124D7265286
F
Formsprint | ADDLIBLE ICSPROG
CALL ICSPROG/LICENSE
5=Temporary 15 day access
6 | Robot CONSOLE
3V+FDD758E066693597A75KL+HY5IM*H5ZI55CEBVRBLQ0I74JV6120CX3ZXW5JX2UYXKSYUJUX
7 | Robot Alert
VWH9844B3DLFHY6+N3Q1TNPK2PKNP2Z8NVXZN0VX1D+Q3R71FE*6D1RH06+TXCAT4MPTMI+BN8T
8 | Robot Schedule
BGH0F89E1CY*3YPADK3JLD1V7I2D3XSIDP0UDVZ58UGE7WF6Y43CTHW1S6YJW1P+HF9JV1*J4PJ
9 | Robot Network Host
D1+369BF95*GE61K09K350M0*4U0+IME0BL30Z7H4VDG20IUK7VL8Q03H*ZX3FPX21JUKSHZTUX
10 | Robot Network Node
G9HB9DD2ABXRC3G6437*24CV+UW4FRYD4FU44I0ANTBW03QHNTMWHH361EY60KL6JL*JHB*KT16
11 | CPA
QBU6B81B99S1MUAB8VRKU8QC3QT896F08IRQ8EQM9IY7W5SFA*RD2P5XUJC4YE+4M0343845NY4

## SBS
Subsystem |  |  |  |  | Subsystem
BACKGROUND | AMSCONFIG |  |  |  | BACKGROUND
BATCHWW | AMSCONFIG |  |  |  | BATCHWW
DCL511SBS | DCL511DTAC |  |  |  | DCL511SBS
DCSBS | AMSCONFIG |  |  |  | DCSBS
FASTFAXL | FASTFAXLC |  |  |  | FASTFAXL
FASTPATH | AMSCONFIG |  |  |  | FASTPATH
FINANCE | AMSCONFIG |  |  |  | FINANCE
ICSFMST | ICSSYSC |  |  |  | ICSFMST
MIMIXSBS | MIMIXQGPL |  |  |  | MIMIXSBS
ORDERPOST | AMSCONFIG |  |  |  | ORDERPOST
PROCURE | AMSCONFIG |  |  |  | PROCURE
QBATCH | AMSCONFIG |  |  |  | QBATCH
QCMN | AMSCONFIG |  |  |  | QCMN
QCTL | AMSCONFIG |  |  |  | QCTL
QHTTPSVR | QHTTPSVR |  |  |  | QHTTPSVR
QINTER0001 | AMSCONFIG |  |  |  | QSERVER
QINTER0002 | AMSCONFIG |  |  |  | QSNADS
QINTER0003 | AMSCONFIG |  |  |  | QSPL
QINTER0101 | AMSCONFIG |  |  |  | QSYSWRK
QINTER0102 | AMSCONFIG |  |  |  | QUSRWRK
QINTER0103 | AMSCONFIG |  |  |  | Q1ABRMNET
QINTER0201 | AMSCONFIG |  |  |  | RBTSLEEPER
QINTER0202 | AMSCONFIG |  |  |  | SPYCS
QINTER0203 | AMSCONFIG |  |  |  | SPYGLASS
QINTER0301 | AMSCONFIG |  |  |  | TURNOVER
QINTER0302 | AMSCONFIG |  |  |  | WWBATCH
QINTER0303 | AMSCONFIG
QINTER0401 | AMSCONFIG
QINTER0402 | AMSCONFIG
QINTER0403 | AMSCONFIG
QINTER0501 | AMSCONFIG
QINTER0502 | AMSCONFIG
QINTER0503 | AMSCONFIG
QINTER0601 | AMSCONFIG
QINTER0602 | AMSCONFIG
QINTER0603 | AMSCONFIG
QINTER0701 | AMSCONFIG
QINTER0702 | AMSCONFIG
QINTER0703 | AMSCONFIG
QINTER0801 | AMSCONFIG
QINTER0802 | AMSCONFIG
QINTER0803 | AMSCONFIG
QINTER0901 | AMSCONFIG
QINTER0902 | AMSCONFIG
QINTER0903 | AMSCONFIG
QMFT | QMQMMFT
QMQM | QMQM
QSERVER | QSYS
QSNADS | QSYS
QSPL | QSYS
QSYSWRK | QSYS
QUSRWRK | QSYS
Q1ABRMNET | QBRM
RBTSLEEPER | RBTSYSLIB
SPYCS | AMSCONFIG
SPYGLASS | AMSCONFIG
TURNOVER | AMSCONFIG
WWBATCH | AMSCONFIG
| SKIP | #REF! | Check/ifs:ICSPRFWORK (/SOP/PDF/INF) | PE

## hosttable chg
10.7.1.231 | DEVA
DEVA.APPN.SNA.IBM.COM
WWDEVA.APPN.SNA.IBM.COM
MXLDEV
addtcphte intnetadr('10.7.1.161') hostname((deva) (deva.appn.sna.ibm.com) (wwdeva.appn.sna.ibm.com) (mxldev) (vdeva) (xmxldeva)) | VDEVA
XMXLDEVA
ADDTCPHTE INTNETADR('10.7.1.231') HOSTNAME(BRMSDEVA)
|  | 10.7.1.230 | BRMSDSS
RMVTCPHTE INTNETADR('10.7.1.231') | DEVA | 10.7.1.161 | BRMSDEVA
RMVTCPHTE INTNETADR('10.7.1.230') | DSS
10.7.1.161 BRMSDEVA