## Tasks
Role Swap WIHA to WI
DONE | TIME | SYSTEM | DAYS BEFORE ROLE SWAP
x |  |  | Create CM ticket and get approvals
x |  |  | Schedule a Teams meeting. 11am-1:30pm ET
x |  | (pgm UT0750C) | Verify IBM keys are in hand for both Temple and CoLo
x |  |  | Get third-party software keys. See both Temple and CoLo tabs at bottom for what is needed.
x |  |  | Put Lansa key into directory '/LANSA_lansapgm/license' via ACS
x |  |  | Have Ricky acquire keys for Staylinked for both Temple and CoLo
DONE | TIME | SYSTEM | DAY OF ROLE SWAP
na |  | FCCTRL | Will flashcopy backup possibly be running close to role swap time? If so: WRKCSEDTA. Option 2-Change beside WIFCDR. Page down 4 times. Change UT0548C to UT0548C_ND. This will skip the 1-hour delay of the backup to ensure it finishes before role swap starts.
x |  | HMC GUI | Set WI to B Normal
x |  | HMC GUI | Set WIFC to B Normal
x |  | FCCTRL | ADDLIBLE QZRDHASM. WRKCSE.
x |  | FCCTRL | Option 5-Display beside WI. Review switch environment.
x |  | FCCTRL | WRKCSEDTA
x |  | FCCTRL | Option 5-Display beside WI. Review switch environment.
x |  | FCCTRL | Option 8-Check beside WI. Runs CHKCSE to verify ready for swap.
DONE | TIME | SYSTEM | ROLE SWAP
x | 12:23 | HMC DSP01 | Login as hscroot/abc12345
x |  | DSP01 | Select 1=Carrollton. 2=Connect shared beside WIHA. Session key=console1/console1.
x |  | DSP01 | Log on console
x |  |  | WA SBS(QCTL QINTER QBATCH QRF). When users are gone and no jobs running, then begin swap.
x |  |  | Email teams that role swap is beginning shortly
x |  |  | Open Teams meeting
x |  | DSP01 | CHGDTAARA DTAARA(UTIL/SYSAVAIL) VALUE('N') Prevent user log-on
x |  | DSP01 | End most jobs/subsystems gracefully. CALL UT0590C
x |  | FCCTRL | ADDLIBLE QZRDHASM. WRKCSE.
x |  | FCCTRL | Option 12-Work with beside WI
x |  | FCCTRL | Option 5-SWITCH. TYPE(*SCHEDULED) TYPE(*GMIR) AUTO REPLICATION(*NO)
x |  | DSP01 | Give G to 'switch' message in Qsysopr
x | ~5-11m | FCCTRL | Power down begins. SRC's appear. Shows D9002740 for a while. Waits on next freeze time on FS7200.
x |  | FS7200 | Login as superuser/Passw0rd. On left, click Copy Services, then Remote Copy. Will show "Idling" soon.
x |  | DSP01 | Disconnect (red X in upper left corner)
x |  | HMC- DSP01 | Connect (computer in upper left corner)
x |  | DSP01 | Login as hscroot/abc12345
x |  | DSP01 | Select 2=Temple
x |  | DSP01 | 2=Connect shared beside WI. Session key=console1/console1. Shows waiting to connect.
x | ~25m | FCCTRL | System IPL's. SRC's appear. Shows C600450A (6-7m). Shows C60041AE (8-11m).
x |  | FCCTRL | Shows 'SWCSE completed successfully' when finished, as well as Sign-on screen on DSP01
x |  | DSP01 | Log on console
x |  | DSP01 | WA SBS(QCTL). Startup pgm should be running
x |  | DSP01 | 5 beside QSTRUPJD. Option 10 (joblog). Verify it shows *PS.
x |  | Mocha | Mocha to WI
x |  | Mocha | DSPSYSVAL QTIME. If way off (> 20 minutes), CHGSYSVAL QTIME 'hhmm00'
x |  | Mocha | If time changed above, WRKJOB QTOTNTP. If not active, STRTCPSVR *NTP.
x |  | Mocha | CALL UT0750C to install IBM keys
x |  | Mocha | CALL QSFWINV, F11 to verify keys
x |  | Mocha | Install third-party keys. See tab below
x |  | DSP01 | Startup pgm finished
x |  | Mocha | WRKJOB RSFSRVTCP_. If not active, the startup job attempted to start it before the license key was entered. Start it: RSF/STRRSFSRV SDLC(*NO) PPP(*NO) TCPIP(*YES)
x |  | Mocha | Application testing begins
x |  | Mocha | Test Passthru to/from MBM and DVL. SP MBM. SP DVL. On MBM, SP WI. On DVL, SP WI. Use SO to end.
x |  | Mocha | WRKCFGSTS *CTL *APPC. DC's, EOEAST, and MBM controllers should be varied on.
x |  | Mocha | Test Datamirror: WI to MBM (PO26); MBM to WI (AR01); WI to EO (IN30 or DP01); EO to WI (DP21 or EO97 or OM90)
x | D3* | Mocha | Initialize 16 tapes if on HA side. WRKMEDBRM TYPE(*EXP) VOL(D20*). Option 10. Parms are: DEV(TAPMLB03) CHECK(*NO) ENDOPT(*UNLOAD)
na |  | Mocha | Change the 16 tapes (option 2-Change) to MEDCLS(ULT4FS600)
x |  | FCCTRL | WRKCSEDTA
x |  | FCCTRL | Option 5-Display beside WIFC. Review flash environment.
x |  | FCCTRL | Option 8-Check beside WIFC. Runs CHKFSFLASH to verify flash environment.
x |  | Mocha | Application testing ends
x |  | FCCTRL | WRKCSE
x |  | FCCTRL | Option 12-Work with beside WI
x |  | FCCTRL | Option 6-Start Replication After Switch. Source Lpar=WI. Target Lpar=WIHA. (Look at far left and far right columns. Ignore middle.) F8-Reverse if needed to set these. F10 to Continue.
x | ~2-5m | FS7200 | On Remote Copy screen, click clipboard-looking icon near the alarm bell to view replication completion %. Once caught up, these disappear.
x |  | FS7200 | On left, click Copy Services, then Remote Copy. WI shows Consistent Copying.
x |  | Mocha | CHGDTAARA DTAARA(UTIL/SYSAVAIL) VALUE('Y') Allow user log-on
x |  | Mocha | CHGDTAARA DTAARA(UTIL/FLASHWHERE *ALL) VALUE(WIFC)
x |  |  | Email management, iseries team, App team, DC users, and Ops that swap has completed
x |  |  | Email Ops to remind them where the console is for running daycloses (Temple. WI lpar)
na | 1:05 | FCCTRL | Was flashcopy backup changed to prevent running close to role swap time? If so: WRKCSEDTA. Option 2-Change beside WIFCDR. Page down 4 times. Change UT0548C_ND to UT0548C. This will add back the 1-hour delay to the backup.
12:23 - 1:05

## Temple keys
Expires | Temple Keys
Perm | RSF: RSF/CHGRSFAUT AGREE(*YES) AUTH(1B6CC2C0) | received | same key all lpars
Perm | ZMOD: ADDLIBLE ZMODLIB10; SETZMLIC. nuBridges FTP Client. . . . . 9999 AAD6/xWQ+osF nuBridges FTP Server. . . . .. 9999 9999 JxP5/+n55hUG nuBridges Zip utility . . . . . . . 9999 AADx//LM9vgO | received | same key all lpars
Perm | RXS: ADDLIBLE RXS; APYLIC LICKEY(7037D64IC31841F5C99C639FA44A4736) PRODUCT(RXS) | received | WI
Perm | Lansa: Log on as QSECOFR LANSA LICENSE Should show Status as Valid F3 to exit | already in IFS | WI
Perm | Staylinked: Open Staylinked Administrator on pc. Double-click the DC. Log-on with administrator and esp. Click Server Configuration. Click Server Licenses. Right-click on License. Click Remove. Right-click. Click Add. Enter # of Perm Clients and license key. IC2RO0C5SG80BMB4FDTZ6ID 6 license. Click Validate. Click Install keys. You will be logged you out. Double-click the DC. Log-on with administrator and esp. Click Server Configuration. Click on Server License to see new code. | received | WI

## CoLo keys
Expires | CoLo Keys
Perm | RSF: RSF/CHGRSFAUT AGREE(*YES) AUTH(D4E0CCEF) | received | same key all lpars
Perm | ZMOD: ADDLIBLE ZMODLIB10; SETZMLIC. nuBridges FTP Client. . . . . 9999 AAD6/7eensUF nuBridges FTP Server. . . . .. 9999 9999 JxP5/0v3glsG nuBridges Zip utility . . . . . . . 9999 AADx/1DCkrYO | received | same key all lpars
Perm | RXS: ADDLIBLE RXS; APYLIC LICKEY(0980672G505225F32EE278BFC22C2087) PRODUCT(RXS) | received | WI
Perm | Lansa: Log on as QSECOFR LANSA LICENSE F6=Create Paste key name: /LANSA_lansapgm/license/x_lic_22G_78C2E20_67_0000339662.xml then Enter Should show Status as Valid F6 to Apply | received | WI
1/8/25 | Staylinked: Open Staylinked Administrator on pc. Double-click the DC. Log-on with administrator and esp. Click Server Configuration. Click Server Licenses. Right-click on License. Click Remove. Right-click. Click Add. Enter # of Temp Clients and license key. AGXCG803EZNZV3VTPOCCU8O 6 license. Click Validate. Click Install keys. You will be logged you out. Double-click the DC. Log-on with administrator and esp. Click Server Configuration. Click on Server License to see new code. | received | WI