## Plan DST2DSC
Task | Assignee | Assigned Date | date | time | Completed Date | Comments | Column1
Pre-Failover
Confirm with Scheduling that there are no issues if we don't get things running until 5am vs 4am | Michael |  |  |  |  | No concerns recently for going past 4. DSMQTRG will run when it runs.
Review "issues and improvement" from 2023
Confirm everyone has a console. JESB uses option B) TSO EMER uses option F) TSO3 Michael - COLO - F600 on all LPARs for Colo Ops won't use them this go around Michael - TEMPLE - F600 on EMER, F601 on JESA/B/C Michael - COLO and TEMPLE - F610 Denise - COLO and TEMPLE - F612 Matt - COLO and TEMPLE - F611 | everyone |  | 2025-10-25 | 23:40 | ml | Denise validated COLO EMER F612 and need to validate credentials Denise validated Temple EMER F612 and credeitals Denise Validated COLO and TEMPLE JESB F612
Confirm DLM health check doing Pre Site Swap -- See Doc | Michael |  | 2025-10-25 | 23:58 | ml | DLm and DataDomain Siteswap procedures pre-check (Business as Usual).docx
Notification to Vendors for Standby Support
Dell (PowerMax, DLm, DataDomain) (notifed Jason Smith and Brad Lake, opened SRs on Pmax and DLM) | Michael |  | 2025-10-24 | 15:00 | ml | Sent email to Marco, Kate, Brad Lake, and Jason Smith. Opened SRs and tuned Stuart and Norman to them
IBM (Matt Cousens) / Mainline (Allen and Alan) | Michael |  | 2025-10-24 | 15:00 | ml | Sent emails to Mainline (Allen and Alan) and IBM (Matt Cousens)
Other
Validate with Cust Facing and ECOMM MQ Jobs haven't changed before outage | Michael |  |  |  |  | Emailed Leonard Hollas, Tom Clark, and Jackilyn Parker | no change since last time -- Will follow this step on 2026 role swap
Confirm any new libraries that were dynamically added to APF/LNKLST have been added to PROG30 | Denise |  | 2025-10-24 |  | ml | 9.APF compared to SYS1.JES2.Z25.PARMLIB(PROG00,PROG30) | No need to repeat - no changes have been made.
Confirm any new OMVS mounts have been added to the BPXPARM member | Matt |  | 2025-10-24 |  | ml | 9.FS compared to SYS1.JES2.Z25.PARMLIB(BPXPRMFP) match | No need to repeat - no changes have been made.
Confirm any new libraries that were dynamically added to LPA have been added to LPALST30 | Larry |  | 2025-10-24 |  | ml | 9.LPA compare | No need to repeat - no changes have been made.
If any policy changes need to be implemented CFRM job to get those applied to the data sets (PCOUPLE & ACOUPLE) -- SYS3.SMP.SYSPLEX.JES2(POLCFRDR) | Michael |  | 2025-10-24 |  | ml | No changes since 08/24 | No need to repeat - no changes have been made.
Verify Colo z16 HMC configs (due to any pre-site swap validation activities) Make sure we aren't set to 1 CPU on LPARs, etc… https://10.49.35.103/preloginmonitor/index.jsp | Michael |  | 2025-10-25 | 21:00 | ml | Under Operational Customizations --> Customize/Delete Activation Profiles Updated XCFB00 from not-dedicated CP to non-dedicated ICF Updated JESA to CP 4,1 and ZIIP 0,1 initial weight 140 Updated JESB to CP 3,1 and ZIIP 0,1 initial weight 120 Updated JESC to CP 2,0 and ZIIP 0,1 initial weight 18 Updated LPAR and LPAR Group weights to match Temple
Confirm time set on COLO HMC and validate SYS1.JES2.PARMLIB(CLOCK02) member set correctly HMC: Home --> Task Index --> Manage System Time make sure we are current time and UTC -6, with 1 hour DST (- 5 hours from UTC) CLOCK02 - W.05.00.00 (-5 hours from UTC) | Denise |  |  | 23:40 | dvm | Time in corner reflects 8:31, we are good IEASYSD2/3 (Disaster), IEASYSF2/3 (Failover), and IEASYS16 (Temple) all use CLOCK02. CLOCK02 set to 5 hours, which is correct compared to UTC right now
Unisphere - Validate Page / Temp volumes in both arrays are in "Ready" status and RDF group is in Adaptive Copy and Failed Over State under Data Protection Temple - 3329 - MF_JES2P_DST_SG COLO - 3328 - MF_JES2P_DSC_SG | Michael |  | 2025-10-25 | 23:47 | ml
Confirm EMER LPAR down in Temple OR only EMER volumes are online TSO DSP VOL should only give this when gearing up to move VOLUME UNIT DEVICE SERIAL ADDR TYPE S24EMR 3003 3390 S23EMR 3004 3390 S23EM1 3006 3390 SYS999 3007 3390 S24EM1 3008 3390 | Michael |  | 2025-10-25 | 23:23 | ml | EMER was already up, no harm in leaving it up.
Shut down MVS3 LPARs and Deactivate those LPARs and the corresponding CF LPARs **Offload JES2 Checkpoint** -- See notes, DO NOT SHUTDOWN JES2 Subsystem on MV3B until offload is complete, see instructions below *** Shutdown MV3A Shutdown MV3C Before issuing $pjes2 on MV3B do the below commands. Once offloaded, issue $PJES2 and complete doc | Michael |  | 2025-10-25 | 21:21 | ml | Notify QA & Scheduling JES2 Checkpoint offload occurs to point both Checkpoints to DASD instead of the CKPT1 living in the coupling facility. The coupling facility gets shutdown and the data is lost. This allows us to retain info between sites
JES2 Checkpoint Procedures: $D CKPTDEF CKPT1=(STRNAME=JES2_MVS3,INUSE=YES,VOLATILE=YES) CKPT2=(DSNAME=SYS1.HASPCKP2,VOLSER=SYS3M1,INUSE=YES,VOLATILE=NO) NEWCKPT1=(DSNAME=,VOLSER=) MODE=DUPLEX,DUPLEX=ON $T CKPTDEF,NEWCKPT1=(DSN=SYS1.HASPCKPT,VOL=SYS3M0) $D CKPTDEF CKPT1=(STRNAME=JES2_MVS3,INUSE=YES,VOLATILE=YES) CKPT2=(DSNAME=SYS1.HASPCKPT,VOLSER=SYSM02,INUSE=YES,VOLATILE=NO) NEWCKPT1=(DSNAME=SYS1.HASPCKPT,VOLSER=SYS3M0) MODE=DUPLEX,DUPLEX=ON | Michael
$TCKPTDEF,RECONFIG=YES *$HASP285 JES2 CHECKPOINT RECONFIGURATION STARTED *$HASP271 CHECKPOINT RECONFIGURATION OPTIONS Response: 1 (FORWARD CKPT1 TO NEWCKPT1) *$HASP273 JES2 CKPT1 DATA SET WILL BE ASSIGNED TO NEWCKPT1 Response: CONT $HASP280 JES2 CKPT1 DATA SET (SYS1.HASPCKPT ON SYS3M0) IS NOW IN USE *24 $HASP294 WAITING FOR RESERVE (VOL SYS3M0). REPLY 'CANCEL' TO END WAIT IEE400I THESE MESSAGES CANCELLED - 24. *$HASP256 FUTURE AUTOMATIC FORWARDING OF CKPT1 IS SUSPENDED UNTIL 306 NEWCKPT1 IS RESPECIFIED. ISSUE $T CKPTDEF,NEWCKPT1=(...) TO RESPECIFY $HASP255 JES2 CHECKPOINT RECONFIGURATION COMPLETE $D CKPTDEF CKPT1=(DSNAME=SYS1.HASPCKPT,VOLSER=SYS3M0,INUSE=YES,VOLATILE=NO), CKPT2=(DSNAME=SYS1.HASPCKPT,VOLSER=SYS3M1,INUSE=YES,VOLATILE=NO), NEWCKPT1=(DSNAME=,VOLSER=), MODE=DUPLEX,DUPLEX=ON | Michael |  | 2025-10-25 | 21:22 | ml
Failover to CoLo
Shutdown Temple Mainframe | [5 empty] | Confirm with Operations-no division requests
Backup Compuware datasets for restore after DST to DSC if needed SYS2.CMPW.LICENSE SYS2.CMPW.LICENSE.CHKPT |  |  | 2025-10-25 | 9:29 | dvm | Note backup dataset name for restore purposes | MT.PERM.CMPW.BKPUP.DR2025
Confirm "sender" channels between PTDCMQ01 and MQPA have been stopped (see email FROM ctm) | Michael |  | 2025-10-25 |  | ml
Order SHH Order Special Job schedule - table DSSHHSAT (check last run jobs on schedule) | Michael |  | 2025-10-26 |  | ml | Work with Scheduling to make sure all jobs are good
Gather "Before" MQ counts for MQPA from Mainview Explorer, save contents in a spreadsheet, "MQP2 Before Shutdown" | Denise |  | 2025-10-26 | 12:27 | dvm
Check all queues on MQPA that have depth -- check persistence of messages -- back up messages if not persistent Run SYS2.SYSTEMS.JOBS(QMMNOPER) Search for BMCQMM309I AMQ* queues can be disregarded. Anything else should be assessed and offload if needed. | Denise |  | 2025-10-26 | 12:28 | dvm | Had an issue with CIG52 or CIG52T messages in the past -- reached out to CMS team in 2022 -- Further analysis revealed that one of the MQTA queues for these is set to non-persistent, but they did not want to change | These error messages are not an issue: BMCQMM327W
DO NOT PROCEED WITH MQ SHUT DOWN UNTIL THE ABOVE STEPS ARE DONE
Load Shutdown table and watch jobs, note anything that needs to be done in future |  |  | 2025-10-26 | 0:00 | ml
Confirm MQPABKUP job ran as part of MQSSHUT | Michael |  | 2025-10-26 | 0:29 | ml
Jobs should handle everything up until stopping CONTROLM/O and running CTMCAJF | Michael
Force job DSTMP01J to run from the schedule to do the initial clean-up of TEMP files | Michael |  |  |  |  | bypassed all conditions, put to class Z.
Before stopping TSO and SDSF access log and grab last IEF234E message to confirm tape made it to CoLo | Michael |  |  |  |  | See DLm Site Swap proceures or IEF234E tab | IEF234E K 0A5F,401215,PVT,DSDISWKB,DSSDUMP - RACK=401215 IEF234E K 0903,900671,PVT,MODB2WKB - RACK=900671
Confirm SHxxx02 | [6 empty] | add JSF to JESB (maybe..)
Shut down JESC LPAR -- Temple | Michael |  |  |  |  | Shutdown Doc
Shut down JESA LPAR -- Temple | Michael |  |  |  |  | Shutdown Doc
Shut down JESB LPAR -- Temple **Refer to JES2 Checkpoint Procedures below | Michael |  |  |  |  | Shutdown Doc
JES2 Checkpoint Procedures: $D CKPTDEF CKPT1=(STRNAME=JES2_JES2,INUSE=YES,VOLATILE=YES) CKPT2=(DSNAME=SYS1.HASPCKPT,VOLSER=SYSM02,INUSE=YES,VOLATILE=NO) NEWCKPT1=(DSNAME=,VOLSER=) MODE=DUPLEX,DUPLEX=ON $T CKPTDEF,NEWCKPT1=(DSN=SYS1.HASPCKPT,VOL=SYSM01) $D CKPTDEF CKPT1=(STRNAME=JES2_JES2,INUSE=YES,VOLATILE=YES) CKPT2=(DSNAME=SYS1.HASPCKPT,VOLSER=SYSM02,INUSE=YES,VOLATILE=NO) NEWCKPT1=(DSNAME=SYS1.HASPCKPT,VOLSER=SYSM01) MODE=DUPLEX,DUPLEX=ON | Michael
$TCKPTDEF,RECONFIG=YES *$HASP285 JES2 CHECKPOINT RECONFIGURATION STARTED *$HASP271 CHECKPOINT RECONFIGURATION OPTIONS Response: 1 (FORWARD CKPT1 TO NEWCKPT1) *$HASP273 JES2 CKPT1 DATA SET WILL BE ASSIGNED TO NEWCKPT1 Response: CONT $HASP280 JES2 CKPT1 DATA SET (SYS1.HASPCKPT ON SYSM01) IS NOW IN USE *24 $HASP294 WAITING FOR RESERVE (VOL SYSM01). REPLY 'CANCEL' TO END WAIT IEE400I THESE MESSAGES CANCELLED - 24. *$HASP256 FUTURE AUTOMATIC FORWARDING OF CKPT1 IS SUSPENDED UNTIL 306 NEWCKPT1 IS RESPECIFIED. ISSUE $T CKPTDEF,NEWCKPT1=(...) TO RESPECIFY $HASP255 JES2 CHECKPOINT RECONFIGURATION COMPLETE $D CKPTDEF CKPT1=(DSNAME=SYS1.HASPCKPT,VOLSER=SYSM01,INUSE=YES,VOLATILE=NO), CKPT2=(DSNAME=SYS1.HASPCKPT,VOLSER=SYSM02,INUSE=YES,VOLATILE=NO), NEWCKPT1=(DSNAME=,VOLSER=), MODE=DUPLEX,DUPLEX=ON | Michael |  |  | 0:57 | ml
Deactivate JESC LPAR -- Temple | Michael
Deactivate JESA LPAR -- Temple | Michael
Deactivate JESB LPAR -- Temple | Michael
Deactivate XCFA00 CF LPAR -- Temple | Michael
Deactivate XCFB00 CF LPAR -- Temple | Michael
Deactivate MV3A LPAR -- Temple | Michael
Deactivate MV3B LPAR -- Temple | Michael
Deactivate MV3C LPAR -- Temple | Michael
Deactivate XCFA01 CF LPAR -- Temple | Michael
Deactivate XCFB01 CF LPAR -- Temple | Michael |  | 2025-10-25 | 0:59 | ml
PowerMax DASD
Startup EMER LPAR in Temple and EMER F600 console Activate EMER Load 3003 / 3003C0 Respond "00,C" when prompted for 8GB memory | Denise |  |  |  |  | MV1AF600 console ID
Respond 01continue and 02continue on RACF messages
Respond 03,warm,noreq for JES2 initialization
If prompted about IEF238D SMFDUMP, cancel it. Right now no dump volume available.
d a,l VTAM should be active, manually start TSO. S TSO
You should now be able to access EMER on F61x console, via option F) TSO3
TSO DSP VOL should only give this when gearing up to move VOLUME UNIT DEVICE SERIAL ADDR TYPE S24EMR 3003 3390 S23EMR 3004 3390 S23EM1 3006 3390 SYS999 3007 3390 S24EM1 3008 3390
Validate no owed tracks on JES2 and MVS3 Storage Groups (R0,R10) Start EMCSCF and EMCRDF if tasks are not active. S EMCSCF -- wait to come up before starting EMCRDF S EMCRDF #SQ VOL,30C0,INV_TRKS | Denise |  |  |  | dvm
Validate TCPIP from Temple, submit SYS2.SYSTEMS.JOBS(TCPEMER) Run "Ping test - EMER" and confirm all Ips respond. This is each F# OSA card that is defined | Michael |  |  |  | ml | No reason to do this
Shutdown EMER LPAR in Temple | [5 empty] | Keep it up
PowerMax and DD/DLm failover activities |  |  | 2025-10-26 | 1:21 | dvm
PowerMax Reverse replicatoin - CoLo (R2) to Temple (R1) replication -- Stop at step 33 in doc | Michael |  |  |  |  | See "PowerMax Siteswap procedures DST to DSC - JES2
DD Reverse replication - CoLo to Temple ---- Same time as Reverse DASD Replication | Michael |  |  |  |  | See DLM and DataDomain Siteswap procedures DST to DSC
Network Port Changes (Likely no action needed, keeping for awareness today) | Michael |  |  |  |  | No changes were needed going to COLO, but if any addresses don't come online, contact Network (Trae, Chou, whoever)
Startup CoLo Mainframe
Activate CBU record - V05 **Update ICF/CPU values in activation profile ICF - 2 initial; 0 reserved CPU - 5 initial; 0 reserved Confirm LPAR CPU counts A-4; B-3; C=2 | Michael |  |  |  |  | We activated the ZIIP and notced PUs went to 8 (assume this is how many remain) | CBU Activation - 2025.docx
Startup EMER LPAR in CoLo - IODF for R2s (4x line) Load address is 4003 ( ADDRESS FOR S24EMR VOLUME) -- confirmed 2025-03-21 Load parm is 4003C3 **WILL GET PROMPT FOR LESS THAN 8GB MEMORY -- Respond 00,c | Michael |  | 2025-10-25 | 20:49 | ml |  | Ran into issue with ISPF profiles…think its related to packs required that are on JES2 or MVS3 sG
Respond to promts as follows: 0 - 00,u 1 - ##,continue for RACF (twice - Primary & Secondary) 2 - For JES2 init $HASP426 -- ##,warm,noreq 3 - For $HASP478 - ##,y 4 - s TSO -- start TSO after d a,l shows VTAM is up | Michael
Validate EMC is working. Might have owed tracks on JES2 and MVS3 Storage Groups (R0,R10) Start EMCSCF and EMCRDF if tasks are not active. S EMCSCF4 -- wait to come up before starting EMCRDF S EMCRDF #SQ VOL,40C0,INV_TRKS | Michael |  | 2025-10-26 | 1:42 | ml
Pre-JESB IPL activities on EMER in COLO (1) Verify unit 4200 is online (SYS111 - SYS1.DISASTER.CNTL) Verify unit 4000 is online (SYSCOM) (2) Execute jobs to reinitialize TEMP volumes: SYS1.DISASTER.CNTL(TEMPOFF) SYS1.DISASTER.CNTL(TEMPIN9J) -- Make sure pointing to TEMPIN9U member (4xxx units) SYS1.DISASTER.CNTL(TEMPONL) SYS1.DISASTER.CNTL(TEMPVVDJ) Vary volumes offline to get COLO back to just the 5 packs we want online SYS1.DISASTER.CNTL(TEMPOFF) | Michael |  | 2025-10-26 | 1:42 | ml | Noticed TEMPIN9U was pointed to UNIT(3s updated to UNIT(4s
If any other volumes are online, vary them off. This is what should be online: TSO DSP VOL should only give this when gearing up to move VOLUME UNIT DEVICE SERIAL ADDR TYPE S24EMR 4003 3390 S23EMR 4004 3390 S23EM1 4006 3390 SYS999 4007 3390 S24EM1 4008 3390 Issue "V 4xxx,OFFLINE" (to bring anything else offline. Such as SYSCOM, 'V 4000,offline" | Michael |  |  | 1:46 | ml
Activate XCFB00 CF LPAR | Michael |  |  | 1:44 | ml
Activate JESB, JESA, JESC LPARs | Michael |  |  | 1:44 | ml
Start JESB F600 Console - Colo | Michael
IPL JESB LPAR (IODF31) Load address is 4460 ( ADDRESS FOR S25R01 VOLUME) -- confirmed 2025-03-21 Load parm is 4000F3 ( ADDRESS FOR SYSCOM VOLUME) -- confirmed 2025-03-21 IPL with Clear option Set scroll option: K S,DEL=RD F6 on console will set Validate system time is accurate | Michael |  |  | 1:47 | ml
IPL System Messages & Responses
IXC420D REPLY I TO INITIALIZE SYSPLEX | Michael |  |  | 1:48 | ml
IXC420D REPLY I TO INITIALIZE SYSPLEX JES2, OR R TO REINITIALIZE XCF. REPLYING I WILL IMPACT OTHER ACTIVE SYSTEMS. | Michael
R 0,I | Michael
Respond to Coupling Facility messages - use what is in COUPLEDR
IXC287I THE COUPLE DATA SETS SPECIFIED IN COUPLEDR ARE INCONSISTENT WITH THOSE LAST USED FOR CFRM IXC288I COUPLE DATA SETS SPECIFIED IN COUPLEDR FOR CFRM ARE PRIMARY: SYS1.PLEXDR.JES2Z15.CFRM.PCOUPLE ON VOLSER SYSM11 ALTERNATE: SYS1.PLEXDR.JES2Z15.CFRM.ACOUPLE ON VOLSER SYSM10 IXC288I COUPLE DATA SETS LAST USED FOR CFRM ARE PRIMARY: SYS1.PLEX.JES2Z15.CFRM.PCOUPLE ON VOLSER SYSM11 ALTERNATE: SYS1.PLEX.JES2Z15.CFRM.ACOUPLE ON VOLSER SYSM10
IXC288I COUPLE DATA SETS LAST USED FOR CFRM ARE PRIMARY: SYS1.PLEX.JES2Z15.CFRM.PCOUPLE ON VOLSER SYSM11 ALTERNATE: SYS1.PLEX.JES2Z15.CFRM.ACOUPLE ON VOLSER SYSM10 IXC289D REPLY U TO USE THE DATA SETS LAST USED FOR CFRM OR C TO USE THE COUPLE DATA SETS SPECIFIED IN COUPLEDR
R 0,C
IXC248E COUPLE DATA SET SYS1.PLEXDR.JES2Z15.CFRM.PCOUPLE ON VOLSER SYSM11 FOR CFRM MAY BE IN USE BY ANOTHER SYSPLEX. IXC247D REPLY U TO ACCEPT USE OR D TO DENY USE OF THE COUPLE DATA SET FOR CFRM.
R 0,U
IXC248E COUPLE DATA SET SYS1.PLEXDR.JES2Z15.CFRM.ACOUPLE ON VOLSER SYSM10 FOR CFRM MAY BE IN USE BY ANOTHER SYSPLEX. IXC247D REPLY U TO ACCEPT USE OR D TO DENY USE OF THE COUPLE DATA SET FOR CFRM.
R 0,U
Validate CF Structures ***Activate CF Policy to load any changes made in Temple since last failover -- ISSUE IF CHANGES NOTED BELOW ARE NOT BEING REFLECTED SETXCF START,POLICY,TYPE=CFRM,POLNAME=POLICY02 | [5 empty] | Not needed this go around, no changes
$HASP426 SPECIFY OPTIONS - JES2 z/OS, reply
R #,WARM,NOREQ | Michael
$HASP479 UNABLE TO OBTAIN CKPT DATA SET LOCK - MEMBER=JESB $HASP454 SHOULD JES2 BYPASS THE MULTI-MEMBER INTEGRITY LOCK? ('Y' OR 'N')
R #,Y | Michael |  |  | 1:49 | ml
$HASP493 JES2 ALL-MEMBER WARM START IS IN PROGRESS - Z## MODE
***JES2 Checkpoint Stuff during IPL*** Put CKPT1 back to CF |  |  |  |  | 1:26
IPL Verification
Do displays on network ports FC/FD/F8/F9 to validate ONLINE | [5 empty] | D M=CHP(F#)
D OMVS
OMVS Active message displayed if fully up | [5 empty] | Confirm it says it is ACTIVE
Display the Coupling Facility
D XCF -- shows JESB in CF D XCF,STR -- shows allocated structures at this point D XCF,STR,STRNM=IXCPATH1A -- confirms XCF path structures are allocated
D GRS
***** Should display GRS STAR MODE
ISG343I 05.49.43 GRS STATUS 321 SYSTEM STATE SYSTEM STATE JESB CONNECTED GRS STAR MODE INFORMATION LOCK STRUCTURE (ISGLOCK) CONTAINS 4194304 LOCKS. THE CONTENTION NOTIFYING SYSTEM IS JESB SYNCHRES: YES ENQMAXU: 16384 ENQMAXA: 250000 GRSQ: CONTENTION
Display SMSVSAM status | Michael
D SMS,SHCDS
***** Should display which datasets are Active. Status should be GOOD.
IGW612I 09:51:57 DISPLAY SMS,SHCDS Name Size %UTIL Status Type PRIM001.VSYSM10 72000Kb 1% GOOD ACTIVE SPA0001.VSYSM11 72000Kb 1% GOOD ACTIVE SEC0001.VSYSM11 72000Kb 1% GOOD ACTIVE SPA0001.VSYSM13 72000Kb 1% GOOD SPARE
D RRS,URSTATUS
ATR623I 09.08.59 RRS UR STATUS 453 SYSTEM GNAME STATE NUM OF URS MIN TIME MAX TIME JESB JES2 FLIGHT.......... JESB JES2 PRE PREPARE..... JESB JES2 STATE CHECK..... JESB JES2 PREPARE......... JESB JES2 DOUBT........... JESB JES2 ONLY AGENT...... JESB JES2 COMMIT.......... JESB JES2 BACKOUT......... JESB JES2 END............. JESB JES2 COMPLETION...... JESB JES2 FORGET.......... JESB JES2 Total URs.... 0
Check Tape Devices and DLm Status
Display device 0A## & 09## in z/OS D M=DEV(0A00-0A1F) D M=DEV(0900-091F) | Michael
Validate DLm VT Status = Running Login to the DLm management tool Select the Console Select option 1 - vtcon Display at the bottom of the log should read "VT Status: Running"
Start VTAM, TCPIP, etc.
F CONTROLO,F=SYS2.IOAO.MCLANE.RULES(IPLMINI) | Michael
Cleanup Catalog for TEMP datasets since TEMP volumes were previously initialized
SYS1.DISASTER.CNTL(DELTMPGN) | [5 empty] | !!!! Manually clean up DB2MSUB.TEMP datasets in 3.4
Eliminate IST530I and IST532I messages
F VTAM,IOPD,IOINT=0 | Michael
Check connectivity (network ports FC/FD/F8/F9, PINGs, etc.,) RO *ALL,D NET,TRL | Michael
Run "ping test-jesb" from Roleswap folder | Michael |  |  |  |  | If all addresses do not respond, contact Network
Stop TCPT3270 -- Port 23 listener -- p tcpt3270 Make sure TCPT327X -- Port 230 listener -- is active, if not issue 's tcpt327x' Start InterSession -- s intsess -- will expire after 30 minutes due to no key | Michael |  |  |  |  | skipping
Ping the PFTECO01 and PFTEAG01 Linux servers
TSO PING lpdstpfteco01 | Michael
TSO PING lpdstpfteag01 | Michael
Validate Tape Processing
Run tape "list" job against previously created tape -- SYS1.DISASTER.CNTL(DRTPREAD)
Run backup job (DLm) -- document tape information for post-test validation - SYS1.DISASTER.CNTL(DRTPWRTE) |  |  |  | 1:59 | ml
Run tape "list" job against newly created tape -- SYS1.DISASTER.CNTL(DRTPREAD)
PowerMax Reverse replicatoin - CoLo (R2) to Temple (R1) replication -- Start at 34 to resume sync | [5 empty] | PowerMax Siteswap procedures DST to DSC - JES2.docx
Start HSM |  |  |  | 2:01 | ml | S HSM
Apply VPS key
Start VPS
Apply ZIP390 Key | [5 empty] | Run SYS2.SYSTEMS.JOBS.Z2R5.VALID(ZIP01) for validation
Apply RTD key, will start on JESA later
DB2 Tasks
Recovery DB2T, once complete can move down to MQT2/3
Start all three DB2Ts on JESB for recovery procedures
/@DBT1 START DB2 | Denise |  |  | 2:09
Continue after DBT1 starts and runs through its recovery
/@DBT2 START DB2 | Denise |  |  | 2:10
Continue after DBT2 starts and runs through its recovery
/@DBT3 START DB2 | Denise |  |  | 2:10
Continue after DBT3 starts and runs through its recovery
Submit SYS1.DISASTER.DB2(DRGRECT) ***May have to run several times until the SYSTSPRT DDNAME only contains “READY” and “END”. If more than “READY” and “END” are listed in SYSTSPRT after about 3 runs, contact a McLane DBA for assistance. Moreover, if any issues occur after DB2 has been started, please contact a McLane DBA. | Denise |  |  | 2:13
After job DBGRECT1 runs through its recovery, shutdown DBT1 & DBT2 and restart DBT1
/@DBT3 STOP DB2 | Denise |  |  | 2:15 |  | Mode(force) if necessary
/@DBT2 STOP DB2 | Denise |  |  | 2:16
/@DBT1 STOP DB2 | Denise |  |  | 2:17
/@DBT1 START DB2 | Denise |  |  | 2:20
Recover DB2P, once complete can move down to MQP2/3
Start all three DB2Ps on JESB for recovery procedures
/@DBP1 START DB2 | Michael |  |  | 2:02 | ml
Continue after DBP1 starts and runs through its recover,
/@DBP2 START DB2 | Michael
Continue after DBP2 starts and runs through its recover,
/@DBP3 START DB2 | Michael
Continue after DBP2 starts and runs through its recover,
Submit SYS1.DISASTER.DB2(DRGRECP) ***May have to run several times until the SYSTSPRT DDNAME only contains “READY” and “END”. If more than “READY” and “END” are listed in SYSTSPRT after about 3 runs, contact a McLane DBA for assistance. Moreover, if any issues occur after DB2 has been started, please contact a McLane DBA. | Michael |  |  | 2:08 | ml
After job DBGRECP1 runs through its recovery, shutdown DBP2 & DBP1 and restart DBP1
/@DBP3 STOP DB2 | Michael |  |  | 2:08 |  | Mode(force) if necessary
/@DBP2 STOP DB2 | Michael |  |  | 2:09
/@DBP1 STOP DB2 | Michael |  |  | 2:09
/@DBP1 START DB2 | Michael |  |  | 2:10 | ml
Repeat the above for DB2I after everything else is up (see notes at bottom) | Michael
MQ Tasks for DB2 related Queue Sharing Groups ***After DB2 recovery tasks are complete***
Start MQT2MSTR (This will also start MQT2CHIN)
/MQT2 START QMGR | Denise |  |  | 2:21 |  | You should see the following for failed strctures CSQE035E MQT2 CSQEQSR1 Structure X1 in failed state, recovery needed | se - x all;f CSQE035E all
Recover MQTA coupling facility structures
Submit OPR.PERM.CNTL(MQSRECT2) | Denise |  |  | 2:25 |  | Look for CSQE131I for each structure | se - x all;f CSQE131I all - do this in the MQT2MSTR
***Watch for tape mount/HSM requests since CONTROL is not up*** | [5 empty] | ME structure will fail
After MQT2 finishes its recovery -- Start MQT3
/MQT3 START QMGR | Denise |  |  | 2:28
***Check for any recovery messages*** Should not get any b/c of MQT2 recovery | [5 empty] | Example, T2 had a structure failure that we recover, so T3 should not CSQE035E MQT2 CSQEQSR1 Structure X1 in failed state, recovery needed
After MQT3 is fully started -- Stop both MQT3 and MQT2
/MQT2 STOP QMGR | Denise |  |  | 2:29
/MQT3 STOP QMGR | Denise |  |  | 2:31
After MQT3 and MQT2 are both down -- Start MQT2
/MQT2 START QMGR | Denise |  |  | 2:31
After MQT2 is up -- Start the TEST MQ Trigger monitor |  |  |  | 2:32
/S MQTRGYYB | Denise
Start MQP2MSTR (This will also start MQP2CHIN)
/MQP2 START QMGR | Michael |  |  | 2:10 | ml
Recover MQPA coupling facility structures
Submit OPR.PERM.CNTL(MQSRECP2) | Michael |  |  | 2:10 | ml | Look for CSQE131I for each structure
After MQP2 finishes its recovery -- Start MQP3
/MQP3 START QMGR | Michael |  |  | 2:12 | ml
***Check for any recovery messages*** Should not get any b/c of MQP2 recovery
After MQP3 is fully started -- Stop both MQP3 and MQP2
/MQP2 STOP QMGR | Michael |  |  | 2:12 | ml
/MQP3 STOP QMGR | Michael |  |  | 2:12 | ml
After MQP3 and MQP2 are both down -- Start MQP2
/MQP2 START QMGR | Michael |  |  | 2:13 | ml
After MQP2 Initialization is complete -- Backup MQPA coupling facility structures
/S MQPABKUP | Michael
*** Confirm the backup (MQPABKUP job in queue) ran successfully
After MQPABKUP is complete -- Start the PROD MQ Trigger monitor
/S MQTRGXXB | Michael
***Check MQPA Queue Counts against B4 values*** NOTE: There can be differences in some queues (i.e. INTEGRATOR) if they are not tied to the PTDCMQ01 MQ server (channels stopped) and OP (schedule stopped) | Denise |  |  |  |  | Queues associated with divisional queue managers could have higher counts since those channels are not stopped - possibly other QMGRs also
Gather "After" MQ counts for MQPA from Mainview Explorer, save contents in a spreadsheet, "MQP2 After Recovery" and compare counts | Denise
MQ Tasks for non-Queue Sharing Groups (NO DB2 required)
Start MQGAMSTR (This will also start MQGACHIN)
/MQGA START QMGR | Michael |  |  | 2:00 | ml
After MQGACHIN: CSQU012I CSQUTIL Initialization command handling completed Start MQGA Agent
/S MQGAAGT | Michael |  |  | 2:00 | ml
Start MQFAMSTR (This will also start MQFACHIN)
/MQFA START QMGR | Michael |  |  | 2:22 | ml
After MQFACHIN: CSQU012I CSQUTIL Initialization command handling completed Start MQFA Agent
/S MQFAAGT | Michael |  |  | 2:22 | ml
Start MQB1MSTR (This will also start MQB1CHIN)
/MQB1 START QMGR | Michael |  |  | 2:01
Start Mainview and begin validation - "S MVSTART" | [5 empty] | Make sure we can see QMs
Final JESB Startup Tasks
Perform Started Task validation for JESB **Intersession will be brought after the final started task validation for ALL LPARs later in this plan** | Michael
Complete PowerMax reverse Replication procedures | Denise
Suspend Snapshot policies in COLO | Denise
IPL JESA
Start JESA F600 Console
IPL JESA LPAR (IODF31) Load address is 4460 ( ADDRESS FOR S25R01 VOLUME) -- confirmed 2025-03-21 Load parm is 4000F3 ( ADDRESS FOR SYSCOM VOLUME) -- confirmed 2025-03-21 IPL with Clear option Set scroll option: K S,DEL=RD F6 on console will set Validate system time is accurate |  |  |  | 2:41 | ml
F CONTROLO,F=SYS2.IOAO.MCLANE.RULES(IPLSECND) | Michael
IPLJESC
IPL JESC LPAR (IODF31) Load address is 4460 ( ADDRESS FOR S25R01 VOLUME) -- confirmed 2025-03-21 Load parm is 4000F3 ( ADDRESS FOR SYSCOM VOLUME) -- confirmed 2025-03-21 IPL with Clear option Set scroll option: K S,DEL=RD F6 on console will set Validate system time is accurate |  |  |  | 2:51 | ml
F CONTROLO,F=SYS2.IOAO.MCLANE.RULES(IPLJESC) | Michael
Validate that ALL expected started tasks are running - SYS2.SYSTEMS.JOBS(STCVER) *** Before bringing up CICS *** | Michael
Run PING tests for JESA and JESC from Roleswap folder ping test-jesa ping test-jesc | Michael |  |  |  |  | If all IPs do not respond, contact Network
Start CICS
Start PROD & TEST TSQ and CMSA tasks
/S J,N=CICSGO1 | Denise |  |  | 3:18
***Verify tasks are started
***** CMAS wait for “CMAS initialization complete”
Start PROD & TEST WUSA and APPL tasks
/S J,N=CICSGO2 | Denise |  |  | 3:20
***Verify tasks are started
***** WUI wait for “CICSPlex SM Web User Interface initialization complete”
*** Look for given in CIPSB1, CIPSB2, CIDSB1, CICE ***
*** Look for given in task ***
Start PROD & TEST Terminal tasks
/S J,N=CICSGO3 | Denise |  |  | 3:21
***Verify tasks are started
*** Look for given in CIPSTB, CIDSTB ***
Initialize EXCI interface on non-JESC LPARSStart PROD & TEST Terminal tasks
/S J,N=CICSGO4 | Denise |  |  | 3:22 |  | Submits M1MBCJB and M1MBCJA
***Verify job successfully completes
Initialize Temporary Storage
Submit MC.PERM.JCL(DSTSQ01J) -- Verify successful completion | Denise |  |  | 3:23
Additional CICS jobs
Run jobs after CICS is up to open files and initialize TCPIP for XPED OPR.PRM.CNTL - SSY0OPEN NRIOPEN CICSTCP | Denise |  |  | 3:25
Final Activities
Validate that ALL expected started tasks are running - SYS2.SYSTEMS.JOBS(STCVER) *** Before bringing up CICS *** | [5 empty] | on a normal DR we would do this, can skip on double siteswap as we are doing very limited validation
Review the DUMP data sets and determine what action is to be taken (Cleared/Sent to IBM) | [5 empty] | no dumps taken this time
Ping from/to mclmvs -- From Desktop run ping test-jesb to work out all cards ping from JESA -- From Desktop run ping test-jesa to work out all cards ping from JESC -- From Desktop run ping test-jesc to work out all cards FTE big test from/to -- Setup job to move data from MQGAAGT to TFTEAG01 CTM / EM validation -- No reason to do to EM/CM on this test. Do a backup in addition to DRTPWRTE -- Setup a job to write some sort of data | [5 empty] | Validate pings worked Run SYS2.SYSTEMS.JOBS(FTEBIGV) to do FTE Z2L and L2Z and backup the file to DSN=MT.PERM.ZSERIES.BIGFILE.TEST.FROM.COLO.D251019
Post-Swap
Validate TSO DB2TOOLS (can query BE3T or anything else)
Note on A61: Michael Lehman: Expected output is to see invalid tracks on EMER (20) JES2P (01), and MVS3P (11) groups, like this: EMCQV33I SRDF-HC Invalid Track Counts by RDF Group RDF Group Devices R1 INVTRK R2 INVTRK 0001 54 0 6,611,006 0011 4 0 93,616 0020 5 0 7,627 ALL 63 0 6,712,249 If invalid tracks on Group 0 or 10, it means MVS3/JES2 are not in sync!!!!
Note on A73: Michael Lehman: Expected output is to see invalid tracks on EMER (20) JES2P (01), and MVS3P (11) groups, like this: EMCQV33I SRDF-HC Invalid Track Counts by RDF Group RDF Group Devices R1 INVTRK R2 INVTRK 0001 54 0 6,611,006 0011 4 0 93,616 0020 5 0 7,627 ALL 63 0 6,712,249 If invalid tracks on Group 0 or 10, it means MVS3/JES2 are not in sync!!!!
Note on A80: James Barton: IXC287I THE COUPLE DATA SETS SPECIFIED IN COUPLE22 ARE INCONSISTENT WITH THOSE LAST USED FOR CFRM IXC288I COUPLE DATA SETS SPECIFIED IN COUPLE22 FOR CFRM ARE 168 PRIMARY: SYS1.PLEX.JES2.CFRM.PCOUPLE ON VOLSER SYSM11 ALTERNATE: SYS1.PLEX.JES2.CFRM.ACOUPLE ON VOLSER SYSM10 IXC288I COUPLE DATA SETS LAST USED FOR CFRM ARE 169 PRIMARY: SYS1.PLEXDR.JES2.CFRM.PCOUPLE ON VOLSER SYSM11 ALTERNATE: SYS1.PLEXDR.JES2.CFRM.ACOUPLE ON VOLSER SYSM10 IXC289D REPLY U TO USE THE DATA SETS LAST USED FOR CFRM OR C TO USE THE COUPLE DATA SETS SPECIFIED IN COUPLE22 IEE282A REPLY 00 EXPECTED; NO OTHER COMMANDS ACCEPTED. SPECIFY REPLY 00. IEE600I REPLY TO 00 IS;C
Note on A105: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: *$HASP458 FORWARDED CKPT1 DATA SET IS 113 SYS1.HASPCKPT ON SYSM01 *02 $HASP457 FORWARDED DATA SET NAME FOUND. SHOULD JES2 FORWARD? ('Y' OR 'N') CNZ2605I At 04.34.19 the system will automatically 115 reply: Y to the following WTOR: 0002 $HASP457 FORWARDED DATA SET NAME FOUND. SHOULD JES2 FORWARD? ('Y' OR 'N') *BPXP007E STARTING PHYSICAL FILE SYSTEM TFS IN ADDRESS SPACE TFSSTC R 02,Y IEE600I REPLY TO 02 IS;Y IEF196I IEF237I 1301 ALLOCATED TO SYS00002 *$HASP416 VERIFY CHECKPOINT DATA SET INFORMATION 121 * VALUES FROM CKPTDEF CKPT1=(STRNAME=JES2_JES2,INUSE=YES), CKPT2=(DSNAME=SYS1.HASPCKPT,VOLSER=SYSM02,INUSE=YES) * VALUES JES2 WILL USE CKPT1=(DSNAME=SYS1.HASPCKPT,VOLSER=SYSM01,INUSE=YES), CKPT2=(DSNAME=SYS1.HASPCKPT,VOLSER=SYSM02,INUSE=YES), LAST WRITTEN SUNDAY, 24 SEP 2017 AT 08:52:05 (GMT) *03 $HASP417 ARE THE VALUES JES2 WILL USE CORRECT? ('Y' OR 'N') R 03,Y IEE600I REPLY TO 03 IS;Y $HASP478 INITIAL CHECKPOINT READ IS FROM CKPT1 126 (SYS1.HASPCKPT ON SYSM01) LAST WRITTEN SUNDAY, 24 SEP 2017 AT 08:52:05 (GMT) ...reconfiguration back to JES2_JES2 structure... $D CKPTDEF $HASP829 CKPTDEF 230 $HASP829 CKPTDEF CKPT1=(DSNAME=SYS1.HASPCKPT,VOLSER=SYSM01, $HASP829 INUSE=YES,VOLATILE=NO), $HASP829 CKPT2=(DSNAME=SYS1.HASPCKPT,VOLSER=SYSM02, $HASP829 INUSE=YES,VOLATILE=NO),NEWCKPT1=(DSNAME=, $HASP829 VOLSER=),NEWCKPT2=(DSNAME=,VOLSER=), $HASP829 MODE=DUPLEX,DUPLEX=ON,LOGSIZE=2, $HASP829 VERSIONS=(STATUS=ACTIVE,NUMBER=50,WARN=80, $HASP829 MAXFAIL=0,NUMFAIL=0,VERSFREE=50,MAXUSED=1), $HASP829 RECONFIG=NO,VOLATILE=(ONECKPT=WTOR, $HASP829 ALLCKPT=WTOR),OPVERIFY=YES $TCKPTDEF,NEWCKPT1=(STRNAME=JES2_JES2) $HASP829 CKPTDEF 251 $HASP829 CKPTDEF CKPT1=(DSNAME=SYS1.HASPCKPT,VOLSER=SYSM01, $HASP829 INUSE=YES,VOLATILE=NO), $HASP829 CKPT2=(DSNAME=SYS1.HASPCKPT,VOLSER=SYSM02, $HASP829 INUSE=YES,VOLATILE=NO), $HASP829 NEWCKPT1=(STRNAME=JES2_JES2), $HASP829 NEWCKPT2=(DSNAME=,VOLSER=),MODE=DUPLEX, $HASP829 DUPLEX=ON,LOGSIZE=2, $HASP829 VERSIONS=(STATUS=ACTIVE,NUMBER=50,WARN=80, $HASP829 MAXFAIL=0,NUMFAIL=0,VERSFREE=50,MAXUSED=1), $HASP829 RECONFIG=NO,VOLATILE=(ONECKPT=WTOR, $HASP829 ALLCKPT=WTOR),OPVERIFY=YES $TCKPTDEF,RECONFIG=YES *$HASP285 JES2 CHECKPOINT RECONFIGURATION STARTING *$HASP233 REASON FOR JES2 CHECKPOINT RECONFIGURATION IS OPERATOR 327 REQUEST *$HASP285 JES2 CHECKPOINT RECONFIGURATION STARTED - DRIVEN BY 328 MEMBER JESB *$HASP271 CHECKPOINT RECONFIGURATION OPTIONS 329 * VALID RESPONSES ARE: * '1' - FORWARD CKPT1 TO NEWCKPT1 '2' - FORWARD CKPT2 TO NEWCKPT2 '5' - SUSPEND THE USE OF CKPT1 '6' - SUSPEND THE USE OF CKPT2 'CANCEL' - EXIT FROM RECONFIGURATION CKPTDEF (NO OPERANDS) - DISPLAY MODIFIABLE SPECIFICATIONS CKPTDEF (WITH OPERANDS) - ALTER MODIFIABLE SPECIFICATIONS *09 $HASP272 ENTER RESPONSE (ISSUE D R,MSG=$HASP271 FOR RELATED MSG) R 09,1 IEE600I REPLY TO 09 IS;1 *$HASP273 JES2 CKPT1 DATA SET WILL BE ASSIGNED TO NEWCKPT1 345 * STRNAME JES2_JES2 * VALID RESPONSES ARE: * 'CONT' - PROCEED WITH ASSIGNMENT 'CANCEL' - EXIT FROM RECONFIGURATION CKPTDEF (NO OPERANDS) - DISPLAY MODIFIABLE SPECIFICATIONS CKPTDEF (WITH OPERANDS) - ALTER MODIFIABLE SPECIFICATIONS *10 $HASP272 ENTER RESPONSE (ISSUE D R,MSG=$HASP273 FOR RELATED MSG) R 10,CONT IEE600I REPLY TO 10 IS;CONT IXC582I STRUCTURE JES2_JES2 ALLOCATED BY SIZE/RATIOS. 357 PHYSICAL STRUCTURE VERSION: D32FCC15 90C89C41 STRUCTURE TYPE: SERIALIZED LIST CFNAME: XCFB00 ALLOCATION SIZE: 30 M MAX STRUCTURE SIZE: 30 M POLICY SIZE: 30000 K ENTRY COUNT: 7004 ELEMENT COUNT: 6957 LOCKS: 2 ENTRY:ELEMENT RATIO: 1 : 1 ALLOCATION SIZE IS WITHIN CFRM POLICY DEFINITIONS IXL014I IXLCONN REQUEST FOR STRUCTURE JES2_JES2 358 WAS SUCCESSFUL. JOBNAME: JES2 ASID: 0039 CONNECTOR NAME: JES2_JESB CFNAME: XCFB00 *$HASP237 NEWCKPT1 STRNAME JES2_JES2 IS ON A VOLATILE COUPLING FACILITY 360 * VALID RESPONSES ARE: * 'CONT' - PROCEED WITH ASSIGNMENT 'CANCEL' - EXIT FROM RECONFIGURATION CKPTDEF (NO OPERANDS) - DISPLAY MODIFIABLE SPECIFICATIONS CKPTDEF (WITH OPERANDS) - ALTER MODIFIABLE SPECIFICATIONS IXL015I STRUCTURE ALLOCATION INFORMATION FOR 359 STRUCTURE JES2_JES2, CONNECTOR NAME JES2_JESB, CONNECTIVITY=DEFAULT CFNAME ALLOCATION STATUS/FAILURE REASON -------- ---------------------------------------- XCFB00 STRUCTURE ALLOCATED A4001800 XCFA00 PREFERRED CF ALREADY SELECTED A4001800 PREFERRED CF HIGHER IN PREFLIST *11 $HASP272 ENTER RESPONSE (ISSUE D R,MSG=$HASP237 FOR RELATED MSG) IST663I IPS SRC REQUEST TO ISTAPNCP RECEIVED, SENSE=087D0001 362 IST664I REAL OLU=MCLANES.TV020020 ALIAS DLU=MCLANES.CIPST IST889I SID = C6634D0EB6A14C5D IST1705I SORDER = APPN FROM START OPTION IST1705I SSCPORD = PRIORITY FROM START OPTION IST894I ADJSSCPS TRIED FAILURE SENSE ADJSSCPS TRIED FAILURE SENSE IST895I ISTAPNCP 08400007 VTAMJES2 08260000 IST314I END R 11,CONT IEE600I REPLY TO 11 IS;CONT IEF196I IEF285I SYS1.HASPCKPT KEPT IEF196I IEF285I VOL SER NOS= SYSM01. $HASP280 JES2 CKPT1 DATA SET (STRNAME JES2_JES2) IS NOW IN USE *$HASP256 FUTURE AUTOMATIC FORWARDING OF CKPT1 IS SUSPENDED UNTIL 368 NEWCKPT1 IS RESPECIFIED. ISSUE $T CKPTDEF,NEWCKPT1=(...) TO RESPECIFY $HASP255 JES2 CHECKPOINT RECONFIGURATION COMPLETE $D CKPTDEF $HASP829 CKPTDEF 393 $HASP829 CKPTDEF CKPT1=(STRNAME=JES2_JES2,INUSE=YES, $HASP829 VOLATILE=YES),CKPT2=(DSNAME=SYS1.HASPCKPT, $HASP829 VOLSER=SYSM02,INUSE=YES,VOLATILE=NO), $HASP829 NEWCKPT1=(DSNAME=,VOLSER=),NEWCKPT2=(DSNAME=, $HASP829 VOLSER=),MODE=DUPLEX,DUPLEX=ON,LOGSIZE=2, $HASP829 VERSIONS=(STATUS=ACTIVE,NUMBER=50,WARN=80, $HASP829 MAXFAIL=0,NUMFAIL=0,VERSFREE=50,MAXUSED=1), $HASP829 RECONFIG=NO,VOLATILE=(ONECKPT=WTOR, $HASP829 ALLCKPT=WTOR),OPVERIFY=YES
Note on A130: James Barton: Ping TFTEAG01 & PFTEAG01 servers Start TPX and logged on to TTWin session which goes to mclmvs (mainframe IP)
Note on A250: James Barton: IXC287I THE COUPLE DATA SETS SPECIFIED IN COUPLE22 ARE INCONSISTENT WITH THOSE LAST USED FOR CFRM IXC288I COUPLE DATA SETS SPECIFIED IN COUPLE22 FOR CFRM ARE 168 PRIMARY: SYS1.PLEX.JES2.CFRM.PCOUPLE ON VOLSER SYSM11 ALTERNATE: SYS1.PLEX.JES2.CFRM.ACOUPLE ON VOLSER SYSM10 IXC288I COUPLE DATA SETS LAST USED FOR CFRM ARE 169 PRIMARY: SYS1.PLEXDR.JES2.CFRM.PCOUPLE ON VOLSER SYSM11 ALTERNATE: SYS1.PLEXDR.JES2.CFRM.ACOUPLE ON VOLSER SYSM10 IXC289D REPLY U TO USE THE DATA SETS LAST USED FOR CFRM OR C TO USE THE COUPLE DATA SETS SPECIFIED IN COUPLE22 IEE282A REPLY 00 EXPECTED; NO OTHER COMMANDS ACCEPTED. SPECIFY REPLY 00. IEE600I REPLY TO 00 IS;C
Note on A253: James Barton: IXC287I THE COUPLE DATA SETS SPECIFIED IN COUPLE22 ARE INCONSISTENT WITH THOSE LAST USED FOR CFRM IXC288I COUPLE DATA SETS SPECIFIED IN COUPLE22 FOR CFRM ARE 168 PRIMARY: SYS1.PLEX.JES2.CFRM.PCOUPLE ON VOLSER SYSM11 ALTERNATE: SYS1.PLEX.JES2.CFRM.ACOUPLE ON VOLSER SYSM10 IXC288I COUPLE DATA SETS LAST USED FOR CFRM ARE 169 PRIMARY: SYS1.PLEXDR.JES2.CFRM.PCOUPLE ON VOLSER SYSM11 ALTERNATE: SYS1.PLEXDR.JES2.CFRM.ACOUPLE ON VOLSER SYSM10 IXC289D REPLY U TO USE THE DATA SETS LAST USED FOR CFRM OR C TO USE THE COUPLE DATA SETS SPECIFIED IN COUPLE22 IEE282A REPLY 00 EXPECTED; NO OTHER COMMANDS ACCEPTED. SPECIFY REPLY 00. IEE600I REPLY TO 00 IS;C

## Temple - LOAD settings
EMER:
JESB/A/C
MV3B/A/C

## Temple HMC-SE Info
d ios,config
D IOS,CONFIG
IOS506I 09.00.50 I/O CONFIG DATA 305
ACTIVE IODF DATA SET = SYS2.IODF11
CONFIGURATION ID = PROD EDT ID = 00
TOKEN: PROCESSOR DATE TIME DESCRIPTION
SOURCE: CP3932A 24-08-21 16:08:44 SYS2 IODF11
ACTIVE CSS: 0 SUBCHANNEL SETS CONFIGURED: 0, 1, 2
CHANNEL MEASUREMENT BLOCK FACILITY IS ACTIVE
SUBCHANNEL SET FOR PPRC PRIMARY: INITIAL = 0 ACTIVE | = | 0
HYPERSWAP FAILOVER HAS OCCURRED: NO
LOCAL SYSTEM NAME (LSYSTEM): P00AF008
Currently using Z16TIO11
LPAR Settings | Log Proc Assignment | Weight | Proc Init | Proc Res | Storage GB | ZIIP Init | ZIIP Res
XCFB00 | Not Dedicated ICF | 900 | 1 | 1 | 16 | n/a | n/a
XCFA00 | Not Dedicated ICF | 900 | 1 | 1 | 14 | n/a | n/a
XCFB01 | Not Dedicated ICF | 100 | 1 | 1 | 6 | n/a | n/a
XCFA01 | Not Dedicated ICF | 100 | 1 | 1 | 6 | n/a | n/a
JESB | Unchek Dedicated proc | 120 | 3 | 1 | 27 | 0 | 1
JESA | Unchek Dedicated proc | 140 | 4 | 1 | 25 | 0 | 1
JESC | Unchek Dedicated proc | 18 | 2 | 0 | 10 | 0 | 1
MV3B | Unchek Dedicated proc | 8 | 1 | 1 | 6 | 0 | 1
MV3A | Unchek Dedicated proc | 4 | 1 | 1 | 6 | 0 | 1
MV3C | Unchek Dedicated proc | 2 | 1 | 1 | 6 | 0 | 1
EMER | Unchek Dedicated proc | 3 | 1 | 1 | 6 | 0 | 0

## Temple HMC LPAR Values
LPAR Group Controls
LPAR Controls

## COLO - LOAD Settings (SNAP)
JESB - Disaster (no CTO or RRS by default)
JESA/C and JESB if failover (CTO and RRS auto start, GRS=STAR)
EMER (SNAP)

## COLO - Load Settings (R2)
EMER
JESA/JESC and JESB Failover (Control-O and RRS auto start, grs=star) -- Use this on a normal siteswap
JESB Disaster Recovery (Control-O and RRS don't start, GRS=TRYJOIN)

## IE234E valid
Find the last IE234E in the log and query the volume in COLO. It should reflect the same job.
https://10.40.22.17/login | Temple
https://10.49.22.9/ | CoLo

## COLO LPAR Values
LPAR Group Controls
LPAR controls