## Pre-Implementation Plan
S.No | Pre-Implementation Plan(DSNT) | Job details | Responsible Team | Status
2 | Take the dup of current runtime libraries - DSNT DSNT.SDSNC.H DSNT.SDSNCLST DSNT.SDSNDBRM DSNT.SDSNEXIT DSNT.SDSNIVPD DSNT.SDSNLINK DSNT.SDSNLOAD DSNT.SDSNLOD2 DSNT.SDSNMACS DSNT.SDSNPFPE DSNT.SDSNSAMP DSNT.SDSNSPFM DSNT.SDSNSPFP DSNT.SDSNSPFS DSNT.SDSNSPFT DSNT.SDXRRESL |  | DB2 | M620979.DSNTDUMP.SMPELIB.D121324
3 | Take the backup of RUNLIB, EXIT and LOAD DSNT.RUNLIB.LOAD, DSNT.SDSNEXIT,DSNT.SDSNLOAD |  | DB2 | DSNT.SDSNEXIT.RSU2312.BACKUP,DSNT.SDSNLOAD.RSU2312.BACKUP,DSNT.RUNLIB.LOAD.RSU2312.BACKUP
4 | Take the backup of SDSNLINK, DBRMLIB.DATA-DSNT.SDSNLINK,DSNT.DBRMLIB.DATA |  | DB2 | DSNT.SDSNLINK.RSU2312.BACKUP,DSNT.DBRMLIB.DATA.RSU2312.BACKUP
5 | Execute Jobs (J0, J1, TESQ) | DSNT.NEW.SDSNSAMP.RSU2312 | DB2 | Completed

## Pre-Implementation Plan (DSNL )
S.No | Pre-Implementation Plan(DSNL) | Job details | Responsible Team | Status
2 | Take the dup of current runtime libraries - DSNL DSNL.SDSNC.H DSNL.SDSNCLST DSNL.SDSNDBRM DSNL.SDSNEXIT DSNL.SDSNIVPD DSNL.SDSNLINK DSNL.SDSNLOAD DSNL.SDSNLOD2 DSNL.SDSNMACS DSNL.SDSNPFPE DSNL.SDSNSAMP DSNL.SDSNSPFM DSNL.SDSNSPFP DSNL.SDSNSPFS DSNL.SDSNSPFT DSNL.SDXRRESL |  | DB2 | M620979.DSNLDUMP.SMPELIB.D011225
3 | Take the backup of RUNLIB, EXIT and LOAD DSNL.RUNLIB.LOAD, DSNL.SDSNEXIT,DSNL.SDSNLOAD |  | DB2 | DSNL.SDSNEXIT.RSU2312.BACKUP DSNL.SDSNLOAD.RSU2312.BACKUP DSNL.RUNLIB.LOAD.RSU2312.BACKUP DSNL.SDSNLINK.RSU2312.BACKUP
4 | Take the backup of SDSNLINK, DBRMLIB.DATA-DSNL.SDSNLINK,DSNL.DBRMLIB.DATA |  | DB2 | DSNL.SDSNLINK.RSU2312.BACKUP
5 | Execute Jobs (J0, J1, TESQ) | DSNL.NEW.SDSNSAMP.RSU2312 | DB2

## Implementation Plan (DSNL )
S.No | Implementation Plan(DSNT - MTMUS) | Job/Command | Responsible Team | Status
1 | Bring down enqueues |  | Production Control | Complete
2 | Bring down DB2 (DSNT, DSNL ) |  | Production Control | Complete
3 | Remove below dataset from LLA, XCFAS DSNL.SDSNLOAD,DSNL.SDSNLINK |  | z/OS | Complete
4 | Rename runtime libraries and copy the new maintenance to current runtime libraries | DSNL.NEW.SDSNSAMP.RSU2312(RENAME1)& RENAME2 | DB2 | Complete
5 | Perform Holdactions | DSNL.NEW.SDSNSAMP.RSU2312(DSNTIJUZ) | DB2 | Complete
7 | Add dataset DSNL.SDSNLOAD,DSNL.SDSNLINK to LLA and then perform LLA refresh |  | z/OS | Complete
8 | Perform DB2 refresh for Early code | /+DSNL REFRESH DB2,EARLY | DB2 | Complete
9 | Start DB2 | /+DSNL START DB2 /+DSNT START DB2 | DB2 | Complete
10 | Issue DISPLAY GROUP COMMAND | (-DISPLAY GROUP DETAIL) | DB2 | Complete
11 | Execute DSNTEJ1L and DSNTEJ2A | DSNL.NEW.SDSNSAMP.RSU2312 | DB2 | Complete
12 | Execute DSNTIJTM Job | DSNL.NEW.SDSNSAMP.RSU2312 | DB2 | Complete
13 | Execute DSNTIJCL Job | DSNL.NEW.SDSNSAMP.RSU2312 | DB2 | Complete
14 | Execute DSNTIJRT Job | DSNL.NEW.SDSNSAMP.RSU2312 | DB2 | Complete
15 | Execute DSNTIJSG Job | DSNL.NEW.SDSNSAMP.RSU2312 | DB2 | Complete

## Implementation Plan
S.No | Implementation Plan(DSNT - MTMUS) | Job/Command | Responsible Team | Status
1 | Bring down enqueues |  | Production Control | Complete
2 | Bring down DB2 |  | Production Control | Complete
3 | Remove below dataset from LLA, XCFAS DSNT.SDSNLOAD |  | z/OS | not required for DSNT
4 | Rename runtime libraries and copy the new maintenance to current runtime libraries | DSNT.NEW.SDSNSAMP.RSU2312(RENAME1)& RENAME2 | DB2 | Complete
5 | Perform Holdactions | DSNT.NEW.SDSNSAMP.RSU2312(DSNTIJUZ) | DB2 | Complete
7 | Perform LLA Refresh and dataset DSNT.SDSNLOAD to be added to LLA |  | z/OS | not required for DSNT
8 | Perform DB2 refresh for Early code | /+DSNT REFRESH DB2,EARLY | DB2 | not required for DSNT
9 | Start DB2 in Access Maint | /+DSNT START DB2 ACCESS(MAINT) | DB2 | Complete
10 | Issue DISPLAY GROUP COMMAND | (-DISPLAY GROUP DETAIL) | DB2 | Complete
11 | Execute DSNTEJ1L and DSNTEJ2A | DSNT.NEW.SDSNSAMP.RSU2312 | DB2 | Complete
12 | Execute DSNTIJTM Job | DSNT.NEW.SDSNSAMP.RSU2312 | DB2 | Complete
13 | Execute DSNTIJCL Job | DSNT.NEW.SDSNSAMP.RSU2312 | DB2 | Complete
14 | Execute DSNTIJRT Job | DSNT.NEW.SDSNSAMP.RSU2312 | DB2 | Complete
15 | Execute DSNTIJSG Job | DSNT.NEW.SDSNSAMP.RSU2312 | DB2 | Complete
16 | Stop DB2 | /+DSNT STOP DB2 | DB2 | Complete

## Validation Plan
S.No | Validation Plan(PDB2 & DB2S) | Job/Command | Status
1 | Execute DSNTEJ0, DSNTEJ1, TESQ | DSNT.NEW.SDSNSAMP.RSU2312 | Complete
2 | Validate DB2 tools |  | Completed
send mail to application team to start their validation

## Validation Plan (DSNL)
S.No | Validation Plan(PDB2 & DB2S) | Job/Command | Status
1 | Execute DSNTEJ0, DSNTEJ1, TESQ | DSNL.NEW.SDSNSAMP.RSU2312 | Complete
2 | Validate DB2 tools |  | Complete
send mail to application team to start their validation

## Runtime Libraries - DSNT & DSNL
DSNT(Test) - Runtime Libraries | DSNL(Production)
DSNT.SDSNC.H | DSNL.SDSNC.H
DSNT.SDSNCLST | DSNL.SDSNCLST
DSNT.SDSNDBRM | DSNL.SDSNDBRM
DSNT.SDSNEXIT | DSNL.SDSNEXIT
DSNT.SDSNIVPD | DSNL.SDSNIVPD
DSNT.SDSNLINK | DSNL.SDSNLINK
DSNT.SDSNLOAD | DSNL.SDSNLOAD
DSNT.SDSNLOD2 | DSNL.SDSNLOD2
DSNT.SDSNMACS | DSNL.SDSNMACS
DSNT.SDSNPFPE | DSNL.SDSNPFPE
DSNT.SDSNSAMP | DSNL.SDSNSAMP
DSNT.SDSNSPFM | DSNL.SDSNSPFM
DSNT.SDSNSPFP | DSNL.SDSNSPFP
DSNT.SDSNSPFS | DSNL.SDSNSPFS
DSNT.SDSNSPFT | DSNL.SDSNSPFT
DSNT.SDXRRESL | DSNL.SDXRRESL
DSNT.RUNLIB.LOAD | DSNL.RUNLIB.LOAD