## Backout steps
FALLBACK Steps to DB2 V12 – DB2D
Important: Fallback is not supported after activation to Function Level 500 in DB2 V13.
Step | Activity | Remarks / Commands | Expected Outcome | Artifact to Capture | Steps Not Followed During Backout
1 | Stop DB2 V13 | Refer IBM Migration Guide p.570 | DB2 enters controlled shutdown sequence | Operator console logs
1.a | STOP DB2 MODE (QUIESCE) | /?STOP DB2 MODE(QUIESCE) | New work drained; DB2 quiesced | DB2 command output
1.b | START DB2 ACCESS (MAINT) | /?START DB2 ACCESS(MAINT) | DB2 in maintenance mode | DB2 command output
1.c | Verify DSNDB01 restrict state | DISPLAY DB(DSNDB01) SPACE(*) RESTRICT | No unexpected restrict states | Display output | Skipped
1.d | Verify DSNDB06 restrict state | DISPLAY DB(DSNDB06) SPACE(*) RESTRICT | No unexpected restrict states | Display output | Skipped
2 | Run DSNTIJFV | Rename cataloged procedures and reactivate DB2 V12 code (p.571) | Catalog procedures reverted to V12 | DSNTIJFV job log
2.a | Update DB2 PROCs | Rename DB2TN.SHR.DB2D.DSNLOAD → .BKUPV13; restore .BKUPV12 | V12 load libraries active | Dataset rename evidence
2.b | APF updates | Remove/add APF entries as required | Correct APF authorization | APF list snapshot
3 | Reconnect subsystems | Reconnect TSO, IMS, CICS (p.572) | Subsystems ready for DB2 V12 | Subsystem logs
3.a | Re-establish V12 procedures | Point procs to V12 libraries | Correct procedure resolution | Proc members
4 | Stop DB2 V13 | /?STOP DB2 | DB2 V13 fully stopped | DB2 stop messages
4.a | Start DB2 V12 | /?START DB2 | DB2 V12 started successfully | Startup messages
5 | Run DB2 V12 IVP jobs | DSNTEJxx validation (p.574) | V12 environment validated | Job outputs
5.a | DSNTEJ2A | DB2PN.DB2V12.DB2D.SDSNSAMP(DSNTEJ2A) | Basic DB2 validation successful | JES output | Skipped
5.b | DSNTEJ2C | DB2PN.DB2V12.DB2D.SDSNSAMP(DSNTEJ2C) | SQL and catalog checks pass | JES output | Skipped
5.c | DSNTEJ2D | DB2PN.DB2V12.DB2D.SDSNSAMP(DSNTEJ2D) | DB2 functions verified | JES output | Skipped
5.d | DSNTEJ2F | DB2PN.DB2V12.DB2D.SDSNSAMP(DSNTEJ2F) | Utilities validated | JES output | Skipped
5.e | DSNTEJ2P | Run step PH02PS05 only | Package bind verification | JES output | Skipped
6 | Test applications | Execute business validation tests | Applications function normally | Test results
7 | Retry failed scenario | Re-run failing workload | Issue reproduced or resolved | Incident evidence
FALLBACK Steps to DB2 V12 – TDB2
Step | Activity | Remarks / Commands | Expected Outcome | Artifact to Capture
1 | Stop DB2 V13 | Refer IBM Migration Guide p.570 | DB2 enters controlled shutdown | Operator console logs
1.a | STOP DB2 MODE (QUIESCE) | /=STOP DB2 MODE(QUIESCE) | New work drained | DB2 command output
1.b | START DB2 ACCESS (MAINT) | /=START DB2 ACCESS(MAINT) | Maintenance mode active | DB2 command output
1.c | Verify DSNDB01 restrict state | DISPLAY DB(DSNDB01) SPACE(*) RESTRICT | No unexpected restrict | Display output
1.d | Verify DSNDB06 restrict state | DISPLAY DB(DSNDB06) SPACE(*) RESTRICT | No unexpected restrict | Display output
2 | Run DSNTIJFV | Rename cataloged procedures (p.571) | V12 catalog procedures active | DSNTIJFV job log
2.a | Update DB2 PROCs | Rename DB2TN.SHR.DSNLOAD → .BKUPV13; restore .BKUPV12 | V12 load libraries active | Dataset rename evidence
2.b | APF updates | Adjust APF authorization | Correct APF configuration | APF snapshot
3 | Reconnect subsystems | Reconnect TSO, IMS, CICS | Subsystems operational | Logs
3.a | Re-establish V12 procedures | Point procs to V12 | Correct startup | Proc members
4 | Stop DB2 V13 | /=STOP DB2 | DB2 V13 stopped | Stop messages
4.a | Start DB2 V12 | /=START DB2 | DB2 V12 active | Startup messages
5 | Run DB2 V12 IVP jobs | DSNTEJxx (p.574) | Environment validated | Job outputs
5.a | DSNTEJ2A | DB2PN.DB2V12.TDB2.SDSNSAMP(DSNTEJ2A) | Validation success | JES output
5.b | DSNTEJ2C | DB2PN.DB2V12.TDB2.SDSNSAMP(DSNTEJ2C) | Validation success | JES output
5.c | DSNTEJ2D | DB2PN.DB2V12.TDB2.SDSNSAMP(DSNTEJ2D) | Validation success | JES output
5.d | DSNTEJ2F | DB2PN.DB2V12.TDB2.SDSNSAMP(DSNTEJ2F) | Validation success | JES output
5.e | DSNTEJ2P | Run step PH02PS05 only | Package validation | JES output
6 | Test applications | Execute validation tests | Applications stable | Test evidence
7 | Retry failed scenario | Re-run failing workload | Root cause confirmed | Incident record

## Fresh Migration Steps
Step | Activity | Remarks / Commands | Expected Outcome | Artifact to Capture
Pre-Migration Activities
1 | Activate function level 510 in DB2 V12 | -ACTIVATE FUNCTION LEVEL (V12R1M510) | Function level 510 active | Screenshot of -DIS GROUP DETAIL
2 | Copy V12 SDSNEXIT member to V13 SDSNEXIT dataset | Ensure correct HLQ | Exit members available in V13 | Dataset listing (ISPF 3.4)
3 | Copy V13 RESL members to V13 SDSNLOAD dataset | Common miss by SMEs | RESL modules present in SDSNLOAD | Dataset listing
4 | Run DSNTIJPM Pre-migration report | Resolve all findings | Report shows no blocking issues | DSNTIJPM output
5 | Verify APAR PH37108 applied | -DIS GROUP DETAIL | APAR applied successfully | Command output
6 | Checkpoint: Obtain a Full Image copy of v12 - Apps & Systems | Recommended before migration | Image copy completed | Job output
7 | Bring down dependent address spaces (CICS, allied tasks) | Stop all DB2-connected tasks | No active threads | CICS region log, DB2 thread list
8 | Bring down DB2 subsystem | -STOP DB2 MODE(QUIESCE) | DB2 stopped cleanly | JES log showing STOP completed
9 | Storage team performs volume-level backup | Full backup recommended | Backup completed | Storage backup report
10 | Run DSN1COPY CHECK for DSNDB01, DSNDB06 | Validate database integrity | No discrepancies found | DSN1COPY output
Migration Execution
11 | Start DB2 in maintenance mode | -START DB2 MODE(MAINT) | DB2 in MAINT mode | Command output
12 | Verify DB status, utilities, threads | -DIS DATABASE(*) | No pending utilities | Command output
13 | Run DSNTIJIC (Image Copy) | For catalog & directory | Image copy successful | Job output
14 | Run Check Data & Check Index | DSNDB01, DSNDB06 | No errors reported | Job output
15 | Run DSNTESQ | SQL schema validation | Validation successful | Job output
16 | Stop DB2 (quiesce) | Before APF/linklist updates, Quiesce will prevent abrupt stopping | DB2 stopped | JES log
17 | Update APF & Linklist | SDSNEXIT, SDSNLOAD, SDSNLOAD2, SDSNLINK APF AUTHORIZATION BEFORE SUBMITING THE JU* Job SERIES HAVE TO UPDATE THE LIBRARY DETAILS IN PARMLIB & LINKED LIST BELOW WHICH WILL BE PERFORMED BY ZOS TEAM. 1. APF AUTHORIZATION KINDLY REMOVE THE FOLLOWING LOAD LIBRARIES TO THE APF LIST TO ENSURE DB2 MODULES ARE EXECUTING CORRECTLY. DSN(**.SDSNLOAD) SMS DSN(**.SDSNLOD2) SMS DSN(**.SDSNEXIT) SMS TAKE A BACKUP OF ABOVE LIBS OR RENAME TO . V12. RENAME V13 LIBS TO ABOVE LIBS. IF REQUIRED TAKE BACK UP OF V13 LIBS. ENSURE SDSNSNEXIT MEMBERS ARE COPIED TO V13 LIBS. AND ALSO ENSUE MEMBERS OF SDXRRESL ARE COPIED TO SDSNLOAD. ALSO ENSURE SDSNEXIT COPIED FROM V12 TO V12 SDSNSEXIT Delete all dependant ALIAS ( LISTCAT ENT(/) ALL ) Rename the version 12 orginal dataset to .V12 Rename the version 13 dataset to orginal dataset Recreate the deleted dependant ALIAS | Libraries updated | PARMLIB/PROGxx listing
18 | Rename the old datasets from v12 to v13 | Take a backup of v12 libraries and copy v13 members in the existing v12 PDS Engage zOS SME to perform APF authorization
19 | Run DSNTIJUZ, DSNTIJUA, DSNTIJUM | Migration jobs | Jobs complete RC=0 | Job outputs
20 | Start DB2 in maintenance mode | Post APF update | DB2 started | JES log
21 | Run DSNTIJTC | Catalog migration | RC=0 | Job output
22 | Verify version status | -DIS GROUP DETAIL | Version shows V13 | Screenshot
23 | Run Check Data & Check Index again | DSNDB01, DSNDB06 | No errors | Job output
24 | Verify database object status | -DIS DATABASE(*) | All objects accessible | Command output
25 | Run DSNTIJTM | Migration job | RC=0 | Job output
26 | Run DSNTIJSG | Migration job | RC=0 | Job output
27 | Run DSNTIJRT | Migration job | RC=0 | Job output
28 | Run DSNTIJRV | Migration job - Optional | RC=0 | Job output
IVP & Post-Migration
29 | Run DSNTJ2A (IVP) | Installation verification | RC=0 | Job output
30 | Run DSNTEJ1L (IVP) | Installation verification | RC=0 | Job output
31 | Run DSNTESC | SQL compatibility check | RC=0 | Job output
32 | Run DSNTIJCL | IVP job | RC=0 | Job output
33 | Run DSNTIJLC | IVP job | RC=0 | Job output
34 | Run DSNTIJVR | IVP job | RC=0 | Job output
35 | Run DSNTIJIC | Final image copy | RC=0 | Job output
36 | Stop DB2 | Prepare for RW mode | DB2 stopped | JES log
37 | Start DB2 in normal RW mode | -START DB2 | DB2 active RW | Screenshot
38 | Run DSNTEJ1 (IVP) | Post-migration validation - Optional | RC=0 | Job output
39 | Run DSNTJ2C (IVP) | Post-migration validation - Optional | RC=0 | Job output
Recommended: Backup system physical objects
WLM validation - Need zOS team
-922 error - IMS and CICS related error
Staging plan as all changes should not be done during the change window
FALLBACK Steps to DB2 V12 DB2D
Fallback is not supported after activation to Function Level 500 in DB2 V13
1 | Stop DB2 V13 | P. 570
| a. STOP DB2 MODE (QUIESCE) | P. 570 | /?STOP DB2 MODE(QUIESCE)
| b. START DB2 ACCESS(MAINT) | P. 570 | /?START DB2 ACCESS(MAINT)
| c. DISPLAY DB(DSNDB01) SPACE(*) RESTRICT | P. 571
| d. DISPLAY DB(DSNDB06) SPACE(*) RESTRICT | P. 571
2 | Run job DSNTIJFV to rename cataloged procudures and reactivate DB2 V12 code | P. 571 | Rename DB2TN.SHR.DB2D.DSNLOAD to .DB2TN.SHR.DB2D.DSNLOAD.BKUPV13
| a. Point to / update DB2 PROCs | P. 571 | Rename DB2TN.SHR.DB2D.DSNLOAD.BKUPV12 to DB2TN.SHR.DB2D.DSNLOAD
| b. Perform APF deletions/updates for necessary load libraries | P. 571 | APF
3 | Reconnect TSO, IMS, and CICS | P. 572
| a. Re-establish your DB2 V12 procedures | P. 572
4 | Stop DB2 V13 | P. 572 | /?STOP DB2
| Start DB2 V12 | P. 572
| a. Start DB2 V12 after necessary updates | P. 572 | /?START DB2
5 | Run DB2 V12 installation verification jobs (DSNTEJxx) | P. 574
| a. DSNTEJ2A V12 | P. 574 | DB2PN.DB2V12.DB2D.SDSNSAMP(DSNTEJ2A)
| b. DSNTEJ2C | P. 574 | DB2PN.DB2V12.DB2D.SDSNSAMP(DSNTEJ2C)
| c. DSNTEJ2D | P. 574 | DB2PN.DB2V12.DB2D.SDSNSAMP(DSNTEJ2D)
| e. DSNTEJ2F | P. 574 | DB2PN.DB2V12.DB2D.SDSNSAMP(DSNTEJ2F)
| f. DSNTEJ2P (run only step PH02PS05) | P. 574 | DB2PN.DB2V12.DB2D.SDSNSAMP(DSNTEJ2P) STEP PH02PS05
| g. Test applications | P. 574
| h. Retry the problem for which caused to necessitate fallback | P. 574
FALLBACK Steps to DB2 V12 TDB2
Fallback is not supported after activation to Function Level 500 in DB2 V13
1 | Stop DB2 V13 | P. 570
| a. STOP DB2 MODE (QUIESCE) | P. 570 | /=STOP DB2 MODE(QUIESCE)
| b. START DB2 ACCESS(MAINT) | P. 570 | /=START DB2 ACCESS(MAINT)
| c. DISPLAY DB(DSNDB01) SPACE(*) RESTRICT | P. 571
| d. DISPLAY DB(DSNDB06) SPACE(*) RESTRICT | P. 571
2 | Run job DSNTIJFV to rename cataloged procudures and reactivate DB2 V12 code | P. 571 | Rename DB2TN.SHR.DSNLOAD to DB2TN.SHR.DSNLOAD.BKUPV13
| a. Point to / update DB2 PROCs | P. 571 | Rename DB2TN.SHR.DSNLOAD.BKUPV12 to DB2TN.SHR.DSNLOAD
| b. Perform APF deletions/updates for necessary load libraries | P. 571 | APF
3 | Reconnect TSO, IMS, and CICS | P. 572
| a. Re-establish your DB2 V12 procedures | P. 572
4 | Stop DB2 V13 | P. 572 | /=STOP DB2
| Start DB2 V12 | P. 572
| a. Start DB2 V12 after necessary updates | P. 572 | /=START DB2
5 | Run DB2 V12 installation verification jobs (DSNTEJxx) | P. 574
| a. DSNTEJ2A V12 | P. 574 | DB2PN.DB2V12.TDB2.SDSNSAMP (DSNTEJ2A)
| b. DSNTEJ2C | P. 574 | DB2PN.DB2V12.TDB2.SDSNSAMP (DSNTEJ2C)
| c. DSNTEJ2D | P. 574 | DB2PN.DB2V12.TDB2.SDSNSAMP (DSNTEJ2D
| e. DSNTEJ2F | P. 574 | DB2PN.DB2V12.TDB2.SDSNSAMP (DSNTEJ2F)
| f. DSNTEJ2P (run only step PH02PS05) | P. 574 | DB2PN.DB2V12.TDB2.SDSNSAMP (DSNTEJ2P) STEP PH02PS05
| g. Test applications | P. 574
| h. Retry the problem for which caused to necessitate fallback | P. 574
| Remigration after Fallback (DB2D) |  |  | IBM Migration Guide P. 576
To remigrate your subsystem to Db2 13:
1. Check the integrity of your Db2 12 catalog and directory:
| • Run the DSN1COPY utility with the CHECK option on your catalog table spaces. |  | IBM Migration P. 576 | DB2PN.DB2V12.DB2D.SDSNSAMP(DSN1COPY) | c 4 | 5 m
| • Run the CHECK DATA utility on DB2 Catalog & Directory Tablespaces |  |  | DB2PN.DB2V12.DB2D.SDSNSAMP(CKCKDATA) | c 0 | 3 m
| • Run the queries in member DSNTESQ of prefix.SDSNSAMP. |  |  | DB2PN.DB2V12.DB2D.SDSNSAMP(DSNTESQ) | c 0 | 1 m
| 2. Optional: Use DSNTIJIC to take an image copy of your Db2 12 catalog. |  |  | DB2PN.DB2V12.DB2D.SDSNSAMP(DSNTIJIC) | c 0 | 9 m
This step is not required, but it is recommended.
| 3. Stop Db2 12. |  |  | /?STOP DB2
| 4. Reconnect TSO, IMS, and CICS to Db2. |  |  | Prepare CICS & IMS (if applicable)
| Re-establish your Db2 13 logon procedures and JCL, as well as your Db2 13 CICS and IMS |  |  | Prepare (if applicable)
connections.
| 5. Rebuild Db2 13 cataloged procedures. |  |  | Rename DB2TN.SHR.DB2D.DSNLOAD to DB2TN.SHR.DB2D.DSNLOAD.BKUPV12 & APF | STN249
| Rename the Db2 13 procedures that were renamed by job DSNTIJFV during fallback. If job DSNTIJFV |  |  | Rename DB2TN.SHR.DB2D.DSNLOAD.DB2V13 to DB2TN.SHR.DB2D.DSNLOAD | STN252
| was not run, you need to rerun jobs DSNTIJMP, DSNTIJMV, and DSNTIJMW. |  |  | DB2TN.DB2V13.DB2D.NEW.SDSNSAMP(DSNTIJM*) & APF
| 6. Start Db2 13. Ensure that you are using your Db2 13 subsystem parameter load module. |  |  | /?START DB2
Tip: If you issued the ACTIVATE command after falling back to Db2 12, Db2 13 might issue reason
| code 00C900A6 after you remigrate. To resolve this situation, run the CATMAINT utility and specify |  |  | DB2TN.DB2V13.DB2D.NEW.SDSNSAMP(DSNTIJTC)
LEVEL V13R1M100. You can use the DSNTIJTC migration job.
| 7. Take an image copy of the Db2 13 catalog by using the DSNTIJIC job. |  |  | DB2TN.DB2V13.DB2D.NEW.SDSNSAMP(DSNTIJIC)
| 8. Verify your Db2 13 system. |  |  | Verify & App Teams Verify
| Remigration after Fallback (TDB2) |  |  | IBM Migration Guide P. 576
To remigrate your subsystem to Db2 13:
1. Check the integrity of your Db2 12 catalog and directory:
| • Run the DSN1COPY utility with the CHECK option on your catalog table spaces. |  | IBM Migration P. 576 | DB2PN.DB2V12.TDB2.SDSNSAMP (DSN1COPY) | c 4 | 3 m
| • Run the CHECK DATA utility on DB2 Catalog & Directory Tablespaces |  |  | DB2PN.DB2V12.TDB2.SDSNSAMP (CHCKDATA) | c 0 | 9 m
| • Run the queries in member DSNTESQ of prefix.SDSNSAMP. |  |  | DB2PN.DB2V12.TDB2.SDSNSAMP (DSNTESQ) | c 0 | 2 m
| 2. Optional: Use DSNTIJIC to take an image copy of your Db2 12 catalog. |  |  | DB2PN.DB2V12.TDB2.SDSNSAMP (DSNTIJIC) | C 0 | 15 m
This step is not required, but it is recommended.
| 3. Stop Db2 12. |  |  | /=STOP DB2
| 4. Reconnect TSO, IMS, and CICS to Db2. |  |  | Prepare CICS & IMS (if applicable)
| Re-establish your Db2 13 logon procedures and JCL, as well as your Db2 13 CICS and IMS |  |  | Prepare (if applicable)
connections.
| 5. Rebuild Db2 13 cataloged procedures. |  |  | Rename DB2TN.SHR.DSNLOAD to DB2TN.SHR.DSNLOAD.BKUPV12 | STN254
| Rename the Db2 13 procedures that were renamed by job DSNTIJFV during fallback. If job DSNTIJFV |  |  | Rename DB2TN.SHR.DSNLOAD.DB2V13 to DB2TN.SHR.DSNLOAD | STN270
| was not run, you need to rerun jobs DSNTIJMP, DSNTIJMV, and DSNTIJMW. |  |  | DB2TN.DB2V13.TDB2.NEW.SDSNSAMP(DSNTIJM*)
| 6. Start Db2 13. Ensure that you are using your Db2 13 subsystem parameter load module. |  |  | /=START DB2
Tip: If you issued the ACTIVATE command after falling back to Db2 12, Db2 13 might issue reason
| code 00C900A6 after you remigrate. To resolve this situation, run the CATMAINT utility and specify |  |  | DB2TN.DB2V13.TDB2.NEW.SDSNSAMP(DSNTIJTC)
LEVEL V13R1M100. You can use the DSNTIJTC migration job.
| 7. Take an image copy of the Db2 13 catalog by using the DSNTIJIC job. |  |  | DB2TN.DB2V13.TDB2.NEW.SDSNSAMP(DSNTIJIC)
| 8. Verify your Db2 13 system. |  |  | Verify & App Teams Verify

## Detailed Remigration steps_Kim
Use the Fresh SMP/E setup and Fresh Target Libraries used in TSYS
Re-migration after Fallback (TDB2)
Step | Activity | Remarks / Commands | Expected Outcome | Artifact to Capture |  | Owner | Duration: Start at 1 PM CST
Pre-Re-migration Activities
0 |  | Delete all modules from DB2TN.SHR.DSNLOAD.DB2V13 DB2PN.DB2V13.TDB2.NEW.SDSNSAMP(DELETMBR) | Delete successful | Screen shot |  | DB2
0.1 | DB2TN.TSYS.DB2V13.SDSNBASE | Copy into DB2TN.SHR.TDB2.SDSNBASE.DB2V13 | 20 members | Screen shot |  | DB2
0.2 | DB2TN.TSYS.DB2V13.SDSNC.H | Copy into DB2TN.SHR.TDB2.SDSNC.H.DB2V13 | 21 members | Screen shot |  | DB2
0.3 | DB2TN.TSYS.DB2V13.SDSNCLST | Copy into DB2TN.SHR.TDB2.SDSNCLST.DB2V13 | 50 members | Screen shot |  | DB2
0.4 | DB2TN.TSYS.DB2V13.SDSNDBRM | Copy into DB2TN.SHR.TDB2.SDSNDBRM.DB2V13 | 246 members | Screen shot |  | DB2
0.5 | DB2TN.TSYS.DB2V13.SDSNEXIT | Copy into DB2TN.SHR.DSNLOAD.DB2V13 | 10 modules | Screen shot |  | DB2
0.6 | DB2TN.TSYS.DB2V13.SDSNIVPD | Copy into DB2TN.SHR.DSNLOAD.DB2V13 | 81 modules | Screen shot |  | DB2
0.7 | DB2TN.TSYS.DB2V13.SDSNLINK | Copy into DB2TN.SHR.DSNLOAD.DB2V13 | 4 modules | Screen shot |  | DB2
0.8 | DB2TN.TSYS.DB2V13.SDSNLOAD | Copy into DB2TN.SHR.DSNLOAD.DB2V13 | 530 modules | Screen shot |  | DB2
0.9 | DB2TN.TSYS.DB2V13.SDSNLOD2 | Copy into DB2TN.SHR.DSNLOAD.DB2V13 | 23 members | Screen shot |  | DB2
0.X | DB2TN.TSYS.DB2V13.SDSNMACS | Copy into DB2TN.SHR.TDB2.SDSNMACS.DB2V13 | 134 members | Screen shot |  | DB2
0.X1 | DB2TN.TSYS.DB2V13.SDSNPFPE | Copy into DB2TN.SHR.TDB2.SDSNPFPE.DB2V13 | 51 members | Screen shot |  | DB2
0.X2 | DB2TN.TSYS.DB2V13.SDSNPFPK | Copy into DB2TN.SHR.TDB2.SDSNPFPK.DB2V13 | 0 members | Screen shot |  | DB2
0.X3 | DB2TN.TSYS.DB2V13.SDSNSAMP | Copy into DB2TN.SHR.TDB2.SDSNSAMP.DB2V13 | 862 members | Screen shot |  | DB2
0.X4 | DB2TN.TSYS.DB2V13.SDSNSPFM | Copy into DB2TN.SHR.TDB2.SDSNSPFM.DB2V13 | 43 members | Screen shot |  | DB2
0.X5 | DB2TN.TSYS.DB2V13.SDSNSPFP | Copy into DB2TN.SHR.TDB2.SDSNSPFP.DB2V13 | 108 members | Screen shot |  | DB2
0.X6 | DB2TN.TSYS.DB2V13.SDSNSPFS | Copy into DB2TN.SHR.TDB2.SDSNSPFS.DB2V13 | 1 member | Screen shot |  | DB2
0.X7 | DB2TN.TSYS.DB2V13.SDSNSPFT | Copy into DB2TN.SHR.DB2D.SDSNSPFTY.DB2V13 | 2 members | Screen shot |  | DB2
0.X8 | DB2TN.TSYS.DB2V13.SDXRRESL | Copy into DB2TN.SHR.DSNLOAD.DB2V13 | 12 members | Screen shot |  | DB2
DB2
1 | Validate Db2 12 catalog integrity (DSN1COPY) | Run DSN1COPY CHECK on catalog table spacesLibrary: DB2PN.DB2V12.TDB2.SDSNSAMP(DSN1COPY) | Catalog integrity verified | DSN1COPY job output |  | DB2 | start
2 | Run CHECK DATA on catalog & directory | Execute CHECK DATA on Db2 catalog and directory table spacesLibrary: DB2PN.DB2V12.TDB2.SDSNSAMP(CHCKDATA) or site-specific CHCKDATA job | No CHECK DATA errors | Job output |  | DB2
3 | Execute DSNTESQ validation queries | Run validation queriesLibrary: DB2PN.DB2V12.TDB2.SDSNSAMP(DSNTESQ) | No blocking issues identified | Query output |  | DB2
4 | Take image copy of Db2 12 catalog (Optional but recommended) | Run catalog image copyLibrary: DB2PN.DB2V12.TDB2.SDSNSAMP(DSNTIJIC) | Db2 12 catalog image copy completed | Job output |  | DB2
5 | Validate BSDS and log chain continuity | Run DSNJU003 to validate BSDS and log ranges DB2PN.DB2V12.TDB2.SDSNSAMP(BSDSUPDT) | BSDS and log chain consistent | DSNJU003 output | Jobs? Is this even needed since we've already been to V13 and did Fallback? | DB2
6 | Verify IRLM and WLM compatibility | Confirm IRLM level and WLM service class definitions meet Db2 13 requirements | No compatibility issues | IRLM / WLM validation report | Shouldn't be different than V12 | DB2
7.1 | Prepare DSNZPARM for Db2 13 | Assemble and link-edit Db2 13 DSNZPARMJob: DSNTIJUZ DB2PN.DB2V13.TDB2.NEW.SDSNSAMP(DSNTIJUZ) DB2TN.DB2V13.TDB2.NEW.SDSNSAMP(DSNTIJUZ) DB2TN.SHR.SDSNSAMP.DB2V13(DSNTIJUZ) | Db2 13 DSNZPARM load module built | DSNTIJUZ output & compare report | Compare with current V12 and previous V13 DSNTIJUZ | DB2
7.2 | Prepare DSNHDECP | DSNHDECP Updates DB2PN.DB2V13.TDB2.NEW.SDSNSAMP(DSNTIJUA) DB2TN.SHR.SDSNSAMP.DB2V13(DSNTIJUA) | CC 0 or CC 4 |  |  | DB2
7.3 | Prepare DSNHMCID | DSNHMCID Updates DB2TN.DB2V13.TDB2.NEW.SDSNSAMP(DSNTIJUM) DB2PN.DB2V13.TDB2.NEW.SDSNSAMP(DSNTIJUM) DB2TN.SHR.SDSNSAMP.DB2V13(DSNTIJUM) | CC 0 or CC 4 |  |  | DB2
8 | Validate APF, LINKLIST, and STEPLIB concatenations | Confirm Db2 13 load libraries are APF-authorized and no stale Db2 12 libraries remain | Correct library chain established | APF list and STEPLIB verification | Do this after stopping TDB2 and renaming datasets | Engage Operator, zOS - Arthur / Srini | 30 minutes
9 | Confirm SMP/E maintenance for Db2 13 | Verify required Db2 13 PTFs and migration maintenance are applied | Maintenance prerequisites met | SMP/E APPLY / ACCEPT logs | Previously done. Is this even needed since we've already been to V13 and did Fallback | DB2
10 | Review DDF configuration | Validate ports, SECMEC, authentication, and restart approach | DDF configuration ready | DDF parms & TCP/IP configuration |  | DB2
Re-migration Execution
11 | Stop Db2 12 subsystem | Issue =STOP DB2 for TDB2 | Db2 12 stopped cleanly | JES log |  | Operators involved - to bring down all | 1 Hour
12 | Prepare TSO, IMS, and CICS connectivity | Prepare Db2 13 logon procedures, JCL, and attachment plans (no activation yet) | Connectivity preparation complete | Procedure / JCL listings |  | zOS - Arthur / Srini
13 | Rebuild Db2 13 cataloged procedures | If DSNTIJFV not run after fallback, execute:DSNTIJMP, DSNTIJMV, DSNTIJMWLibrary: DB2TN.DB2V13.TDB2.NEW.SDSNSAMP(DSNTIJM*) | Db2 13 procedures rebuilt | Job output | Rename libs instead | DB2
14 | Run post-migration enablement jobs (if required) | Execute as applicable:DSNTIJPM, DSNTIJEN, DSNTIJSG DB2TN.SHR.SDSNSAMP.DB2V13 | Post-migration enablement completed | Job outputs | Not needed for ReMigration | DB2
15 | Start Db2 13 subsystem | Issue =START DB2 using Db2 13 parameter load module | Db2 13 started successfully | Command output |  | DB2
16 | Resolve ACTIVATE fallback condition (if encountered) | If reason code 00C900A6, run CATMAINT LEVEL V13R1M100Job: DSNTIJTCLibrary: DB2TN.DB2V13.TDB2.NEW.SDSNSAMP(DSNTIJTC) DB2TN.SHR.SDSNSAMP.DB2V13 | Catalog maintenance completed | Job output |  | DB2
17 | Verify catalog restriction state | Issue -DISPLAY DATABASE(*) RESTRICT and validate DSNDB01 / DSNDB06 | Catalog unrestricted | Command output |  | DB2
18 | ACTIVATE Db2 13 function level | Issue -ACTIVATE FUNCTION LEVEL (V13R1Mxxx) per enterprise standard | Target function level active | Command output | Not yet? Comes in at V13R1M100 | DB2
19 | REBIND critical system and application packages | Rebind packages with appropriate APPLCOMPAT for Db2 13 | Packages valid and stable | REBIND job outputs | Not yet? | DB2
20 | Take image copy of Db2 13 catalog | Run catalog image copyLibrary: DB2TN.DB2V13.TDB2.NEW.SDSNSAMP(DSNTIJIC) DB2TN.SHR.SDSNSAMP.DB2V13(DSNTIJM*) | Db2 13 catalog image copy completed | Job output |  | DB2
21 | RUNSTATS on catalog objects | Execute DSNTIJRT or tailored RUNSTATS jobs DB2TN.SHR.SDSNSAMP.DB2V13(RUNSTATS) DB2TN.SHR.SDSNSAMP.DB2V13(RUNSTATS) | Stable access paths | Job output |  | DB2
22 | Stop / Start DDF and validate clients |  | DB2TN.DB2V13.TDB2.NEW.SDSNSAMP(DSNTIJIC) | Test logs | Why? | DB2
Post-Re-migration Validation | [5 empty] | DB2
23 | Verify Db2 13 subsystem health | Validate catalog, directory, utilities, and application connectivity | Db2 13 validated | Verification checklist |  | DB2 | 30 minutes
24 | Enable IFCID / SMF tracing | Start accounting and performance traces | Observability enabled | Trace activation logs | Jobs? | DB2
25 | Capture post-migration performance baseline | Capture buffer hit ratios, CPU, storage, top SQLs | Baseline established | Performance report |  | DB2
26 | Confirm fallback readiness | Retain Db2 12 load libraries and image copies for emergency backout | Controlled fallback possible | Retention checklist |  | DB2

## Detailed Remigration steps D,T
Use the Fresh SMP/E setup and Fresh Target Libraries used in TSYS
Re-migration after Fallback (TDB2)
Step | Activity | Remarks / Commands | Expected Outcome | Artifact to Capture
Pre-Re-migration Activities
1 | Validate Db2 12 catalog integrity (DSN1COPY) | Run DSN1COPY CHECK on catalog table spacesLibrary: DB2PN.DB2V12.TDB2.SDSNSAMP(DSN1COPY) | Catalog integrity verified | DSN1COPY job output
2 | Run CHECK DATA on catalog & directory | Execute CHECK DATA on Db2 catalog and directory table spacesLibrary: DB2PN.DB2V12.TDB2.SDSNSAMP(DSNTIJCD) or site-specific CHCKDATA job | No CHECK DATA errors | Job output
3 | Execute DSNTESQ validation queries | Run validation queriesLibrary: DB2PN.DB2V12.TDB2.SDSNSAMP(DSNTESQ) | No blocking issues identified | Query output
4 | Take image copy of Db2 12 catalog (Optional but recommended) | Run catalog image copyLibrary: DB2PN.DB2V12.TDB2.SDSNSAMP(DSNTIJIC) | Db2 12 catalog image copy completed | Job output
5 | Validate BSDS and log chain continuity | Run DSNJU003 to validate BSDS and log ranges | BSDS and log chain consistent | DSNJU003 output
6 | Verify IRLM and WLM compatibility | Confirm IRLM level and WLM service class definitions meet Db2 13 requirements | No compatibility issues | IRLM / WLM validation report
7 | Prepare DSNZPARM for Db2 13 | Assemble and link-edit Db2 13 DSNZPARMJob: DSNTIJUZ | Db2 13 DSNZPARM load module built | DSNTIJUZ output & compare report
8 | Validate APF, LINKLIST, and STEPLIB concatenations | Confirm Db2 13 load libraries are APF-authorized and no stale Db2 12 libraries remain | Correct library chain established | APF list and STEPLIB verification
9 | Confirm SMP/E maintenance for Db2 13 | Verify required Db2 13 PTFs and migration maintenance are applied | Maintenance prerequisites met | SMP/E APPLY / ACCEPT logs
10 | Review DDF configuration | Validate ports, SECMEC, authentication, and restart approach | DDF configuration ready | DDF parms & TCP/IP configuration
Re-migration Execution
11 | Stop Db2 12 subsystem | Issue -STOP DB2 for TDB2 | Db2 12 stopped cleanly | JES log
12 | Prepare TSO, IMS, and CICS connectivity | Prepare Db2 13 logon procedures, JCL, and attachment plans (no activation yet) | Connectivity preparation complete | Procedure / JCL listings
13 | Rebuild Db2 13 cataloged procedures | If DSNTIJFV not run after fallback, execute:DSNTIJMP, DSNTIJMV, DSNTIJMWLibrary: DB2TN.DB2V13.TDB2.NEW.SDSNSAMP(DSNTIJM*) | Db2 13 procedures rebuilt | Job output
14 | Run post-migration enablement jobs (if required) | Execute as applicable:DSNTIJPM, DSNTIJEN, DSNTIJSG | Post-migration enablement completed | Job outputs
15 | Start Db2 13 subsystem | Issue -START DB2 using Db2 13 parameter load module | Db2 13 started successfully | Command output
16 | Resolve ACTIVATE fallback condition (if encountered) | If reason code 00C900A6, run CATMAINT LEVEL V13R1M100Job: DSNTIJTCLibrary: DB2TN.DB2V13.TDB2.NEW.SDSNSAMP(DSNTIJTC) | Catalog maintenance completed | Job output
17 | Verify catalog restriction state | Issue -DISPLAY DATABASE(*) RESTRICT and validate DSNDB01 / DSNDB06 | Catalog unrestricted | Command output
18 | ACTIVATE Db2 13 function level | Issue -ACTIVATE FUNCTION LEVEL (V13R1Mxxx) per enterprise standard | Target function level active | Command output
19 | REBIND critical system and application packages | Rebind packages with appropriate APPLCOMPAT for Db2 13 | Packages valid and stable | REBIND job outputs
20 | Take image copy of Db2 13 catalog | Run catalog image copyLibrary: DB2TN.DB2V13.TDB2.NEW.SDSNSAMP(DSNTIJIC) | Db2 13 catalog image copy completed | Job output
21 | RUNSTATS on catalog objects | Execute DSNTIJRT or tailored RUNSTATS jobs | Stable access paths | Job output
22 | Stop / Start DDF and validate clients | Issue -STOP DDF / -START DDF and validate IMS, CICS, z/OS Connect | Distributed connectivity verified | Test logs
Post-Re-migration Validation
23 | Verify Db2 13 subsystem health | Validate catalog, directory, utilities, and application connectivity | Db2 13 validated | Verification checklist
24 | Enable IFCID / SMF tracing | Start accounting and performance traces | Observability enabled | Trace activation logs
25 | Capture post-migration performance baseline | Capture buffer hit ratios, CPU, storage, top SQLs | Baseline established | Performance report
26 | Confirm fallback readiness | Retain Db2 12 load libraries and image copies for emergency backout | Controlled fallback possible | Retention checklist
Re-migration after Fallback (DB2D)
Step | Activity | Remarks / Commands | Expected Outcome | Artifact to Capture
Pre-Re-migration Activities
1 | Validate Db2 12 catalog integrity (DSN1COPY) | Run DSN1COPY CHECK on catalog table spacesLibrary: DB2PN.DB2V12.DB2D.SDSNSAMP(DSN1COPY) | Catalog integrity verified | DSN1COPY job output
2 | Run CHECK DATA on catalog & directory | Execute CHECK DATA on Db2 catalog and directory table spacesLibrary: DB2PN.DB2V12.DB2D.SDSNSAMP(DSNTIJCD) or site CHCKDATA job | No CHECK DATA errors | Job output
3 | Execute DSNTESQ validation queries | Run validation queriesLibrary: DB2PN.DB2V12.DB2D.SDSNSAMP(DSNTESQ) | No blocking issues identified | Query output
4 | Take image copy of Db2 12 catalog (Optional but recommended) | Run catalog image copyLibrary: DB2PN.DB2V12.DB2D.SDSNSAMP(DSNTIJIC) | Db2 12 catalog image copy completed | Job output
5 | Validate BSDS and log chain continuity | Run DSNJU003 to validate BSDS and log ranges | BSDS and log chain consistent | DSNJU003 output | Didn't do
6 | Verify IRLM and WLM compatibility | Confirm IRLM level and WLM service class definitions meet Db2 13 requirements | No compatibility issues | IRLM / WLM validation report | Didn't do
7 | Prepare DSNZPARM for Db2 13 | Assemble and link-edit Db2 13 DSNZPARMJob: DSNTIJUZ | Db2 13 DSNZPARM load module built | DSNTIJUZ output & compare report
8 | Validate APF, LINKLIST, and STEPLIB concatenations | Confirm Db2 13 load libraries are APF-authorized and no stale Db2 12 libraries remain | Correct library chain established | APF list and STEPLIB verification
9 | Confirm SMP/E maintenance for Db2 13 | Verify required Db2 13 PTFs and migration maintenance are applied | Maintenance prerequisites met | SMP/E APPLY / ACCEPT logs | Did later
10 | Review DDF configuration | Validate ports, SECMEC, authentication, and restart approach | DDF configuration ready | DDF parms & TCP/IP configuration
Re-migration Execution
11 | Stop Db2 12 subsystem | Issue -STOP DB2 for DB2D | Db2 12 stopped cleanly | JES log
12 | Prepare TSO, IMS, and CICS connectivity | Prepare Db2 13 logon procedures, JCL, and attachment plans (no activation yet) | Connectivity preparation complete | Procedure / JCL listings
13 | Rebuild Db2 13 cataloged procedures | If DSNTIJFV not run after fallback, execute:DSNTIJMP, DSNTIJMV, DSNTIJMWLibrary: DB2TN.DB2V13.DB2D.NEW.SDSNSAMP(DSNTIJM*) | Db2 13 procedures rebuilt | Job output
14 | Run post-migration enablement jobs (if required) | Execute as applicable:DSNTIJPM, DSNTIJEN, DSNTIJSG | Post-migration enablement completed | Job outputs | Didn't do
15 | Start Db2 13 subsystem | Issue -START DB2 using Db2 13 parameter load module | Db2 13 started successfully | Command output
16 | Resolve ACTIVATE fallback condition (if encountered) | If reason code 00C900A6, run CATMAINT LEVEL V13R1M100Job: DSNTIJTCLibrary: DB2TN.DB2V13.DB2D.NEW.SDSNSAMP(DSNTIJTC) | Catalog maintenance completed | Job output | Didn't get
17 | Verify catalog restriction state | Issue -DISPLAY DATABASE(*) RESTRICT and validate DSNDB01 / DSNDB06 | Catalog unrestricted | Command output | Didn't get that far
18 | ACTIVATE Db2 13 function level | Issue -ACTIVATE FUNCTION LEVEL (V13R1Mxxx) per enterprise standard | Target function level active | Command output | Didn't get that far
19 | REBIND critical system and application packages | Rebind packages with appropriate APPLCOMPAT for Db2 13 | Packages valid and stable | REBIND job outputs | Didn't get that far
20 | Take image copy of Db2 13 catalog | Run catalog image copyLibrary: DB2TN.DB2V13.DB2D.NEW.SDSNSAMP(DSNTIJIC) | Db2 13 catalog image copy completed | Job output | Successful
21 | RUNSTATS on catalog objects | Execute DSNTIJRT or tailored RUNSTATS jobs | Stable access paths | Job output | Not yet
22 | Stop / Start DDF and validate clients | Issue -STOP DDF / -START DDF and validate IMS, CICS, z/OS Connect | Distributed connectivity verified | Test logs | Partial
Post-Re-migration Validation
23 | Verify Db2 13 subsystem health | Validate catalog, directory, utilities, and application connectivity | Db2 13 validated | Verification checklist
24 | Enable IFCID / SMF tracing | Start accounting and performance traces | Observability enabled | Trace activation logs
25 | Capture post-migration performance baseline | Capture buffer hit ratios, CPU, storage, top SQLs | Baseline established | Performance report
26 | Confirm fallback readiness | Retain Db2 12 load libraries and image copies for emergency backout | Controlled fallback possible | Retention checklist

## Job Sequence (hidden)
sequence
DSN01JPM
DSN02JIC
DSN03STO
DSN04DPY
DSN05DPY
DSN06DPY
DSN07DPY
DSN08DPY
DSN09DPY
DSN10DPY
DSN11DPY
DSN12DPY
DSN13DPY
DSN14DPY
DSN15DPY
DSN16STA
DSN17CMD
DSN18CHD
DSN19CHD
DSN20CHD
DSN21CHD
DSN22CHD
DSN23CHD
DSN24CHD
DSN25JCX
DSN26JCX
DSN27JCX
DSN28JCX
DSN29JCX
DSN30JCX
DSN31JCX
DSN32ESQ
DSN33JIC
DSN34STO
DSN3SADR
DSN3540S
DSN355AL
DSN36RE1
DSN36RE2
DSN36YAL
DSN36ZOS
DSN37JUZ
DSN38JUA
DSN39JUM
DSN40STA
DSN41JTC
DSN42JIC
DSN43CHD
DSN44CHD
DSN45CHD
DSN46CHD
DSN47CHD
DSN48CHD
DSN49CHD
DSN50JCX
DSN51JCX
DSN52JCX
DSN53JCX
DSN54JCX
DSN55JCX
DSN56JCX
DSN57CMD
DSN59JSG
DSN60JRT
DSN61JRV
DSN62WLM
DSN63J2A
DSN64J1L
DSN65ESC
DSN66JCL
DSN67JLC
DSNG8JVR
DSN69JIC
DSN70STO
DSN71STA
DSN72J2C
DSN73J2D
DSN74J2E
DSN75J2F
DSN76J2P
PDB2BIND
REPORT
SAMP

## Detailed Backout steps for D,T
FALLBACK Steps to DB2 V12 – DB2D
Step | Activity | Remarks / Commands | Expected Outcome | Artifact to Capture
1 | Stop Db2 13 | Refer IBM Db2 13 Migration Guide (Fallback section, p.570) | Db2 enters controlled shutdown sequence | Operator console logs
1.a | STOP DB2 MODE (QUIESCE) | -STOP DB2 MODE(QUIESCE) | New work drained; Db2 quiesced | Db2 command output
1.b | START DB2 ACCESS (MAINT) | -START DB2 ACCESS(MAINT) | Db2 in maintenance mode | Db2 command output
1.c | Verify DSNDB01 restrict state | -DISPLAY DB(DSNDB01) SPACE(*) RESTRICT | No unexpected restrict states | Display output
1.d | Verify DSNDB06 restrict state | -DISPLAY DB(DSNDB06) SPACE(*) RESTRICT | No unexpected restrict states | Display output
1.e | Verify no utilities running | -DISPLAY UTILITY(*) | No active utilities | Display output
2 | Run DSNTIJFV | Rename cataloged procedures and reactivate Db2 V12 code (p.571) | Catalog procedures reverted to V12 | DSNTIJFV job log
2.a | Update DB2 PROCs | Rename DB2TN.SHR.DB2D.DSNLOAD → .BKUPV13; restore .BKUPV12 | V12 load libraries active | Dataset rename evidence
2.b | APF updates | Remove/add APF entries for restored V12 libraries | Correct APF authorization | APF list snapshot
2.c | Validate STEPLIB/LINKLIST | Confirm no V13 libraries remain in concatenation | Clean V12 library chain | STEPLIB/LINKLIST listing
3 | Reconnect subsystems | Reconnect TSO, IMS, CICS (p.572) | Subsystems ready for Db2 V12 | Subsystem logs
3.a | Re-establish V12 procedures | Point procs to V12 libraries | Correct procedure resolution | Proc members
4 | Stop Db2 13 (final) | -STOP DB2 | Db2 13 fully stopped | Db2 stop messages
4.a | Start Db2 12 | -START DB2 | Db2 12 started successfully | Startup messages
4.b | Verify Db2 12 status | -DISPLAY DB2-DISPLAY GROUP DETAIL | Db2 12 active and stable | Display output
5 | Run Db2 V12 IVP jobs | DSNTEJxx validation (p.574) | V12 environment validated | Job outputs
5.a | DSNTEJ2A | DB2PN.DB2V12.DB2D.SDSNSAMP(DSNTEJ2A) | Basic Db2 validation successful | JES output
5.b | DSNTEJ2C | DB2PN.DB2V12.DB2D.SDSNSAMP(DSNTEJ2C) | SQL and catalog checks pass | JES output
5.c | DSNTEJ2D | DB2PN.DB2V12.DB2D.SDSNSAMP(DSNTEJ2D) | Db2 functions verified | JES output
5.d | DSNTEJ2F | DB2PN.DB2V12.DB2D.SDSNSAMP(DSNTEJ2F) | Utilities validated | JES output
5.e | DSNTEJ2P | Run step PH02PS05 only | Package bind verification | JES output
6 | Validate DDF status | -DISPLAY DDF-START DDF (if required) | DDF active on Db2 12 | Command output
7 | Rebind critical packages (if needed) | Rebind packages impacted by fallback | Packages usable on V12 | REBIND job output
8 | Test applications | Execute business and technical validation tests | Applications function normally | Test results
9 | Capture fallback baseline | Capture logs, buffer pools, and KPIs | Baseline preserved | Performance snapshot
10 | Retry failed scenario | Re-run failing workload | Issue reproduced or resolved | Incident evidence
FALLBACK Steps to DB2 V12 – TDB2
Step | Activity | Remarks / Commands | Expected Outcome | Artifact to Capture
1 | Stop DB2 V13 | Refer IBM Migration Guide p.570 | Db2 enters controlled shutdown | Operator console logs
1.a | STOP DB2 MODE (QUIESCE) | /=STOP DB2 MODE(QUIESCE) | New work drained; Db2 quiesced | Db2 command output
1.b | START DB2 ACCESS (MAINT) | /=START DB2 ACCESS(MAINT) | Db2 in maintenance mode | Db2 command output
1.c | Verify DSNDB01 restrict state | DISPLAY DB(DSNDB01) SPACE(*) RESTRICT | No unexpected restrict states | Display output
1.d | Verify DSNDB06 restrict state | DISPLAY DB(DSNDB06) SPACE(*) RESTRICT | No unexpected restrict states | Display output
1.e | Verify utilities are drained | -DISPLAY UTILITY(*) | No active utilities on catalog/directory | Display output
2 | Run DSNTIJFV | Rename cataloged procedures and reactivate Db2 12 code (p.571) | Catalog procedures reverted to V12 | DSNTIJFV job log
2.a | Update DB2 PROCs | Rename DB2TN.SHR.DSNLOAD → .BKUPV13; restore .BKUPV12 | V12 load libraries active | Dataset rename evidence
2.b | APF updates | Remove/add APF entries as required | Correct APF authorization | APF list snapshot
2.c | Validate STEPLIB/LINKLIST | Ensure no Db2 13 libraries remain | Clean execution path | STEPLIB/LINKLIST listing
3 | Reconnect subsystems | Reconnect TSO, IMS, CICS (p.572) | Subsystems ready for Db2 12 | Subsystem logs
3.a | Re-establish V12 procedures | Point procs to V12 libraries | Correct procedure resolution | Proc members
4 | Stop DB2 V13 (final) | /=STOP DB2 | Db2 V13 fully stopped | Db2 stop messages
4.a | Start DB2 V12 | /=START DB2 | Db2 V12 started successfully | Startup messages
4.b | Verify Db2 member status | -DISPLAY DB2-DISPLAY GROUP DETAIL | Member active and healthy | Command output
5 | Run DB2 V12 IVP jobs | DSNTEJxx validation (p.574) | V12 environment validated | Job outputs
5.a | DSNTEJ2A | DB2PN.DB2V12.TDB2.SDSNSAMP(DSNTEJ2A) | Basic Db2 validation successful | JES output
5.b | DSNTEJ2C | DB2PN.DB2V12.TDB2.SDSNSAMP(DSNTEJ2C) | SQL and catalog checks pass | JES output
5.c | DSNTEJ2D | DB2PN.DB2V12.TDB2.SDSNSAMP(DSNTEJ2D) | Db2 functions verified | JES output
5.d | DSNTEJ2F | DB2PN.DB2V12.TDB2.SDSNSAMP(DSNTEJ2F) | Utilities validated | JES output
5.e | DSNTEJ2P | Run STEP PH02PS05 only | Package bind verification | JES output
6 | Validate DDF | -DISPLAY DDF-START DDF (if required) | Distributed access validated | DDF command output
7 | Test applications | Execute business validation tests | Applications function normally | Test results
8 | Optional REBIND (if required) | Rebind packages with V12 APPLCOMPAT | Stable access paths | REBIND job output
9 | Retry failed scenario | Re-run failing workload | Issue reproduced or resolved | Incident evidence

## Validation Checklist
DB2D Validation Checklist
S.No | Task | Command & Job Details | Comments | DB2D Status | TDB2 Status
1 | Execute -DISPLAY GROUP DETAIL | Issue command:-DISPLAY GROUP DETAILVerify member status, group attach name, CF structures, and Db2 level |  | done
2 | Validate Db2 subsystem status | Issue commands:-DISPLAY DB2-DISPLAY THREAD(*) | All members ACTIVE, no hung threads | done
3 | Validate Admin Tool | Launch Admin Tool (ADBTEP2/ADBTEPA) via TSO/ISPFValidate catalog access and basic object browse | Tool launches without errors | done
4 | Validate QMF | Log in to QMF for TSO/ISPFRun a sample catalog query (e.g., SYSIBM.SYSTABLES) | QMF connects successfully | ISPF QMF not batch
5 | Validate SPUFI | Invoke SPUFI via ISPF optionExecute a simple SELECT statement | SQL executes without error | ISPF SPUFI and Batch
6 | Validate OMEGAMON for Db2 | Access OMEGAMON Db2 workspaceValidate thread activity, buffer pools, logs, and locking panels | All Db2 metrics visible
7 | Validate PowerExchange (PWX) tasks | Verify PWX started tasks are activeCheck JES logs and PWX console messages | PWX tasks running normally
8 | Validate QLIK connectivity | Execute QLIK reload or connectivity test to Db2 DDF endpoint | Successful data refresh
9 | Validate DDF connectivity | Issue commands:-DISPLAY DDF-DISPLAY THREAD(*) TYPE(SYSTEM) | DDF ACTIVE, no auth failures
10 | Validate IMS attachment | Verify IMS Db2 attachment regionCheck IMS logs and issue test transaction | IMS-Db2 connectivity OK
11 | Validate CICS attachment | Validate CICS Db2 attachment (DSNCLI/DSNC transaction)Run test CICS-Db2 transaction | CICS connectivity OK
12 | Validate z/OS Connect (if applicable) | Execute REST API call mapped to Db2Verify successful response | API responds successfully
13 | Execute critical Db2 utilities | Run sample utilities:• RUNSTATS• COPY• REORG (TEST object)Verify completion codes | Utilities complete RC=0/4
14 | Validate REBIND status | Review REBIND job outputsCheck for SQLCODE -4743 / -4742 | No REBIND failures
15 | Validate application connectivity | Execute representative batch and online jobs | Applications functional
16 | Validate logs and BSDS | Issue commands:-DISPLAY LOG-DISPLAY BSDS | Logs active, no BSDS issues
17 | Validate SMF / IFCID traces | Verify active traces:-DISPLAY TRACE(*) | Required traces enabled
18 | Validate performance baseline | Compare buffer hit ratios, CPU, EDM pools vs pre-fallback baseline | Performance within tolerance
19 | Review Db2 master and JES logs | Review DSNMSTR, DBM1, IRLM logs | No severe or recurring errors
20 | Sign-off validation | Obtain application and infrastructure sign-off | Validation complete