## Pre-Implementation Plan
S.No | Pre-Implementation Plan(PDB2) | Job details | Responsible Team | Status
1 | Take the dup of current SMP/E Libraries DB2PN.DB2V12.SDSNBASE DB2PN.DB2V12.SDSNBASU DB2PN.DB2V12.SDSNC.H DB2PN.DB2V12.SDSNCLST DB2PN.DB2V12.SDSNDBRM DB2PN.DB2V12.SDSNEXIT DB2PN.DB2V12.SDSNIVPD DB2PN.DB2V12.SDSNLINK DB2PN.DB2V12.SDSNLOAD DB2PN.DB2V12.SDSNLOD2 DB2PN.DB2V12.SDSNMACS DB2PN.DB2V12.SDSNPFPE DB2PN.DB2V12.SDSNPFPK DB2PN.DB2V12.SDSNSAMP DB2PN.DB2V12.SDSNSPFM DB2PN.DB2V12.SDSNSPFP DB2PN.DB2V12.SDSNSPFS DB2PN.DB2V12.SDSNSPFT DB2PN.DB2V12.SDXRRESL |  | DB2 | DUMP DATASET - DB2PN.DB2V12.PDB2.RSU2312.SMPEDMP.D110824
2 | Take the dup of current runtime libraries - PDB2 SYS1.DSN.SSPGM DB2PN.PDB2.SDSNEXIT DB2PN.PDB2.SDXRRESL |  | DB2 | DUMP DATASET - DB2PN.DB2V12.PDB2.RSU2312.PDB2DMP.D110824, DB2PN.DB2V12.DSN.SSPGM.BKUP
3 | Take the dup of current runtime libraries - DB2S SYS1.DB2S.SDSNLOAD DB2PN.DB2S.SDSNEXIT DB2PN.DB2S.SDXRRESL |  | DB2 | DUMP DATASET -DB2PN.DB2V12.PDB2.RSU2312.DB2SDMP.D110824, DB2PN.DB2V12.DB2S.SDSNLOAD.BKUP
4 | Take the dup of RUNLIB DB2PN.DB2V12.RUNLIB.LOAD |  | DB2 | DB2PN.DB2V12.RUNLIB.LOAD.D051124
5 | Backup of DB2PN.DB2V12.SDSNLINK.BKP |  | DB2 | DB2PN.DB2V12.SDSNLINK.BKP.D051124
6 | Execute Jobs (J0, J1, TESQ) | ] | DB2
\

## Implementation Plan
S.No | Implementation Plan(PDB2 & DB2S) | Job/Command | Responsible Team | Status
1 | Bring down enqueues |  | Production Control | Completed for DB2S & PDB2
2 | Bring down DB2 |  | Production Control | Completed for DB2S & PDB2
3 | Remove below dataset from LLA, XCFAS SYS1.DSN.SSPGM |  | z/OS | Completed for PDB2
4 | Rename runtime libraries and copy the new maintenance to current runtime libraries | DB2PN.DB2V12.PDB2.RSU2312.JCL(RENAMEA) - PDB2 DB2PN.DB2V12.DB2S.RSU2312.JCL(RENAMEA) - DB2S | DB2 | Completed for DB2S - T0B0GUOR JOB17897 Compelted for PDB2 - T0B0GOMR JOB18124
5 | Perform Holdactions | DB2PN.DB2V12.PDB2.RSU2312.JCL(DSNTIJUZ) DB2PN.DB2V12.DB2S.RSU2312.JCL(DSNTIJUZ) | DB2 | Completed for DB2S - DB2SIJUZ JOB17899 Completed for PDB2 - PDB2IJUZ JOB18125
6 | Copy ZPARM module DB2PN.PDB2.SDSNEXIT(DSNZPARP) to SYS1.DSN.SSPGM |  | DB2 | Completed for PDB2 - T0B0GUOC JOB18126
| Copy ZPARM module DB2PN.DB2S.SDSNEXIT(DSNZPARS) to SYS1.DB2S.SDSNLOAD |  | DB2 | Completed for DB2S - T0B0GUOC JOB17903
7 | Perform LLA Refresh and dataset SYS1.DSN.SSPGM to be added to LLA |  | z/OS | Completed
8 | Perform DB2 refresh for Early code | /+ REFRESH DB2,EARLY - PDB2 /! REFRESH DB2,EARLY - DB2S | DB2 | Completed for DB2S Completed for PDB2
9 | Start DB2 in Access Maint | /+ START DB2 ACCESS(MAINT) - PDB2 /! START DB2 ACCESS(MAINT) - DB2S | DB2 | Completed for DB2S Completed for PDB2
10 | Issue DISPLAY GROUP COMMAND | (-DISPLAY GROUP DETAIL) | DB2 | Completed for DB2S - T0B0GUOD JOB17925 Completed for PDB2 - T0B0GUOD JOB18150
11 | Execute DSNTEJ1L and DSNTEJ2A | DB2PN.DB2V12.PDB2.RSU2312.JCL DB2PN.DB2V12.DB2S.RSU2312.JCL | DB2 | Completed for DB2S Completed for PDB2
12 | Execute DSNTIJTM Job | DB2PN.DB2V12.PDB2.RSU2312.JCL DB2PN.DB2V12.DB2S.RSU2312.JCL | DB2 | Completed for DB2S - T0B0GUOM JOB17977 Completed for PDB2 - PDB2IJTM JOB18155
13 | Execute DSNTIJCL Job | DB2PN.DB2V12.PDB2.RSU2312.JCL DB2PN.DB2V12.DB2S.RSU2312.JCL | DB2 | Completed for DB2S - T0B0GUOL JOB17990 Completed for PDB2 - PDB2IJCL JOB18160
14 | Execute DSNTIJRT Job | DB2PN.DB2V12.PDB2.RSU2312.JCL DB2PN.DB2V12.DB2S.RSU2312.JCL | DB2 | Completed for DB2S - T0B0GUOT JOB18008 Completed for PDB2 - PDB2IJRT JOB18161
15 | Execute DSNTIJSG Job | DB2PN.DB2V12.PDB2.RSU2312.JCL DB2PN.DB2V12.DB2S.RSU2312.JCL | DB2 | Completed for DB2S - T0B0GUOG JOB18045 Completed for PDB2 - PDB2IJSG JOB18163
16 | Stop DB2 | /+ STOP DB2 - PDB2 /! STOP DB2 - DB2S | DB2 | Completed for DB2S Completed for PDB2
Proceed with IPL

## Validation Plan
S.No | Validation Plan(PDB2 & DB2S) | Job/Command | Status
1 | Execute DSNTEJ0, DSNTEJ1, TESQ | DB2PN.DB2V12.PDB2.RSU2312.JCL DB2PN.DB2V12.DB2S.RSU2312.JCL | J0, J1, TESQ JOBS TO BE SUBMITTED
2 | Validate DB2 tools |  | Completed
send mail to application team to start their validation

## Sheet4
DB2PN.DB2V12.SDSNBASE
DB2PN.DB2V12.SDSNBASU
DB2PN.DB2V12.SDSNC.H
DB2PN.DB2V12.SDSNCLST
DB2PN.DB2V12.SDSNDBRM
DB2PN.DB2V12.SDSNEXIT
DB2PN.DB2V12.SDSNIVPD
DB2PN.DB2V12.SDSNLINK
DB2PN.DB2V12.SDSNLOAD
DB2PN.DB2V12.SDSNLOD2
DB2PN.DB2V12.SDSNMACS
DB2PN.DB2V12.SDSNPFPE
DB2PN.DB2V12.SDSNPFPK
DB2PN.DB2V12.SDSNSAMP
DB2PN.DB2V12.SDSNSPFM
DB2PN.DB2V12.SDSNSPFP
DB2PN.DB2V12.SDSNSPFS
DB2PN.DB2V12.SDSNSPFT
DB2PN.DB2V12.SDXRRESL