## DB2A - Pre-Implementation Steps
DB2 Function Level 510 Implementation Plan
S.No | Task | Command & Job Details | Status | Comments
1 | Execute DSNTIJPE and Clear all the actions coming up in the REPORT(01 to 21) | DB2TN.DB2V12.V12FL510.DB2A.SDSNSAMP(DB2AJPE) | Complete
2 | Check that Db2 is at a sufficient code level by issuing a DISPLAY GROUP command | DB2TN.DB2V12.V12FL510.DB2A.SDSNSAMP(DISGROUP)
3 | Backup of all the DB2 Runtime Libraries |  | Complete
4 | Run premigration job DSNTIJPE and verify if all the reports looks good | DB2TN.DB2V12.V12FL510.DB2A.SDSNSAMP(DB2AJPE)
5 | Execute CLIST to customize FL 510 Jobs | DB2TN.DB2V12.V12FL510.DB2A.SDSNSAMP | Complete
DB2TN.DB2V12.DBRMLIB.DATA
DB2TN.DB2V12.DBRMLIB.DATA.FL510.BKUP
DB2TN.DB2V12.SRCLIB.DATA
DB2TN.DB2V12.SRCLIB.DATA.FL510.BKUP
DB2TN.DB2V12.RUNLIB.LOAD
DB2TN.DB2V12.RUNLIB.LOAD.FL510.BKUP
DB2TN.DB2V12.SDSNEXIT
DB2TN.DB2V12.SDSNEXIT.FL510.BKUP
DB2TN.SHR.DB2A.DSNLOAD
DB2TN.SHR.DB2A.DSNLOAD.FL510.BKUP
DB2PN.DB2A.SDSNEXIT
DB2PN.DB2A.SDSNEXIT.FL510.BKUP

## DB2A Implementation Steps
DB2 Function Level 510 Implementation Plan
S.No | Task | Command & Job Details | Owner | Status | Comments
1 | Execute DISPLAY Command | DB2TN.DB2V12.V12FL510.DB2A.SDSNSAMP(DISPLAY) | DB2
2 | Run the DSNTIJIC job to take an image copy of the Db2 catalog and directory | DB2TN.DB2V12.V12FL510.DB2A.SDSNSAMP(DSNTIJIC) | DB2
3 | Execute DSNTIJUZ by changing Install SYSADM to DB2ADM | DB2TN.DB2V12.V12FL510.DB2A.SDSNSAMP(DSNTIJUZ) | DB2 |  | Required to submit jobs when DB2 is in maintenance mode ( only DB2 admins can access DB2 )
4 | Submit COPY job to copy the zparm module . | DB2TN.DB2V12.V12FL510.DB2A.SDSNSAMP(COPY1) | DB2
5 | Bring down DB2A and related enqueues |  | Production Control
6 | Bring up DB2A in maintenance mode | /_DB2A START DB2 ACCESS(MAINT) | DB2
7 | Run the CATMAINT utility with LEVEL V12R1M510 to update the CATALOG | DB2TN.DB2V12.V12FL510.DB2A.SDSNSAMP(DSNTIJTC) | DB2
8 | Verify Catalog level pointing it to V12R1F509 by issuing display GROUP DETAIL command | DB2TN.DB2V12.V12FL510.DB2A.SDSNSAMP(GROUP01) | DB2
9 | Run the tailored DSNTIJAF job with ACTIVATE TEST command | DB2TN.DB2V12.V12FL510.DB2A.SDSNSAMP(JAF1) | DB2
10 | Run the tailored DSNTIJAF job with ACTIVATE command | DB2TN.DB2V12.V12FL510.DB2A.SDSNSAMP(JAF2) | DB2
11 | Submit DSNTIJUA job by changing SQLLEVEL to V12R1M500 | DB2TN.DB2V12.V12FL510.DB2A.SDSNSAMP( DSNTIJUA) | DB2
12 | Submit COPY job to copy the DECP module | DB2TN.DB2V12.V12FL510.DB2A.SDSNSAMP(COPY2) | DB2
13 | Execute DISPLAY GROUP DETAIL COMMAND | DB2TN.DB2V12.V12FL510.DB2A.SDSNSAMP(GROUP02) | DB2
14 | Bring down DB2K and Bring up DB2K and it's enqueues |  | Production Control

## DB2A Validation Steps
DB2 Function Level 510 Implementation Plan
S.No | Task | Command & Job Details | Status | Comments
1 | Execute -DISPLAY GROUP DETAIL Job | DB2TN.DB2V12.V12FL510.DB2A.SDSNSAMP(DISPLAY)
2 | Validate Admin Tool
3 | Validate QMF
4 | Validate SPUFI
5 | Validate Omegamon
6 | Validate PWX Tasks
7 | Validate QLIK
6 | Execute Utilities